## Rekap BoQ Periode 2026
Compile All BOQ Material FTTH-OPEN-AREA RANCAMANYAR (PT. METANOUVA INFORMATIKA) |  |  |  |  | Cluster ID |  |  | NET-H-004396 |  |  |  |  | NET-H-004397 |  |  |  |  | NET-H-004938 |  |  |  |  | NET-H-004399 |  |  |  |  | NET-H-004400 |  |  |  |  | NET-H-004401 |  |  |  |  | NET-H-004402 |  |  |  |  | NET-H-004404 |  |  |  |  | NET-H-004405 |  |  |  |  | NET-H-004406 |  |  |  |  | NET-H-004409 | [7 empty] | NET-H-004410 |  | MF-H-000141
[5 empty] | Project Name |  | 13 | FTTH Open Area Rancamanyar RW 01 |  |  |  |  | FTTH Open Area Rancamanyar RW 02 |  |  |  |  | FTTH OPEN Area Rancamanyar RW 03 |  |  |  |  | FTTH OPEN Area Rancamanyar RW 04 |  |  |  |  | FTTH OPEN Arean Rancamanyar RW 05 |  |  |  |  | FTTH OPEN Arean Rancamanyar RW 06 |  |  |  |  | FTTH OPEN Arean Rancamanyar RW 07 |  |  |  |  | FTTH OPEN Arean Rancamanyar RW 09 |  |  |  |  | FTTH OPEN Arean Rancamanyar RW 10 |  |  |  |  | FTTH OPEN Arean Rancamanyar RW 11 |  |  |  |  | FTTH OPEN Arean Rancamanyar RW 14 | [7 empty] | FTTH OPEN Arean Rancamanyar RW 15 |  | POP Rancamanyar Baleendah
[5 empty] | Homepass Plan |  | 9324 | 353 |  |  |  |  | 861 |  |  |  |  | 1220 |  |  |  |  | 455 |  |  |  |  | 400 |  |  |  |  | 413 |  |  |  |  | 589 |  |  |  |  | 555 |  |  |  |  | 740 |  |  |  |  | 570 |  |  |  |  | 1722 | [7 empty] | 1446
[5 empty] | No. Tiket Release | [7 empty] | UR10074 |  |  |  |  | UR10468 |  |  |  |  | UR10558 |  |  |  |  | UR08988 |  |  |  |  | UR09954 |  |  |  |  | UR09786 |  |  |  |  | UR09788 |  |  |  |  | UR12267 |  |  |  |  | UR11024 |  |  |  |  | UR12741 | [7 empty] | UR11027 |  | UR11027
|  |  | Summary All Qty Material |  |  |  |  | Qty Material |  |  |  |  | Qty Material |  |  |  |  | Qty Material |  |  |  |  | Qty Material |  |  |  |  | Qty Material |  |  |  |  | Qty Material |  |  |  |  | Qty Material |  |  |  |  | Qty Material |  |  |  |  | Qty Material |  |  |  |  | Qty Material |  |  |  |  | Qty Material |  |  |  |  | Qty Material |  |  |  |  | Qty Material
Deskripsi | Material Code | Satuan | BoQ Plan | Additional | MOS | Used | Remains | BoQ Plan | Additional | MOS | Used | Remains | BoQ Plan | Additional | MOS | Used | Remains | BoQ Plan | Additional | MOS | Used | Remains | BoQ Plan | Additional | MOS | Used | Remains | BoQ Plan | Additional | MOS | Used | Remains | BoQ Plan | Additional | MOS | Used | Remains | BoQ Plan | Additional | MOS | Used | Remains | BoQ Plan | Additional | MOS | Used | Remains | BoQ Plan | Additional | MOS | Used | Remains | BoQ Plan | Additional | MOS | Used | Remains | BoQ Plan | Additional | MOS | Used | Remains | BoQ Plan | Additional | MOS | Used | Remains | BoQ Plan | Additional | MOS | Used | Remains
TIANG 7 METER - 3" OD.90 X 2.8 X 7000 | [01-013-13103] | Batang | 378 | 2 | 378 | 15 | -2 | 9 | 2 | 9 | 15 | -2 | 27 |  | 27 |  | 0 | 20 |  | 20 |  | 0 | 21 |  | 21 |  | 0 | 5 |  | 5 |  | 0 | 19 |  | 19 |  | 0 | 19 |  | 19 |  | 0 | 3 |  | 3 |  | 0 | 50 |  | 50 |  | 0 | 24 |  | 24 |  | 0 | 120 |  | 120 |  | 0 | 25 |  | 25 |  | 0 | 36 |  | 36 |  | 0
TIANG 6 METER - 2" OD.57 X 1.5 X 6000 | [01-013-13104] | Batang | 628 | 0 | 631 | 0 | 3 | 28 |  | 28 |  | 0 | 52 |  | 52 |  | 0 | 89 |  | 89 |  | 0 | 34 |  | 34 |  | 0 | 44 |  | 44 |  | 0 | 35 |  | 35 |  | 0 | 53 |  | 53 |  | 0 | 56 |  | 56 |  | 0 | 37 |  | 37 |  | 0 | 41 |  | 41 |  | 0 | 56 |  | 56 |  | 0 | 103 |  | 106 |  | 3 |  |  |  |  | 0
CLOSURE DACK 288 CORE FIBERTRON (LOGO) | NWK-00468 | Unit | 14 | 0 | 12 | 0 | -2 | 1 |  | 1 |  | 0 | 1 |  | 1 |  | 0 |  |  | 1 |  | 1 | 1 |  | 1 |  | 0 | 1 |  | 1 |  | 0 | 1 |  | 1 |  | 0 |  |  | 1 |  | 1 | 1 |  | 1 |  | 0 | 1 |  | 1 |  | 0 | 1 |  | 1 |  | 0 | 1 |  | 1 |  | 0 | 0 |  | 1 |  | 1 | 5 |  |  |  | -5
CLOSURE DACK 144 CORE FIBERTRON (LOGO) | NWK-00466 | Unit | 22 | 0 | 22 | 0 | 0 | 1 |  | 1 |  | 0 | 1 |  | 1 |  | 0 | 4 |  | 4 |  | 0 | 1 |  | 1 |  | 0 | 1 |  | 1 |  | 0 |  |  |  |  | 0 | 2 |  | 2 |  | 0 | 1 |  | 1 |  | 0 | 2 |  | 2 |  | 0 | 1 |  | 1 |  | 0 | 5 |  | 5 |  | 0 | 3 |  | 3 |  | 0 |  |  |  |  | 0
24 CORE 4 FRP MICRO CABLE | [01-013-00010] | Meter | 0 | 0 | 5623 | 0 | 5623
KABEL FO 48 CORE ZTT 2024 | CBL-00043 | Meter | 11294 | 0 | 5681 | 0 | -5613 |  |  |  |  | 0 | 1557 |  | 1557 |  | 0 | 785 |  | 785 |  | 0 | 852 |  | 852 |  | 0 |  |  |  |  | 0 | 827 |  | 827 |  | 0 | 958 |  | 958 |  | 0 | 702 |  | 702 |  | 0 | 481 |  |  |  | -481 | 718 |  |  |  | -718 | 2642 |  |  |  | -2642 | 1772 |  |  |  | -1772 |  |  |  |  | 0
KABEL FO 48 CORE- 8 T 2023 | [01-013-00406] | Meter | 0 | 0 | 498 | 0 | 498 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 498 |  | 498 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
KABEL FO 48 CORE- 4 T 2023 | [01-013-00344] | Meter | 0 | 0 | 300 | 0 | 300 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 300 |  | 300 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
KABEL FO 24/2T ZTT 2024 | CBL-00461 | Meter | 10673 | 0 | 10043 | 0 | -630 | 907 |  | 907 |  | 0 | 140 |  | 140 |  | 0 | 1518 |  | 1518 |  | 0 | 197 |  | 197 |  | 0 | 990 |  | 990 |  | 0 |  |  |  |  | 0 | 270 |  | 270 |  | 0 | 267 |  | 267 |  | 0 | 1289 |  | 1289 |  | 0 | 791 |  | 791 |  | 0 | 2139 |  | 2139 |  | 0 | 1535 |  | 1535 |  | 0 | 630 |  |  |  | -630
KABEL FO 144C/12T ZTT 2024 | CBL-00465 | Meter | 1926 | 0 | 0 | 0 | -1926 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1926 |  |  |  | -1926
KABEL FO 96C/8T ZTT 2024 | 10001296 | Meter | 1898 | 0 | 0 | 0 | -1898 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1898 |  |  |  | -1898
KABEL FO 96/8T ZTT 2022 | 01-013-01273 | Meter | 0 | 0 | 740 | 0 | 740
KABEL FO 96C/8T Stralight 2025 | 01-013-06350 | Meter | 0 | 0 | 729 | 0 | 729
BRACKET TIANG DROP WIRE | CPT-00620 | Pcs | 117 | 0 | 125 | 0 | 8 | 4 |  | 4 |  | 0 | 10 |  | 10 |  | 0 | 14 |  | 14 |  | 0 | 6 |  | 6 |  | 0 | 5 |  | 5 |  | 0 | 5 |  | 5 |  | 0 | 7 |  | 7 |  | 0 | 6 |  | 6 |  | 0 | 10 |  | 10 |  | 0 | 8 |  | 8 |  | 0 | 25 |  | 25 |  | 0 | 17 |  | 25 |  | 8 |  |  |  |  | 0
BRACKET TIANG FLEXIBEL BEHEL PER (BRACKET C) | CPT-00623 | Pcs | 1056 | 0 | 1434 | 0 | 378 | 37 |  | 37 |  | 0 | 79 |  | 79 |  | 0 | 109 |  | 109 |  | 0 | 55 |  | 55 |  | 0 | 49 |  | 49 |  | 0 | 54 |  | 54 |  | 0 | 72 |  | 72 |  | 0 | 59 |  | 59 |  | 0 | 87 |  | 87 |  | 0 | 65 |  | 65 |  | 0 | 180 |  | 180 |  | 0 | 128 |  | 588 |  | 460 | 82 |  |  |  | -82
Strength Clamp Buaya 50/70 | 29000001 | Pcs | 1134 | 0 | 380 | 0 | -754 | 42 |  | 42 |  | 0 | 66 |  | 66 |  | 0 | 118 |  | 118 |  | 0 | 118 |  | 118 |  | 0 | 42 |  | 36 |  | -6 | 42 |  |  |  | -42 | 54 |  |  |  | -54 | 44 |  |  |  | -44 | 82 |  |  |  | -82 | 66 |  |  |  | -66 | 230 |  |  |  | -230 | 146 |  |  |  | -146 | 84 |  |  |  | -84
Strength Clamp Buaya 70/95 | 29000002 | Pcs | 70 | 0 | 112 | 0 | 42 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 70 |  | 112 |  | 42
KABEL DROPCORE PRECON 1 CORE 3 SELING SC/UPC-SC/UPC 50 METER | CBL-00215 | Pcs | 19 | 0 | 0 | 0 | -19 | 3 |  |  |  | -3 | 1 |  |  |  | -1 | 10 |  |  |  | -10 | 1 |  |  |  | -1 |  |  |  |  | 0 |  |  |  |  | 0 | 1 |  |  |  | -1 | 3 |  |  |  | -3 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
KABEL DROPCORE PRECON 1 CORE 3 SELING SC/UPC-SC/UPC 75 METER | CBL-00225 | Pcs | 80 | 0 | 3 | 0 | -77 | 3 |  | 3 |  | 0 | 9 |  |  |  | -9 | 20 |  |  |  | -20 | 6 |  |  |  | -6 | 6 |  |  |  | -6 | 11 |  |  |  | -11 | 11 |  |  |  | -11 | 14 |  |  |  | -14 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
KABEL DROPCORE PRECON 1 CORE 3 SELING SC/UPC-SC/UPC 100 METER | CBL-00220 | Pcs | 323 | 0 | 400 | 0 | 77 | 7 |  | 7 |  | 0 | 18 |  | 18 |  | 0 | 33 |  | 33 |  | 0 | 11 |  | 11 |  | 0 | 8 |  | 8 |  | 0 | 10 |  | 10 |  | 0 | 12 |  | 12 |  | 0 | 8 |  | 8 |  | 0 | 44 |  | 44 |  | 0 | 26 |  | 26 |  | 0 | 80 |  | 80 |  | 0 | 66 |  | 143 |  | 77 |  |  |  |  | 0
KABEL DROPCORE PRECON 1 CORE 3 SELING SC/UPC-SC/UPC 150 METER | CBL-00223 | Pcs | 215 | 0 | 215 | 0 | 0 | 10 |  | 10 |  | 0 | 23 |  | 23 |  | 0 | 22 |  | 22 |  | 0 | 9 |  | 9 |  | 0 | 10 |  | 10 |  | 0 | 10 |  | 10 |  | 0 | 11 |  | 11 |  | 0 | 13 |  | 13 |  | 0 | 16 |  | 16 |  | 0 | 14 |  | 14 |  | 0 | 47 |  | 47 |  | 0 | 30 |  | 30 |  | 0 |  |  |  |  | 0
KABEL DROPCORE PRECON 1 CORE 3 SELING SC/UPC-SC/UPC 200 METER | CBL-00226 | Pcs | 91 | 0 | 91 | 0 | 0 | 4 |  | 4 |  | 0 | 12 |  | 12 |  | 0 | 11 |  | 11 |  | 0 | 7 |  | 7 |  | 0 | 2 |  | 2 |  | 0 | 2 |  | 2 |  | 0 | 11 |  | 11 |  | 0 | 5 |  | 5 |  | 0 | 5 |  | 5 |  | 0 | 7 |  | 7 |  | 0 | 12 |  | 12 |  | 0 | 13 |  | 13 |  | 0 |  |  |  |  | 0
KABEL DROPCORE PRECON 1 CORE 3 SELING SC/UPC-SC/UPC 250 METER | CBL-00229 | Pcs | 28 | 0 | 28 | 0 | 0 | 3 |  | 3 |  | 0 | 5 |  | 5 |  | 0 | 3 |  | 3 |  | 0 | 2 |  | 2 |  | 0 | 4 |  | 4 |  | 0 |  |  |  |  | 0 | 3 |  | 3 |  | 0 | 2 |  | 2 |  | 0 |  |  |  |  | 0 | 2 |  | 2 |  | 0 | 2 |  | 2 |  | 0 | 2 |  | 2 |  | 0 |  |  |  |  | 0
KABEL DROPCORE PRECON 1 CORE 3 SELING SC/UPC-SC/UPC 300 METER | CBL-00231 | Pcs | 4 | 0 | 5 | 0 | 1 |  |  |  |  | 0 | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1 |  | 2 |  | 1 | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
BRACKET X-FRAME BEHEL MINI 12X40X40 (HITAM-MERAH) | SPP-00100 | Pcs | 230 | 0 | 260 | 0 | 30 | 4 |  | 4 |  | 0 | 17 |  | 17 |  | 0 | 15 |  | 15 |  | 0 | 13 |  | 13 |  | 0 |  |  |  |  | 0 | 9 |  | 9 |  | 0 | 10 |  | 10 |  | 0 | 1 |  | 1 |  | 0 | 31 |  | 31 |  | 0 | 15 |  | 15 |  | 0 | 101 |  | 131 |  | 30 | 14 |  | 14 |  | 0 |  |  |  |  | 0
BRACKET X-FRAME BEHEL 12X65X65 | CPT-00655 | Pcs | 117 | 0 | 145 | 0 | 28 | 4 |  | 4 |  | 0 | 10 |  | 10 |  | 0 | 14 |  | 14 |  | 0 | 6 |  | 6 |  | 0 | 5 |  | 5 |  | 0 | 5 |  | 5 |  | 0 | 7 |  | 7 |  | 0 | 6 |  | 6 |  | 0 | 10 |  | 10 |  | 0 | 8 |  | 8 |  | 0 | 25 |  | 25 |  | 0 | 17 |  | 45 |  | 28 |  |  |  |  | 0
BRACKET COILAN X-FRAME (BESAR 4 PER) | CPT-00630 | Pcs | 62 | 0 | 61 | 0 | -1 | 3 |  | 3 |  | 0 | 4 |  | 4 |  | 0 | 3 |  | 3 |  | 0 | 3 |  | 3 |  | 0 | 2 |  | 2 |  | 0 | 3 |  | 3 |  | 0 | 3 |  | 3 |  | 0 | 2 |  | 2 |  | 0 | 4 |  | 4 |  | 0 | 5 |  | 5 |  | 0 | 10 |  | 10 |  | 0 | 6 |  | 6 |  | 0 | 14 |  | 13 |  | -1
BRACKET SALIB BARU | 90000151 | Pcs | 20 | 0 | 25 | 0 | 5 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 20 |  | 25 |  | 5
DUDUKAN CLOUSURE BRACKET COILAN X-FRAME (MODEL BARU) | CPT-00718 | Pcs | 62 | 0 | 61 | 0 | -1 | 3 |  | 3 |  | 0 | 4 |  | 4 |  | 0 | 3 |  | 3 |  | 0 | 3 |  | 3 |  | 0 | 2 |  | 2 |  | 0 | 3 |  | 3 |  | 0 | 3 |  | 3 |  | 0 | 2 |  | 2 |  | 0 | 4 |  | 4 |  | 0 | 5 |  | 5 |  | 0 | 10 |  | 10 |  | 0 | 6 |  | 6 |  | 0 | 14 |  | 13 |  | -1
MUR + BAUT STENLIS M10 - 1.5 X 45 | CPT-00914 | Pcs | 186 | 0 | 183 | 0 | -3 | 9 |  | 9 |  | 0 | 12 |  | 12 |  | 0 | 9 |  | 9 |  | 0 | 9 |  | 9 |  | 0 | 6 |  | 6 |  | 0 | 9 |  | 9 |  | 0 | 9 |  | 9 |  | 0 | 6 |  | 6 |  | 0 | 12 |  | 12 |  | 0 | 15 |  | 15 |  | 0 | 30 |  | 30 |  | 0 | 18 |  | 18 |  | 0 | 42 |  | 39 |  | -3
MUR + BAUT STENLIS M08 - 1.25 X 80 | 01-013-03083 | Pcs | 234 | 0 | 250 | 0 | 16 | 8 |  | 8 |  | 0 | 20 |  | 20 |  | 0 | 28 |  | 28 |  | 0 | 12 |  | 12 |  | 0 | 10 |  | 10 |  | 0 | 10 |  | 10 |  | 0 | 14 |  | 14 |  | 0 | 12 |  | 12 |  | 0 | 20 |  | 20 |  | 0 | 16 |  | 16 |  | 0 | 50 |  | 50 |  | 0 | 34 |  | 50 |  | 16 |  |  |  |  | 0
ODP Boxes 16 port with 1:8 PLC Splitter including accessories but without connector and adapter | GT0000100 | Unit | 117 | 0 | 117 | 0 | 0 | 4 |  | 4 |  | 0 | 10 |  | 10 |  | 0 | 14 |  | 14 |  | 0 | 6 |  | 6 |  | 0 | 5 |  | 5 |  | 0 | 5 |  | 5 |  | 0 | 7 |  | 7 |  | 0 | 6 |  | 6 |  | 0 | 10 |  | 10 |  | 0 | 8 |  | 8 |  | 0 | 25 |  | 25 |  | 0 | 17 |  | 17 |  | 0 |  |  |  |  | 0
Outdoor Connector with SC/UPC adapter, magenta color | GT0000201M | Pcs | 1739 | 0 | 883 | 0 | -856 | 62 |  | 62 |  | 0 | 152 |  | 152 |  | 0 | 215 |  | 215 |  | 0 | 86 |  | 86 |  | 0 | 74 |  | 74 |  | 0 | 75 |  | 75 |  | 0 | 106 |  | 83 |  | -23 | 95 |  |  |  | -95 | 147 |  | 136 |  | -11 | 113 |  |  |  | -113 | 357 |  |  |  | -357 | 257 |  |  |  | -257 |  |  |  |  | 0
Outdoor Connector with SC/UPC adapter, silver color | GT0000201S | Pcs | 8163 | 0 | 8163 | 0 | 0 | 302 |  | 302 |  | 0 | 728 |  | 728 |  | 0 | 1039 |  | 1039 |  | 0 | 390 |  | 390 |  | 0 | 346 |  | 346 |  | 0 | 355 |  | 355 |  | 0 | 506 |  | 506 |  | 0 | 471 |  | 471 |  | 0 | 683 |  | 683 |  | 0 | 505 |  | 505 |  | 0 | 1613 |  | 1613 |  | 0 | 1225 |  | 1225 |  | 0 |  |  |  |  | 0
ODP 10 PORT WITH 8PCS SC UPC ADAPTER AND OUTDOOR CONNECTOR | NWK-00964 | Unit | 803 | 0 | 1197 | 0 | 394 | 30 |  | 30 |  | 0 | 72 |  | 72 |  | 0 | 103 |  | 103 |  | 0 | 38 |  | 38 |  | 0 | 34 |  | 34 |  | 0 | 35 |  | 35 |  | 0 | 50 |  | 50 |  | 0 | 47 |  | 47 |  | 0 | 67 |  | 67 |  | 0 | 49 |  | 49 |  | 0 | 157 |  | 157 |  | 0 | 121 |  | 515 |  | 394 |  |  |  |  | 0
1:8 balanced PLC Splitter SC/UPC,G657A2,0.9mm,0.6m | 01-013-00225 | Pcs | 117 | 0 | 100 | 0 | -17 | 4 |  | 4 |  | 0 | 10 |  | 10 |  | 0 | 14 |  | 14 |  | 0 | 6 |  | 6 |  | 0 | 5 |  | 5 |  | 0 | 5 |  | 5 |  | 0 | 7 |  | 7 |  | 0 | 6 |  | 6 |  | 17 | 10 |  | 10 |  | 0 | 8 |  | 8 |  | 0 | 25 |  | 25 |  | 0 | 17 |  |  |  | 0 |  |  |  |  | 0
1*8 PLC SPLITTER 1:8 | 01-013-00004 | Pcs | 34 | 0 | 0 | 0 | -34 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 34 |  |  |  | -34 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
1:8 balanced PLC Splitter SC/UPC,G657A2,0.9mm,0.6m WITH CONNECTOR INPUT | 00-013-13404 | Pcs | 769 | 0 | 1572 | 0 | 803 | 30 |  | 30 |  | 0 | 72 |  | 72 |  | 0 | 103 |  | 103 |  | 0 | 38 |  | 38 |  | 0 |  |  |  |  | 0 | 35 |  | 35 |  | 0 | 50 |  | 50 |  | 0 | 47 |  | 47 |  | 0 | 67 |  | 67 |  | 0 | 49 |  | 49 |  | 0 | 157 |  | 157 |  | 0 | 121 |  | 924 |  | 803 |  |  |  |  | 0
PATCHCORD LC/UPC - SC/UPC 3 METER ( Simplex ) | JTR-02242 | Pcs | 117 | 0 | 117 | 0 | 0 | 4 |  | 4 |  | 0 | 10 |  | 10 |  | 0 | 14 |  | 14 |  | 0 | 6 |  | 6 |  | 0 | 5 |  | 5 |  | 0 | 5 |  | 5 |  | 0 | 7 |  | 7 |  | 0 | 6 |  | 6 |  | 0 | 10 |  | 10 |  | 0 | 8 |  | 8 |  | 0 | 25 |  | 25 |  | 0 | 17 |  | 17 |  | 0 |  |  |  |  | 0
Precon 3m (Produksi in-House MSP) | In MSP | Pcs | 43 | 0 | 43 | 0 | 0 |  |  |  |  | 0 | 3 |  | 3 |  | 0 | 4 |  | 4 |  | 0 | 2 |  | 2 |  | 0 | 3 |  | 3 |  | 0 | 1 |  | 1 |  | 0 | 1 |  | 1 |  | 0 | 2 |  | 2 |  | 0 | 2 |  | 2 |  | 0 |  |  |  |  | 0 | 15 |  | 15 |  | 0 | 10 |  | 10 |  | 0 |  |  |  |  | 0
Outdoor Connector With SC/UPC Adapter, green color | 01-013-00587 | Pcs | 0 | 0 | 1952 |  | 1952 |  |  | 170 |  | 170 |  |  | 162 |  | 162 |  |  | 162 |  | 162 |  |  | 162 |  | 162 |  |  | 162 |  | 162 |  |  | 162 |  | 162 |  |  | 162 |  | 162 |  |  | 162 |  | 162 |  |  | 162 |  | 162 |  |  | 162 |  | 162 |  |  | 162 |  | 162 |  |  | 162 |  | 162 |  |  |  |  | 0
STAINLESS BELT NON MAGNET | [01-013-11630] | Rol (50) | 0 | 0 | 2 |  | 2 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2 |  | 2
STOPPING BUCKLER | [01-013-01157] | Pcs | 0 | 0 | 1010 |  | 1010 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 1010 |  | 1010
CLAMP DROP WIRE ( S CLAMP ) | [01-013-08487] | Pcs | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
ADAPTER LC/UPC DUPLEX AUTO SHUTTER | 01-013-00033 | Unit | 147 | 0 | 0 |  | -147 | [60 empty] | 147 |  |  |  | -147
OTB RACK PAZ 48 core LC/UPC | JTR-02154 | Units | 6 | 0 | 0 |  | -6 | [60 empty] | 6 |  |  |  | -6
CABLE MANAGEMENT METAL 1U ( CCM-M1U-BLK ) | CPT-00671 | Units | 6 | 0 | 0 |  | -6 | [60 empty] | 6 |  |  |  | -6
KSS Spiral Wrapping Band KS-6BK Hitam 10m | 90000156 | Units | 14 | 0 | 0 |  | -14 | [60 empty] | 14 |  |  |  | -14
CAGE NUT MUR + RING 6 | CPT-00674 | Units | 12 | 0 | 0 |  | -12 | [60 empty] | 12 |  |  |  | -12
FLEXIBLE WP 1/2" INCH | CPT-00753 | Meter | 5 | 0 | 0 |  | -5 | [60 empty] | 5 |  |  |  | -5
PIGTAIL LC/UPC | JTR-02401 | Unit | 288 | 0 | 0 |  | -288 | [60 empty] | 288 |  |  |  | -288
TIANG 9 METER - 3" OD.90 X 2.8 X 9000 | 01-013-13101 | Batang | 3 | 4 | 4 |  | -3 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 4 | 4 |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3 |  |  |  | -3
HOSE CLAMP/KLEM SELANG 1 1/2 INCH [25-38mm] | 29000006 | Unit | 3 | 0 | 0 |  | -3 | [60 empty] | 3 |  |  |  | -3
Nylon Cable Tie 3.6x300mm Hitam | 90000163 | Unit | 1 | 0 | 0 |  | -1 | [60 empty] | 1 |  |  |  | -1
Pipa Pralon 1,5inch | CPT-00533 | Batang | 1 | 0 | 0 |  | -1 | [60 empty] | 1 |  |  |  | -1
PLC SPLITTER 1X8 SC/UPC | [01-013-03725 | PCS | 0 | 0 | 94 |  | 94 |  |  | 7 |  | 7 |  |  | 7 |  | 7 |  |  | 7 |  | 7 |  |  | 7 |  | 7 |  |  | 7 |  | 7 |  |  | 7 |  | 7 |  |  | 7 |  | 7 |  |  | 7 |  | 7 |  |  | 7 |  | 7 |  |  | 7 |  | 7 |  |  | 7 |  | 7 |  |  | 17 |  | 17 |  |  |  |  | 0
Syarat & Ketentuan :
1. Mohon untuk seluruh mitra menggunakan template yg telah disediakan oleh PT. Remala Abadi Tbk
2. Template ini dibuat untuk memudahkan mitra pada saat melakukan compile keselurahan material yg telah diterima & untuk mempermudah pada saat rekonsil material yg telah di pick up
3. Pada saat Vendor melakukan request permintaan material kepada Team Project diwajibkan untuk mengirimankan Compile material excel (Hanya untuk project yg secara materialnya belum full fill)
4. Apabila ada deskripsi item list material diatas yang tidak tercantumkan mohon untuk disesuaikan & ditambahkan tabel dibawah
5. Untuk Project Backbone & FTTH mohon untuk dipisahkan excel Compile material BoQ nya
Note*
BoQ Plan : Mengacu kepada BoQ yg diterima dari WO email
Addtitional : Apabila ada penambahan material tambahan diluar dari WO BoQ Plan
MOS (Material On Site) : Material yang diterima oleh Mitra sesuai dengan Surat Jalan Pengambilan
Used : Material yang telah digunakan secara implementasi aktual
Remains : Sisa material yg belum dipick up

## Tracker (hidden)
[11 empty] | Wajib isi | [55 empty] | 52273
[7 empty] | Cluster input | [9 empty] | STATUS | [7 empty] | SPK SItac Survey | WO Sitac Survey | Sitac Input | [7 empty] | Survey Input |  |  |  |  | APD Input | [22 empty] | Budget Approval |  |  | PROJECT
No | Cluster / Funnel Name | Cluster ID | Project Name | FTTX Type | Metode | ID Pelanggan | Kota | Kecamatan | Kelurahan | Cluster Type | HP Estimate | ODN Plan | ODN Terpasang | Project Type | KSO Partner | KSO Contact | Vendor | Project Status | Gap Project Status | Remarks Project | Issue Project | Catagory Remark | SPK Numb | Obstacle | Date | No | Approaching Date | Re-Permit Date | BA Sitac Date | Sitac Status | Gap Analys Sitac | Sitac PIC | Skema | Remarks Sitac | Survey Date | Suvey PIC | Survey Status | HP After Survey | Remarks Survey | Pre-APD date | Final APD Date | HP APD | PIC APD | APD Status | Gap Analysis APD | APD Link | Remarks APD | BTS Tujuan | Jumlah Hub Box | Jumlah MS / Core | FAT / ODN | Plan Pole | Terpasang Pole | Pole EKSISTING | DW Dist (m) | 12c Dist (m) | 24c Dist (m) | 48c Feeder (m) | 72c Feeder (m) | 96c Feeder (m) | 144c Feeder (m) | 288c Feeder (m) | BA Date | BA Status | Gap Analysis BA | Project ID | HP Build | Req WO Civil Date | WO Civil Date | WO Civil Numb | WO Civil Status | Vendor Splice | Req WO Splice Date | WO Splice Date | WO Splice Number | WO Splice Status | Done Splice Date | RFS Declare
1 | FTTX Perumahan Mandosi Permai Tahap 2 | NET-H-000001 | FTTX Perumahan Mandosi Permai Tahap 2 | FTTH | Cascade |  | Kota Bekasi | Jatiasih | Jatiasih | Open Area | 127 | 8 | 8 | Non-KSO | Nethome |  | MKU (Mitra Karsa Utama) | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | Penjadwalan QC |  |  | 2022-11-05 |  |  | BA Done |  |  |  |  | 2023-02-27 |  | Done |  |  |  |  | 127 | Uli | Done | Uploaded to Drive | FTTX Perumahan Mandosi Permai Tahap 2 | - | BTS Komsen |  | 2 | 8 | 12 |  |  |  | 570 | [9 empty] | NET-H-000001 FTTX Perumahan Mandosi Permai Tahap 2 | 127 |  | 2023-05-15 |  | Done | [7 empty] | #REF! | #REF! | #REF!
2 | KSO BTS Ramli RW 004 Kalibaru | KSO-H-000001 | KSO BTS Ramli RW 004 Kalibaru | FTTH | Reverse |  | Jakarta Utara | Cilincing | Kalibaru | Open Area | 528 | 44 | 32 | KSO | Pak Ramli | 0878-7819-3232 | BMS | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | QC Done |  |  | 2023-02-19 |  |  | BA Done |  | Pak Ramli |  | Diurus Pak Ramli | 2023-02-19 |  | Done |  |  |  |  | 528 | 3party Pak Thandy | Done | Uploaded to Drive | KSO BTS Ramli RW 004 Kalibaru | - | [18 empty] | KSO-H-000001 KSO BTS Ramli RW 004 Kalibaru | 384 |  | 2023-07-18 |  | Done | [7 empty] | #REF! | #REF! | #REF!
3 | FTTX RW 006 Kaliabang Tengah | NET-H-000002 | FTTX RW 006 Kaliabang Tengah | FTTH | Cascade |  | Kota Bekasi | Bekasi Utara | Kaliabang Tengah | Open Area | 785 |  |  | Non-KSO | Nethome |  | Sinergi | 4. Electrical Work | 7. E2E Integration | Progress splice FAT & penambahan feeder 48 core | No Issue |  | - | Vendor sudah di ultimatum akan di Opname |  |  | 2023-03-27 |  |  | BA Done |  |  |  |  | 2023-03-27 |  | Done |  |  |  |  | 785 | 3party Pak Thandy | Done | Not Yet to Drive |  | - | [18 empty] | NET-H-000002 FTTX RW 006 Kaliabang Tengah |  |  | 2023-07-10 |  | Done | [7 empty] | #REF! | #REF! | #REF!
4 | FTTX RW 003 Bantar Gebang | NET-H-000003 | FTTX RW 003 Bantar Gebang | FTTH | Cascade |  | Kota Bekasi | Bantar Gebang | Bantar Gebang | Open Area | 1000 |  |  | Non-KSO | Nethome |  | BMS | 2. Survey, Sitac & Design | 1. Sitac Process | WO sudah implementasi turun ke Vendor tetapi BA permit awal sudah tdak berlaku | No Issue |  | - | Repermit - Kendala belum dapat ijin tanam tiang |  |  | 2023-03-13 |  |  | BA Done |  |  |  |  | 2023-03-18 |  | Done |  |  |  | 2023-04-08 | 1000 | 3party Pak Thandy | Done | Uploaded to Drive | FTTX RW 003 Bantar Gebang | - | [18 empty] | NET-H-000003 FTTX RW 003 Bantar Gebang |  |  | 2023-04-11 | 0007/SVY-BMS/FMI/IV/2023 | Done | [7 empty] | #REF! | #REF! | #REF!
5 | FTTX RW 001 Kelurahan Rambutan | KSO-H-000002 | FTTX RW 001 Kelurahan Rambutan | FTTH | Cascade |  | Jakarta Timur | Ciracas | Rambutan | Open Area | 382 |  |  | KSO | Pak Aqil | 0811-1442-909 | BMS | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - |  |  |  | 2023-04-13 |  |  | BA Done |  | Pak Aqil |  | Diurus Pak Aqil | 2023-04-13 |  | Done |  |  |  |  | 382 | 3party Pak Thandy | Done | Uploaded to Drive | FTTX RW 001 Kelurahan Rambutan | - | [18 empty] | KSO-H-000002 FTTX RW 001 Kelurahan Rambutan | 382 |  | 2023-05-12 | 0061/SVY-BMS/FMI/V/2023 | Done | [7 empty] | #REF! | #REF! | #REF!
6 | FTTX RW 002 Kelurahan Rambutan | KSO-H-000003 | FTTX RW 002 Kelurahan Rambutan | FTTH | Cascade |  | Jakarta Timur | Ciracas | Rambutan | Open Area | 384 |  |  | KSO | Pak Aqil | 0811-1442-909 | - | 1. Reject | Reject |  |  |  | - |  |  |  | 2023-04-13 |  |  | On Progress |  | Pak Aqil |  | Diurus Pak Aqil | 2023-04-13 |  | Done |  |  |  |  | 384 | 3party Pak Thandy | Done | Uploaded to Drive | FTTX RW 002 Kelurahan Rambutan | - | [18 empty] | KSO-H-000003 FTTX RW 002 Kelurahan Rambutan | [12 empty] | #REF! | #REF! | #REF!
7 | FTTX RW 003 Kelurahan Dukuh | KSO-H-000004 | FTTX RW 003 Kelurahan Dukuh | FTTH | Reverse |  | Jakarta Timur | Kramatjati | Dukuh | Open Area | 641 |  |  | KSO | Pak Aqil | 0811-1442-909 | BMS | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | QC Done |  |  | 2023-04-13 |  |  | BA Done |  | Pak Aqil |  | Diurus Pak Aqil | 2023-04-13 |  | Done |  |  |  |  | 641 | 3party Pak Thandy | Done | Uploaded to Drive | FTTX RW 003 Kelurahan Dukuh | - | [18 empty] | KSO-H-000004 FTTX RW 003 Kelurahan Dukuh | 641 |  | 2023-05-12 | 0060/SVY-BMS/FMI/V/2023 | Done | [7 empty] | #REF! | #REF! | #REF!
8 | FTTX RW 004 Kelurahan Dukuh | KSO-H-000005 | FTTX RW 004 Kelurahan Dukuh | FTTH | Cascade |  | Jakarta Timur | Kramatjati | Dukuh | Open Area | 1192 |  |  | KSO | Pak Aqil | 0811-1442-909 | - | 1. Reject | Reject |  |  |  | - |  |  |  | 2023-04-13 |  |  | On Progress |  | Pak Aqil |  | Diurus Pak Aqil | 2023-04-13 |  | Done |  |  |  |  | 1192 | 3party Pak Thandy | Done | Uploaded to Drive | FTTX RW 004 Kelurahan Dukuh | - | [18 empty] | KSO-H-000005 FTTX RW 004 Kelurahan Dukuh | [12 empty] | #REF! | #REF! | #REF!
9 | FTTX RW 005 Bantar Gebang | NET-H-000004 | FTTX RW 005 Bantar Gebang | FTTH | Reverse |  | Kota Bekasi | Bantar Gebang | Bantar Gebang | Open Area | 532 |  |  | Non-KSO | Nethome |  | BMS | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | QC Done |  |  | 2023-03-13 |  |  | BA Done |  |  |  |  | 2023-03-18 |  | Done |  |  |  | 2023-04-08 | 532 | 3party Pak Thandy | Done | Uploaded to Drive | FTTX RW 005 Bantar Gebang | - | [18 empty] | NET-H-000004 FTTX RW 005 Bantar Gebang | 532 |  | 2023-04-04 | 0005/SVY-BMS/FMI/IV/2023 | Done | [7 empty] | #REF! | #REF! | #REF!
10 | FTTX RW 001 Kelurahan Cisalak Depok | NET-H-000005 | FTTX RW 001 Kelurahan Cisalak Depok | FTTH | Cascade |  | Kota Depok | Sukmajaya | Cisalak | Open Area | 750 |  |  | Non-KSO | Nethome |  | - | 1. Reject | Reject |  |  |  | - |  |  |  | 2023-03-27 |  |  | Approaching | [6 empty] | Not Yet | [6 empty] | Not Yet |  |  | - | [18 empty] | NET-H-000005 FTTX RW 001 Kelurahan Cisalak Depok | [12 empty] | #REF! | #REF! | #REF!
11 | FTTX RW 006 Jatiraden | NET-H-000006 | FTTX RW 006 Jatiraden | FTTH | QODN |  | Kota Bekasi | Jatisampurna | Jatiraden | Open Area | 760 |  |  | Non-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | assign Vendor | Issue Space Tiang | Permit Issue | - | Repermit - kendala RW & RT meminta kompensasi lagi 4 juta rw per Rt 2 juta (6 RT) |  |  | 2023-03-27 | 2023-04-05 |  | NY Start Permit |  |  |  |  | 2023-04-06 |  | Done | [5 empty] | Uli | Done | Uploaded to Drive | FTTX RW 006 Jatiraden | Sudah catu ke BB Existing FMI | BTS Jatiraden Sarto |  | 6 | 41 | 94 |  |  |  | 2450 |  | 1775 | [7 empty] | NET-H-000006 FTTX RW 006 Jatiraden |  |  |  |  | Done
12 | FTTX RW 09 Desa Bojong Nangka | NET-H-000007 | FTTX RW 09 Desa Bojong Nangka | FTTH | QODN |  | Kab. Bogor | Gunung Putri | Bojong Nangka | Open Area | 480 |  |  | Non-KSO | Nethome |  | - | 1. Reject | Reject |  | Lebih dari 3 Provider | Permit Issue | - |  |  |  | 2023-03-27 |  |  | Approaching | [6 empty] | Not Yet | [6 empty] | Not Yet |  |  | - | [18 empty] | NET-H-000007 FTTX RW 09 Desa Bojong Nangka
13 | FTTX RW 02 JATILUHUR | NET-H-000008 | FTTX RW 02 JATILUHUR | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatiluhur | Open Area | 1608 |  |  | Non-KSO | Nethome |  | - | 1. Reject | Reject |  | High Price Issue | High Price | - |  |  |  | 2023-03-27 | 2023-04-14 |  | Approaching |  |  |  | Pergantian Pengurus |  |  | Not Yet | [6 empty] | Not Yet |  |  | - | [18 empty] | NET-H-000008 FTTX RW 02 JATILUHUR
14 | FTTX RW 01 Jatimakmur | NET-H-000009 | FTTX RW 01 Jatimakmur | FTTH | QODN |  | Kota Bekasi | Pondok Gede | Jatimakmur | Open Area | 626 |  |  | Non-KSO | Nethome |  | - | 1. Reject | Reject |  | Permit Issue By RW | Permit Issue | - |  |  |  | 2023-03-27 |  |  | Approaching | [6 empty] | Not Yet | [6 empty] | Not Yet |  |  | - | [18 empty] | NET-H-000009 FTTX RW 01 Jatimakmur
15 | FTTX RW 015 Padurenan | NET-H-000010 | FTTX RW 015 Padurenan | FTTH | QODN |  | Kota Bekasi | Mustika Jaya | Padurenan | Open Area | 634 |  |  | Non-KSO | Nethome |  | - | 1. Reject | Reject |  | Permit Issue By RW | Permit Issue | - |  |  |  | 2023-03-27 |  |  | Approaching | [6 empty] | Not Yet |  |  |  | 2023-09-07 |  | 3party Pak Thandy | Done | Uploaded to Drive | FTTX RW 015 Padurenan | Sudah mencatu ke ODC Existing | [18 empty] | NET-H-000010 FTTX RW 015 Padurenan
16 | FTTX RW 06 Jatimakmur | NET-H-000011 | FTTX RW 06 Jatimakmur | FTTH | Reverse |  | Kota Bekasi | Pondok Gede | Jatimakmur | Open Area | 750 |  |  | Non-KSO | Nethome |  | - | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | QC Done |  |  | 2023-03-27 |  |  | Approaching | [6 empty] | Not Yet |  |  |  | 2023-09-07 | 654 | 3party Pak Thandy | Done | Uploaded to Drive | FTTX RW 019 Jatimakmur | Sudah mencatu ke kabel distribusi RW09 Jatimakmur | [18 empty] | NET-H-000011 FTTX RW 06 Jatimakmur | 654 | [11 empty] | #N/A | #N/A | #N/A
17 | FTTX RW 02 Sumur Batu | NET-H-000012 | FTTX RW 02 Sumur Batu | FTTH | QODN |  | Kota Bekasi | Bantar Gebang | Sumur Batu | Open Area | 500 |  |  | Non-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process | On going Sitac (cek HP by Desk) | No Issue | Sitac On Process | - |  |  |  | 2023-03-27 |  |  | NY Start Permit |  | Zahrudin |  |  |  |  | Not Yet |  |  |  | 2023-09-07 |  | 3party Pak Thandy | Done | Uploaded to Drive | FTTX RW 02 Sumur Batu | Belum mencatu ke Existing | [18 empty] | NET-H-000012 FTTX RW 02 Sumur Batu
18 | FTTX RW 02 CIKIWUL | NET-H-000013 | FTTX RW 02 CIKIWUL | FTTH | QODN |  | Kota Bekasi | Bantar Gebang | Cikiwul | Open Area | 791 | 99 |  | Non-KSO | Nethome |  | TIT (Tauco Integra Telekomunikasi) | 1. Reject | Reject | Resurvey ulang oleh sitac inhouse untuk area yg UG | Tidak bisa tanam tiang diarea jalan utama (UG) | Installation On Progress | 0496/SPK-FMI/VII/24 |  |  |  | 2023-03-27 | 2023-04-05 |  | BA Done | [6 empty] | Not Yet | 791 |  |  | 2024-08-07 | 727 | Muchamad Rivai | Done | Uploaded to Drive | FTTX RW 02 CIKIWUL | Need Redesign Cascade to QODN | BTS Seven Net | 5 | 9 | 57 | 97 | 0 |  | 9067 | 2900 | 2600 | [8 empty] | NET-H-000013 FTTX RW 02 CIKIWUL | 0
19 | FTTX RW 04 Jatiasih | NET-H-000014 | FTTX RW 04 Jatiasih | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatiasih | Open Area | 750 |  |  | Non-KSO | Nethome |  | - | 1. Reject | Reject |  | High Price Issue | High Price | - |  |  |  | 2023-03-27 |  |  | Approaching | [6 empty] | Not Yet | [6 empty] | Not Yet |  |  | - | [18 empty] | NET-H-000014 FTTX RW 04 Jatiasih
20 | FTTX RW 04 Jatirasa (Replace RW 05 jatirasa Segmen 1) | NET-H-000015 | FTTX RW 04 Jatirasa (Replace RW 05 jatirasa Segmen 1) | FTTH | Reverse |  | Kota Bekasi | Jatiasih | Jatirasa | Open Area | 720 |  |  | Non-KSO | Nethome |  | LISMA | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | QC Done |  |  | 2023-03-27 | 2023-04-05 |  | BA Done |  |  |  |  | 2023-07-20 |  | Done |  |  |  |  | 1424 | Uli | Done | Uploaded to Drive | FTTX RW 04 Jatirasa (Replace RW 05 Jatirasa Segmen 1) | Sudah catu ke Closure existing | BTS Jatirasa Swatantra |  | 15 | 95 | 228 |  |  |  | 9920 |  | 1564 | [7 empty] | NET-H-000015 FTTX RW 04 Jatirasa (Replace RW 05 jatirasa Segmen 1) | 720 |  |  |  | Done | [7 empty] | #REF! | #REF! | #REF!
21 | KSO Pak Sarto Jatisampurna RW 01, 04, 05, 06, 07, 09, 16 | KSO-H-000006 | KSO Pak Sarto Jatisampurna RW 01, 04, 05, 06, 07, 09, 16 | FTTH | Reverse |  | Kota Bekasi | Jatisampurna | Jatisampurna | Open Area | 2292 | 185 | 170 | KSO | Pak Sarto | 0857-7979-6616 | Jangkar | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | QC Done |  |  | 2023-05-01 |  |  | BA Done |  | Pak Sarto |  | Diurus Pak Sarto | 2023-06-07 |  | Done |  |  |  |  | 2292 | 3party Pak Thandy | Done | Uploaded to Drive | KSO Pak Sarto Jatisampurna RW 1-15 | - | [18 empty] | KSO-H-000006 KSO Pak Sarto Jatisampurna RW 01, 04, 05, 06, 07, 09, 16 | 2040 |  |  | Done | Done | [7 empty] | #REF! | #REF! | #REF!
22 | KSO Pak Sarto Jatisampurna RW 02, 03, 08, 10, 11, 12, 13, 14, 15 | KSO-H-000007 | KSO Pak Sarto Jatisampurna RW 02, 03, 08, 10, 11, 12, 13, 14, 15 | FTTH | Cascade |  | Kota Bekasi | Jatisampurna | Jatisampurna | Open Area | 3920 |  |  | KSO | Pak Sarto | 0857-7979-6616 | - | 1. Reject | Reject |  |  |  | - | [42 empty] | KSO-H-000007 KSO Pak Sarto Jatisampurna RW 02, 03, 08, 10, 11, 12, 13, 14, 15 | [12 empty] | #REF! | #REF! | #REF!
23 | KSO Pak Edi Sector (HOS COKROAMINOTO Tangerang) RW 004-008 | KSO-H-000008 | KSO Pak Edi Sector (HOS COKROAMINOTO Tangerang) RW 004-008 | FTTH | Cascade |  | Kota Tangerang | Larangan | Kreo | Open Area | 1400 |  |  | KSO | Pak Edi | 0816-1616-840 | - | 1. Reject | Reject |  |  |  | - | Finalisasi PKS Dengan KSO | [5 empty] | BA Done |  | Pak Edi |  | Diurus Pak Edi | 2023-03-30 |  | Done |  |  |  |  | 1400 | 3party Pak Thandy | Done | Uploaded to Drive | KSO Pak Edi Sector (HOS COKROAMINOTO Tangerang) RW 004-008 | - | [18 empty] | KSO-H-000008 KSO Pak Edi Sector (HOS COKROAMINOTO Tangerang) RW 004-008 | [12 empty] | #REF! | #REF! | #REF!
24 | KSO Pak Andri (Pulogebang Rawakuning) | KSO-H-000009 | KSO Pak Andri (Pulogebang Rawakuning) | FTTH | Cascade |  | Jakarta Timur | Cakung | Pulo Gebang | Open Area | 2848 |  |  | KSO | Pak Andri | 0856-1367-905 | - | 1. Reject | Reject |  |  |  | - | Finalisasi PKS Dengan KSO |  |  | 2023-04-12 |  |  | BA Done |  | Pak Andri |  | Diurus Pak Andri | 2023-08-16 |  | Done |  |  |  |  | 2848 | 3party Pak Thandy | Done | Not Yet to Drive |  | - | [18 empty] | KSO-H-000009 KSO Pak Andri (Pulogebang Rawakuning) | [12 empty] | #REF! | #REF! | #REF!
25 | FTTX RW 008 Penggilingan, Kec. Cakung (Greenet) | NET-H-000016 | FTTX RW 008 Penggilingan, Kec. Cakung (Greenet) | FTTH | Reverse |  | Jakarta Timur | Cakung | Penggilingan | Open Area | 720 |  |  | KSO | Greenet |  | BMS | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | QC Done |  |  | 2023-05-03 |  |  | BA Done |  |  |  |  | 2023-05-05 |  | Done |  |  |  |  | 720 | 3party Pak Thandy | Done | Not Yet to Drive |  | - | [18 empty] | NET-H-000016 FTTX RW 008 Penggilingan, Kec. Cakung (Greenet) | 720 |  | 2023-05-03 | 0052/SVY-BMS/FMI/V/2023 | Done | [7 empty] | #REF! | #REF! | #REF!
26 | Perumahan Puri Kencana | NET-H-000017 | Perumahan Puri Kencana | FTTH | cascade |  | Jakarta Barat | Kembangan | Kembangan Selatan | Perumahan | 600 |  |  | Non-KSO | Nethome |  | - | 1. Reject | Reject |  |  |  | - |  |  |  | 2023-05-30 |  |  | On Progress |  |  |  |  | 2023-06-09 |  | Done |  |  |  |  | 600 | 3party Pak Thandy | Done | Uploaded to Drive | Perumahan Puri Kencana | - | [18 empty] | NET-H-000017 Perumahan Puri Kencana | [12 empty] | #REF! | #REF! | #REF!
27 | Serpong Paradise | NET-H-000018 | Serpong Paradise | FTTH | cascade |  | Kota Tangerang Selatan | Setu | Babakan | Perumahan | 5653 |  |  | Non-KSO | Nethome |  | - | 1. Reject | Reject |  |  |  | - |  |  |  | 2023-06-05 |  |  | On Progress |  |  |  |  | 2023-06-09 |  | Done |  |  |  |  | 5653 | 3party Pak Thandy | Done | Uploaded to Drive | Serpong Paradise | APD hanya mengkover FASUM | [18 empty] | NET-H-000018 Serpong Paradise | [12 empty] | #REF! | #REF! | #REF!
28 | Perumahan Baranangsiang Indah RW 5 | KSO-H-000010 | Perumahan Baranangsiang Indah RW 5 | FTTH | QODN |  | Kota Bogor | Bogor Timur | Katulampa | Perumahan | 612 |  |  | KSO | Pak Yuno | 0811-1109-911 | - | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | - |  |  |  | 2023-07-15 |  |  | NY Start Permit |  | Pak Yuno |  | Diurus Pak Yuno | 2023-07-15 |  | Done | [5 empty] | 3party Pak Thandy | Done | Uploaded to Drive | Perumahan Baranangsiang Indah RW 5 | - | [18 empty] | KSO-H-000010 Perumahan Baranangsiang Indah RW 5
29 | KSO Purwakarta (Kelurahan Kertamukti) | KSO-H-000011 | KSO Purwakarta (Kelurahan Kertamukti) | FTTH | Reverse |  | Kab. Purwakarta | Campaka | Kertamukti | Open Area | 1044 |  |  | KSO | Maxpro | Pak Anto 0857-1558-5955 | Sinergi | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | Penjadwalan QC |  |  | 2023-07-16 |  |  | BA Done |  | Pak Anto |  | Diurus Pak Anto | 2023-07-20 |  | Done |  |  |  |  | 1044 | 3party Pak Thandy | Done | Uploaded to Drive | KSO Purwakarta - Kelurahan Kertamukti | - |  |  | 13 | 71 | [14 empty] | KSO-H-000011 KSO Purwakarta (Kelurahan Kertamukti) | 1044 |  | 2023-10-25 | 0002/SVY-STSIQBAL/FMI/X/2023 | Done | [7 empty] | #REF! | #REF! | #REF!
30 | GP Plaza | NET-B-000001 | GP Plaza | FTTB | Reverse |  | Jakarta Pusat | Tanah Abang | Gelora | Apartement & Office | 338 | 0 |  | Non-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air |  | No Issue | On Air | - | [6 empty] | BA Done | [11 empty] | 338 | MSP | Done | Not Yet to Drive | Not Yet to Drive | New Langji | BTS Binus | [17 empty] | NET-B-000001 GP Plaza | 338 | [11 empty] | #REF! | #REF! | #REF!
31 | Intiland Tower | NET-B-000002 | Intiland Tower | FTTB | Reverse |  | Jakarta Pusat | Tanah Abang | Karet Tengsin | Office | 59 | 0 |  | Non-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air |  | No Issue | On Air | - | [6 empty] | BA Done | [12 empty] | MSP | Done | Not Yet to Drive | Not Yet to Drive | - | [18 empty] | NET-B-000002 Intiland Tower | 59 | [11 empty] | #REF! | #REF! | #REF!
32 | Menara BRIPENS | NET-B-000003 | Menara BRIPENS | FTTB | Reverse |  | Jakarta Selatan | Setiabudi | Karet Semanggi | Office | 9 | 0 |  | Non-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air |  | No Issue | On Air | - | [6 empty] | BA Done | [12 empty] | MSP | Done | Not Yet to Drive | Not Yet to Drive | New Langji | BTS Mustika Ratu | [17 empty] | NET-B-000003 Menara BRIPENS | 9 | [11 empty] | #REF! | #REF! | #REF!
33 | Indomobil Tower | NET-B-000004 | Indomobil Tower | FTTB | Reverse |  | Jakarta Selatan | Jatinegara | Bidara Cina | Office | 30 | 0 |  | Non-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | Pengajuan Kerjasama dengan gedung | No Issue | Sitac On Process | - | [6 empty] | On Progress | [12 empty] | Muchamad Rivai | Done |  | Not Yet to Drive | - | [18 empty] | NET-B-000004 Indomobil Tower | [12 empty] | #REF! | #REF! | #REF!
34 | FTTX Site Taman Rahayu, Bekasi | NET-H-000019 | FTTX Site Taman Rahayu, Bekasi | FTTH | Cascade |  | Kab. Bekasi | Setu | Taman Rahayu | Perumahan | 1049 |  |  | Non-KSO | Nethome | 0857-7979-6616 | Oemerta Karya | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | Terjadi FAT loss dibeberapa titik, sudah action repair beberapa kali tetapi tetap loss (infonya ada RT/RW Net diarea tsb) | [5 empty] | BA Done | [11 empty] | 1049 | Uli | Done | Uploaded to Drive | FTTX KSO PT Jangkar Site Taman Rahayu | - | BTS Seven Net | [17 empty] | NET-H-000019 FTTX Site Taman Rahayu, Bekasi | 976 | [11 empty] | #REF! | #REF! | #REF!
35 | FTTX Brigif 1 PIK Jayasakti | NET-H-000020 | FTTX Brigif 1 PIK Jayasakti | FTTH | Cascade |  | Jakarta Timur | Pasar Rebo | Pekayon | Perumahan | 323 |  |  | Non-KSO | Nethome |  | DSSI (Delia Solusi Sejahtera Indonesia) | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | Penjadwalan QC | [5 empty] | On Progress | [11 empty] | 323 | Uli | Done | Uploaded to Drive | FTTX Brigif 1 PIK Jayasakti | - | BTS Kencana Putri |  | 1 (Cascading) | 26 | NP 27, EP 1, TL 22 |  |  |  |  | 3650 | [8 empty] | NET-H-000020 FTTX Brigif 1 PIK Jayasakti | 323 | [11 empty] | #REF! | #REF! | #REF!
36 | FTTX Batalyon Koperasi Yonif 201 | NET-H-000021 | FTTX Batalyon Koperasi Yonif 201 | FTTH | cascade |  | Jakarta Timur | Pasar Rebo | Pekayon | Perumahan | 494 |  |  | Non-KSO | Nethome |  | - | 1. Reject | Reject |  |  |  | - | Belum dapat info terkait sitac & kerjasama | [5 empty] | On Progress | [11 empty] | 494 | Uli | Done | Uploaded to Drive | FTTX Batalyon Koperasi Yonif 201 | - | BTS Kencana Putri | [17 empty] | NET-H-000021 FTTX Batalyon Koperasi Yonif 201 | [12 empty] | #REF! | #REF! | #REF!
37 | FTTX Batalyon Koperasi Yonif 203 | NET-H-000022 | FTTX Batalyon Koperasi Yonif 203 | FTTH | cascade |  | Kota Tangerang | Jatiuwung | Gandasari | Perumahan | 544 |  |  | Non-KSO | Nethome |  | - | 1. Reject | Reject |  |  |  | - | Belum dapat info terkait sitac & kerjasama | [5 empty] | On Progress | [11 empty] | 544 | Uli | Done | Uploaded to Drive | FTTX Batalyon Koperasi Yonif 203 | - | BTS Veteran | [17 empty] | NET-H-000022 FTTX Batalyon Koperasi Yonif 203 | [12 empty] | #REF! | #REF! | #REF!
38 | Mensana Tower | NET-B-000005 | Mensana Tower | FTTB | Reverse |  | Kota Bekasi | Jatisampurna | Jatisampurna | Office | 24 | 0 |  | Non-KSO | Nethome |  | - | 5. Ready For Service | 8. Area On Air |  | No Issue | On Air | - | [6 empty] | On Progress |  |  |  |  | 2024-01-08 | Sofyan | Done | [5 empty] | Faisal | Done |  | Not Yet to Drive | - | BTS Komsen | [17 empty] | NET-B-000005 Mensana Tower | 24 | [11 empty] | #REF! | #REF! | #REF!
39 | KSO BTS Ramli RW 004 Kalibaru - Perluasan | KSO-H-000012 | KSO BTS Ramli RW 004 Kalibaru - Perluasan | FTTH | Reverse |  | Jakarta Utara | Cilincing | Kalibaru | Open Area | 298 | 25 | 25 | KSO | Pak Ramli | 0878-7819-3232 | MKU (Mitra Karsa Utama) | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | QC Done | [5 empty] | BA Done |  |  |  |  | 2023-10-21 | Alif & Nutsvy | [5 empty] | 298 | 3party Pak Thandy | Done | Uploaded to Drive | KSO BTS Ramli RW 004 Kalibaru (Perluasan) | - | BTS Ramli Kalibaru |  | 4 | 25 | NP 26, EP 2, TL 2 |  |  |  | 1673 | [9 empty] | KSO-H-000012 KSO BTS Ramli RW 004 Kalibaru - Perluasan | 298 |  |  |  | Done | [7 empty] | #REF! | #REF! | #REF!
40 | Apt. Grand Icon caman | NET-B-000006 | Apt. Grand Icon caman | FTTB | Reverse | TCF-17073 | Kota Bekasi | Pondok Gede | Jatibening | Apartement & Office | 592 | 0 |  | Non-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air |  | No Issue | On Air | - | [6 empty] | On Progress | [11 empty] | 596 | Faisal | Done |  | Not Yet to Drive | New Langji | BTS Jatibening Baru | [17 empty] | NET-B-000006 Apt. Grand Icon caman | 592 | [11 empty] | #REF! | #REF! | #REF!
41 | Gedung Tata Puri | NET-B-000007 | Gedung Tata Puri | FTTB | Reverse |  | Jakarta Pusat | Tanah Abang | Kebon Melati | Office |  | 0 |  | Non-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | Pengajuan Kerjasama dengan gedung | No Issue | Sitac On Process | - | [6 empty] | On Progress | [13 empty] | Done |  | Not Yet to Drive | - | [18 empty] | NET-B-000007 Gedung Tata Puri | [12 empty] | #REF! | #REF! | #REF!
42 | Menara Sudirman | NET-B-000008 | Menara Sudirman | FTTB | Reverse |  | Jakarta Selatan | Kebayoran Baru | Senayan | Office |  | 0 |  | Non-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | Pengajuan Kerjasama dengan gedung | No Issue | Sitac On Process | - | [6 empty] | On Progress | [13 empty] | Done |  | Not Yet to Drive | - | [18 empty] | NET-B-000008 Menara Sudirman | [12 empty] | #REF! | #REF! | #REF!
43 | Bojong Kulur RW 11 | KSO-H-000013 | Bojong Kulur RW 11 | FTTH | Reverse |  | Kab. Bogor | Gunung Putri | Bojong Kulur | Open Area | 347 |  |  | KSO | Belacom | 0877-7516-9193 | Belacom | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | QC Done | [5 empty] | BA Done | [11 empty] | 347 | Faisal | Done |  |  | - | BTS Komsen | [17 empty] | KSO-H-000013 Bojong Kulur RW 11 | 216 | [11 empty] | #REF! | #REF! | #REF!
44 | Mangga Dua Square | NET-B-000009 | Mangga Dua Square | FTTB | Reverse |  | Jakarta Utara | Pademangan | Ancol | Office |  | 26 |  | Non-KSO | Nethome |  | - | 5. Ready For Service | 8. Area On Air |  | No Issue | On Air | - | [6 empty] | BA Done | [11 empty] | 229 |  | Done | Uploaded to Drive | FTTB Mangga Dua Square | New Langji | BTS Tambora/BTS Golden |  |  | 26 | [14 empty] | NET-B-000009 Mangga Dua Square | 229 | [11 empty] | #REF! | #REF! | #REF!
45 | Kondomonium Juanda | NET-B-000010 | Kondomonium Juanda | FTTB | Reverse |  | Jakarta Pusat | Gambil | Kebon Kelapa | Apartement | 150 | 0 |  | Non-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | Pengajuan Kerjasama dengan gedung | No Issue | Sitac On Process | - | [6 empty] | BA Done | [13 empty] | Done |  | Not Yet to Drive | - | [18 empty] | NET-B-000010 Kondomonium Juanda | [12 empty] | #REF! | #REF! | #REF!
46 | Apartement City Resort | NET-B-000011 | Apartement City Resort | FTTB | Reverse |  | Jakarta Barat | Cengkareng | Cengkareng Timur | Apartement | 1028 | 78 |  | Non-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | Pengajuan Kerjasama dengan gedung | No Issue | Sitac On Process | - | Belum dapat info terkait sitac & kerjasama | [5 empty] | On Progress |  |  |  |  | 2023-12-22 | Aris Tegar | Done | 964 |  | 2024-11-29 | 2024-11-29 | 964 | Aris Setiawan | Done APD | Uploaded to Drive | FTTB Apartment City Resort | - | BTS Cengkareng |  | 22 | 78 |  |  | 1 | [6 empty] | 545 |  |  |  |  | NET-B-000011 Apartement City Resort | [12 empty] | #REF! | #REF! | #REF!
47 | Townhouse City Resort | NET-H-000023 | Townhouse City Resort | FTTH | cascade |  | Jakarta Barat | Cengkareng | Cengkareng Timur | Townhouse | 218 |  |  | Non-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | - | Belum dapat info terkait sitac & kerjasama | [5 empty] | On Progress | [7 empty] | 218 |  | 2024-11-29 | 2024-11-29 | 218 | Aris Setiawan | Done APD | Uploaded to Drive | APD NET-H-000023 Townhouse City Resort | - | BTS Plan Langji City Resort |  | 1 | 17 | [5 empty] | 1285 | [8 empty] | NET-H-000023 Townhouse City Resort | [12 empty] | #REF! | #REF! | #REF!
48 | Apartement Bintaro Icon | NET-B-000012 | FTTB Apartment Bintaro Icon | FTTB | Reverse |  | Tangerang Selatan | Pondok Aren | Bintaro | Apartement | 590 | 29 |  | Non-KSO | Nethome |  | - | 5. Ready For Service | 8. Area On Air |  | No Issue | On Air | - | [6 empty] | On Progress |  |  |  |  | 2023-12-21 | Ahmad Sofian | Done | 590 |  | 2024-07-12 | 2024-07-12 | 590 | Aris Setiawan | Done APD | Uploaded to Drive | FTTB Apartment Bintaro Icon | New Langji | BTS PDG Bintaro |  | 8 | 29 | [14 empty] | NET-B-000012 FTTB Apartment Bintaro Icon | 590 | [11 empty] | #REF! | #REF! | #REF!
49 | KSO Pak Sarto Kel. Jatirangga (Segment 1) | KSO-H-000014 | KSO Pak Sarto Kel. Jatirangga (Segment 1) | FTTH | cascade |  | Kota Bekasi | Jatisampurna | Jatirangga | Open Area | 249 |  |  | KSO | Pak Sarto | 0857-7979-6616 | Jangkar | 1. Reject | Reject |  |  |  | - | Belum ada progres dari KSO Jangkar | [5 empty] | On Progress | [9 empty] | 2023-12-28 | 2024-01-02 | 249 | Iyat | Done | Uploaded to Drive | APD FTTH KSO Pak Sarto (Kel. Jatirangga Segment 1) | - | BTS Jatiraden Sarto |  | 3 | 20 | 1 (EP = 48) |  |  |  |  | 2139 | [8 empty] | KSO-H-000014 KSO Pak Sarto Kel. Jatirangga (Segment 1) | [12 empty] | #REF! | #REF! | #REF!
50 | Apartement Riverdale Cikarang | NET-B-000013 | Apartement Riverdale Cikarang | FTTB | Reverse |  | Cikarang | Cikarang Barat | Kalijaya | Apartement | 794 | 0 |  | Non-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process | Pengajuan Kerjasama dengan gedung | No Issue |  | - | [6 empty] | On Progress |  |  |  |  | 30 Januari |  | Done |  |  | 2024-02-02 |  | 794 | Faisal | Done |  | Not Yet to Drive | - | [18 empty] | NET-B-000013 Apartement Riverdale Cikarang | [12 empty] | #REF! | #REF! | #REF!
51 | FTTX PARK SERPONG (LIPPO GROUP) | NET-H-000024 | FTTX PARK SERPONG (LIPPO GROUP) | FTTH | cascade |  | Kab. Tangerang | Legok | Medang | Perumahan | 27410 |  |  | Non-KSO | Nethome |  | - | 1. Reject | Reject |  |  |  | - | Proses pengajuan kerjasama dengan developer | [5 empty] | On Progress | [9 empty] | 2024-02-02 |  |  |  | Done Proyeksi RAB |  |  | - | PLAN NEW BTS KELAPA 2 |  | 587 | 2296 | [14 empty] | NET-H-000024 FTTX PARK SERPONG (LIPPO GROUP) | [12 empty] | #REF! | #REF! | #REF!
52 | Wisma Nugra Santana | NET-B-000014 | Wisma Nugra Santana | FTTB | Reverse |  | Jakarta Pusat | Tanah Abang | Karet Tengsin | Office | 143 | 0 |  | Non-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | Pengajuan Kerjasama dengan gedung | No Issue | Sitac On Process | - | [6 empty] | On Progress | [9 empty] | 2024-02-23 |  |  | Faisal | Done |  | Not Yet to Drive | - | [18 empty] | NET-B-000014 Wisma Nugra Santana | [12 empty] | #REF! | #REF! | #REF!
53 | Wisma PMI - JL.WIJAYA | KSO-B-000001 | Wisma PMI - JL.WIJAYA | FTTB | Reverse |  | Jakarta Selatan | Kebayoran Baru | Petogogan | Office | 21 | 0 |  | KSO | PAK YOGI | 0813-1052-3400 | - | 5. Ready For Service | 8. Area On Air |  | No Issue | On Air | - | [6 empty] | On Progress |  |  |  |  | 2024-02-03 |  | Done |  |  | 2024-02-16 |  | 21 | Faisal | Done |  | Not Yet to Drive | - | BTS Mampang Pondok Karya | [17 empty] | KSO-B-000001 Wisma PMI - JL.WIJAYA | 21 | [11 empty] | #REF! | #REF! | #REF!
54 | FTTX site Taruma Jaya | NET-H-000025 | FTTX SITE TARUMAJAYA | FTTH | Cascade |  | Kab. Bekasi | Tarumajaya | Setiamulya | Perumahan | 2194 | 150 |  | Non-KSO | Nethome |  | MKU (Mitra Karsa Utama) | 4. Electrical Work | 7. E2E Integration | Pelurusan Core kearah Plan Langji & Pencarian funnel cluster baru diarea sekitar BTS Sitetarumajaya oleh MKU didampingi oleh sitac FMI | No Issue |  | - | Banyak Area yg permitnya belum close didepan | [5 empty] | On Progress |  | Rino & Andi | [7 empty] | 2024-03-01 | 2024-03-04 |  | Uli | Done | Uploaded to Drive | FTTX Site Tarumajaya | - | Plan Bangun Langji |  | 21 | 150 | 262 (NP = 221) ( TL= 39) (EP=3) |  |  |  | 8275 |  | 3710 |  | 1150 | [5 empty] | NET-H-000025 FTTX SITE TARUMAJAYA | [12 empty] | #REF! | #REF! | #REF!
55 | FTTX Kelurahan Duri Kosambi Jakarta Barat | KSO-H-000015 | FTTH Duri Kosambi RW 01 & 07 | FTTH | QODN |  | Jakarta Barat | Cengkareng | Duri Kosambi | Open Area | 1875 | 235 |  | KSO | Pak Reno |  | - | 1. Reject | Reject |  | PKS KSO Belum Clear | Permit Issue | - | Proses skema kerjasama dengan KSO | [5 empty] | On Progress |  | Toro & Rino | [5 empty] | 2991 |  |  |  | 2991 | Uli | Waiting Survey |  | FTTH Duri Kosambi RW 01 & 07 | - |  | 7 | [16 empty] | KSO-H-000015 FTTH Duri Kosambi RW 01 & 07
56 | FTTX Bangun Reksa Indah 2 | NET-H-000026 | FTTH Bangun Reksa Indah 2 RW.06 | FTTH | Cascade |  | Kota Tangerang | Karang Tengah | Pondok Pucung | Perumahan | 615 | 41 |  | Non-KSO | Nethome |  | Oemerta Karya | 3. Civil Work | 6. Pole & ODN Instalation | progress penarikan & tanam tiang | No Issue |  | - |  | 2024-04-01 |  |  |  |  | On Progress |  | Toro | [7 empty] | 2024-03-05 | 2024-04-23 | 615 | Iyat | Done | Uploaded to Drive | FTTH Bagun Reksa Indah 2 RW.06 | - | BTS RADEN FATAH |  | 6 | 41 | NP (69), NP Galvanis (40), EP (1) |  |  |  |  | 5359 | [8 empty] | NET-H-000026 FTTH Bangun Reksa Indah 2 RW.06 | [12 empty] | #REF! | #REF! | #REF!
57 | FTTX RT 015 Griya Alam Sentosa | NET-H-000027 | Griya Alam Sentosa RT 15 | FTTH | cascade |  | Kab. Bogor | Cileungsi | Pasir Angin | Perumahan | 113 | 8 |  | Non-KSO | Nethome |  | DSSI (Delia Solusi Sejahtera Indonesia) | 1. Reject | Reject | Peluasan Area menajadi 1 area RW.08 |  |  | - | RW08 meminta untuk sekalian perluasan seluruh RW08 | [5 empty] | BA Done | [9 empty] | 2024-03-01 | 2024-03-01 | 113 | Uli | Done | Uploaded to Drive | FTTTX Griya Alam Sentosa RT.15 | - | BTS Sevennet |  | 1 | 8 | (EP = 3) (NP = 13) |  |  |  | 823 | [9 empty] | NET-H-000027 Griya Alam Sentosa RT 15 | [12 empty] | #REF! | #REF! | #REF!
58 | The Hive Tamansari | NET-B-000015 | The Hive Tamansari | FTTB | Reverse |  | Jakarta Timur | Jatinegara | Cipinang Cempendak | Apartement | 410 | 0 |  | Non-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | Pengajuan Kerjasama dengan gedung | No Issue | Sitac On Process | - | [6 empty] | On Progress |  | Rino | [11 empty] | Progress APD |  | Not Yet to Drive | - | [18 empty] | NET-B-000015 The Hive Tamansari | [12 empty] | #REF! | #REF! | #REF!
59 | FTTX RW011 Cawang | NET-H-000028 | FTTH RW 11 Kelurahan Cawang (RT 03, 05, 09) | FTTH | QODN |  | Jakarta Timur | Kramatjati | Cawang | Open Area | 150 | 14 | 14 | NON-KSO | Nethome |  | MKU (Mitra Karsa Utama) | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | Pada saat Team IKR ke lokasi untuk aktivasi client untuk beberapa FAT loss | 2024-04-01 |  |  |  |  | On Progress |  | Rino | Reguler |  |  |  |  | 182 |  | 2024-05-13 | 2024-05-13 | 182 | Aris Setiawan | Done APD | Uploaded to Drive | FTTH RW 11 Kelurahan Cawang (RT 03, 05, 09) |  | BTS Cawang |  | 1 | 14 | 17 | 17 | 2 |  | 1140 | 455 | [8 empty] | NET-H-000028 FTTH RW 11 Kelurahan Cawang (RT 03, 05, 09) | 182 | 2024-05-20 | 2024-05-20 | 0007/SVYSPL-KARSA/FMI/V/2024 | Done | [6 empty] | 2024-09-04
60 | FTTX RW06 Pulo Gadung | NET-H-000029 | FTTH RW.06 PULO GADUNG | FTTH | QODN |  | Jakarta Timur | Pulo Gadung | Pulo Gebang | Perumahan | 650 | 0 |  | Non-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | SPK Sitac Survey Done | No Issue | Sitac On Process | - |  | 2024-04-01 |  |  |  |  | NY Start Permit |  | Andi | [7 empty] | 2024-03-04 |  |  | Iyat | Done Pre-APD | Uploaded to Drive | FTTX RW.06 PULO GADUNG |  | Plan Bangun Langji | [17 empty] | NET-H-000029 FTTH RW.06 PULO GADUNG
61 | FTTX RW 008 Utan Kayu | NET-H-000030 | FTTH RW.08 UTAN KAYU UTARA | FTTH | QODN |  | Jakarta Timur | Matraman | Utan Kayu Utara | Open Area | 500 | 0 |  | Non-KSO | Nethome |  | MKU (Mitra Karsa Utama) | 1. Reject | Reject | Pihak lingkungan menolak | Pihak lingkungan menolak | Permit Issue | 0219/SPK-FMI/IV/24 |  | 2024-04-01 |  |  |  |  | On Progress |  | Andi | [7 empty] | 2024-03-04 |  |  | Iyat | Done Pre-APD | Uploaded to Drive | FTTX RW.08 UTAN KAYU UTARA |  | BTS IS Plaza | [17 empty] | NET-H-000030 FTTH RW.08 UTAN KAYU UTARA | 0
62 | FTTX RW 07 Jatiwaringin | NET-H-000031 | FTTX RW.07 JATIWARINGIN | FTTH | QODN |  | Kota Bekasi | Pondok Gede | Jatiwaringin | Open Area | 700 | 99 |  | Non-KSO | Nethome |  | MKU (Mitra Karsa Utama) | 1. Reject | Reject | Beririsan dengan Boundary FKI | Beririsan dengan Boundary FKI | Permit Issue | - |  | 2024-04-01 |  |  |  |  | On Progress |  | Andi | [5 empty] | 1539 |  | 2024-03-05 | 2024-05-21 | 1539 | Aris Setiawan | Done APD | Uploaded to Drive | APD |  | Plan Bangun Langji/BTS Jatibening Baru |  | 4 | 99 | 167 | 0 |  |  | 3070 | 6698 | [8 empty] | NET-H-000031 FTTX RW.07 JATIWARINGIN | 0
63 | FTTH Jl. Karyawan I & II RW.05 Kel. Karang Timur | NET-H-000032 | FTTH Jl. Karyawan I & II RW.05 Kel. Karang Timur | FTTH | cascade |  | Kota Tangerang | Karang Tengah | Karang Tengah | Open Area | 2400 | 0 |  | Non-KSO | Nethome |  | - | 1. Reject | Reject |  |  |  | - | [6 empty] | Cancel |  | Toro | [7 empty] | 2024-03-05 |  | 905 | Uli | Done Pre-APD | Uploaded to Drive | FTTH Jl. Karyawan I & II RW.05 Kel. Karang Timur |  | BTS Raden Fatah | [17 empty] | NET-H-000032 FTTH Jl. Karyawan I & II RW.05 Kel. Karang Timur | [12 empty] | #N/A | #N/A | #N/A
64 | FTTX RW.09 Menteng Dalam | NET-H-000033 | FTTH RW.09 Kelurahan Menteng Dalam | FTTH | QODN |  | Jakarta Selatan | Tebet | Menteng Dalam | Open Area | 240 | 18 |  | Non-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 4. APD Done | Persiapan Material | Terkait issue kompensasi penanaman tiang yg tinggi dikembalikan kembali ke team sitac FMI | High Price | - |  | 2024-04-01 |  |  |  |  | On Progress |  | Andi | [5 empty] | 240 |  | 2024-03-08 | 2024-05-14 | 240 | Aris Setiawan | Done APD | Uploaded to Drive | APD Revisi |  | BTS Mustika Ratu |  | 1 | 18 | 40 |  |  |  | 784 | 1529 | [8 empty] | NET-H-000033 FTTH RW.09 Kelurahan Menteng Dalam
65 | FTTX RW 06 ( RT 1 ) Jatibening Pondok Gede Bekasi | NET-H-000034 | FTTH RW.006 Kelurahan Jatibening Baru | FTTH | QODN |  | Kota Bekasi | Pondok Gede | Jatibening Baru | Perumahan | 220 | 15 |  | Non-KSO | Nethome |  | MKU (Mitra Karsa Utama) | 1. Reject | Reject | Sedang didiskusikan dengan pihak RW untuk start progress implementasi (05/09/2024) | rw meminta surat kerjasama secara tertulis kalo mau menempel di tiang exsisting lain | Permit Issue | - |  | 2024-04-01 |  |  |  |  | On Progress |  | Andi | [5 empty] | 262 |  | 2024-03-08 | 2024-03-20 | 241 | Aris Setiawan | Done APD | Uploaded to Drive | APD Revisi 2 |  | BTS Jatibening Baru | 2 | 1 | 15 | 37 | 0 |  | 2387 | 1233 | 946 | [8 empty] | NET-H-000034 FTTH RW.006 Kelurahan Jatibening Baru | 0
66 | FTTB The apartment Lotus Residence | NET-B-000016 | FTTB The apartment Lotus Residence | FTTB | Reverse |  | Kota Depok | Cilodong | Jatimulya | Apartemen | 256 | 16 |  | Non-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air |  | No Issue | On Air | - | [6 empty] | On Progress |  | Rino |  |  | 2024-03-21 | Aris Tegar | Done | 256 |  | 2024-06-27 | 2024-06-27 | 256 | Aris Setiawan | Done APD | Uploaded to Drive | FTTB Apartement Lotus Residence GDC | New Langji | BTS Kocen & BTS Tapos |  | 5 | 16 | 3 |  |  |  |  | 720 | [8 empty] | NET-B-000016 FTTB The apartment Lotus Residence | 256 | 2024-06-27 |  |  | Done | Rinjani | 2024-07-08 | 2024-07-08 | 959/SPLICE-RINJANI/FMI/VII/2024 | Done Splice |  |  | #REF! | #REF! | #REF!
67 | FTTX Wisma 2 & 3 Pasar Kemis | NET-H-000035 | FTTH - Perumahan Wisma 2 & 3 (RW.15) Pasar Kemis | FTTH | Cascade |  | Kabupaten Tangerang | Pasar Kemis | Kuta Jaya | Perumahan | 1625 | 108 |  | Non-KSO | Nethome |  | DSSI (Delia Solusi Sejahtera Indonesia) | 4. Electrical Work | 7. E2E Integration | Menunggu penarikan backbone sampai ke Langji | Menunggu hasil rekomtek PU / untuk penarikan backbone terhambat di PU dan terkena biaya 11.000 per meter (Estimasi yg terkena PU 3.000M) | Installation On Progress | - | Menunggu tiang 7m bulat | 2024-04-01 |  |  |  |  | On Progress |  | Toro | [7 empty] | 2024-03-13 | 2024-04-19 | 1625 | Uli | Done | Uploaded to Drive | FTTH - Perumahan Wisma 2 & 3 (RW.15) Pasar Kemis |  | Plan Bangun Langji |  | 15 | 108 | 166 |  |  |  |  | 2240 |  |  | 6220 | [5 empty] | NET-H-000035 FTTH - Perumahan Wisma 2 & 3 (RW.15) Pasar Kemis | [12 empty] | #REF! | #REF! | #REF!
68 | Apartemen Paragon Village | NET-B-000017 | FTTB Apartment Paragon Village | FTTB | Reverse |  | Kabupaten Tangerang | Curug | Binong | Apartemen | 1204 | 0 |  | Non-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | Pengajuan Kerjasama dengan gedung | No Issue | Sitac On Process | - | [6 empty] | On Progress |  | Bu FAhria |  |  | 2024-03-09 | Astika | Done | 1204 |  | 2024-09-18 | 2024-09-18 | 1204 | Aris Setiawan | Done APD | Uploaded to Drive | FTTB Apartment Paragon Village | Resurvey Opsi 2 | Plan Bangun Langji | [17 empty] | NET-B-000017 FTTB Apartment Paragon Village | 1204 | [11 empty] | #REF! | #REF! | #REF!
69 | FTTX Komp.Zeni RW03 | NET-H-000036 | FTTX RW.03 KOMP ZENI, RAWAJATI | FTTH | QODN |  | Jakarta Selatan | Pancoran | Rawajati | Perumahan | 370 | 24 |  | Non-KSO | Nethome |  | INHOUSE | 1. Reject | Reject | Beririsan dengan Boundary FKI | Beririsan dengan Boundary FKI | Permit Issue | - |  | 2024-04-01 |  |  |  |  | On Progress |  | zahrudin | [5 empty] | 370 |  | 2024-03-13 | 2024-05-15 | 370 | Aris Setiawan | Done APD | Uploaded to Drive | APD |  | BTS Cawang |  | 1 | 24 | 51 |  |  |  | 499 | 2345 | [8 empty] | NET-H-000036 FTTX RW.03 KOMP ZENI, RAWAJATI | 0
70 | FTTX Kelurahan Sindang Rasa | NET-H-000037 | FTTX KELURAHAN SINDANGRASA | FTTH | Cascade |  | Kota Bogor | Bogor Timur | Sindang Rasa | Open Area | 2817 | 201 |  | Non-KSO | Nethome |  | DSSI (Delia Solusi Sejahtera Indonesia) | 3. Civil Work | 6. Pole & ODN Instalation | Progres puling & tanam tiang 6m & 9m | No Issue | Installation On Progress | - | Menunggu Tiang 7 meter bulat 3inch | 2024-04-01 |  |  |  |  | On Progress |  | zahrudin | [7 empty] | 2024-03-14 | 2024-05-21 | 2817 | Uli | Done APD | Uploaded to Drive | FTTH KELURAHAN SINDANGRASA |  | Plan Bangun Langji |  | 7 | 201 | [14 empty] | NET-H-000037 FTTX KELURAHAN SINDANGRASA | [12 empty] | #N/A | #N/A | #N/A
71 | FTTX RW 09 Jatibening Baru | NET-H-000038 | FTTH RW.009 Kelurahan Jatibening Baru | FTTH | QODN |  | Kota Bekasi | Pondok Gede | Jatibening Baru | Perumahan | 800 | 36 |  | Non-KSO | Nethome |  | MKU (Mitra Karsa Utama) | 1. Reject | Reject | Beririsan dengan Boundary FKI | Beririsan dengan Boundary FKI | Permit Issue | - |  | 2024-04-01 |  |  |  |  | On Progress |  | Andi | [8 empty] | 2024-05-14 |  | Uli | Done | Uploaded to Drive | FTTH RW.009 Kelurahan Jatibening Baru (531 HP) |  | BTS Jatibening |  | 5 | 36 | 64 | 0 |  |  | 145 | 3375 | [8 empty] | NET-H-000038 FTTH RW.009 Kelurahan Jatibening Baru | 0
72 | Apartment The Mansion Jasmine | NET-B-000018 | Apartment The Mansion Jasmine | FTTB | Reverse |  | Jakarta Utara | Pademangan | Pademangan Timur | Apartemen | 2000 | 177 |  | KSO | Indospace |  | BMS | 5. Ready For Service | 8. Area On Air |  | No Issue | On Air | - | [6 empty] | On Progress |  | Pak Budi |  |  | 2024-05-21 | Nutsvy Ratsby | Done | 2204 |  | 2024-05-22 | 2024-05-22 | 2204 | Aris Setiawan | Done APD | Uploaded to Drive | FTTB Apartment The Mansion Jasmine | - | BTS Kemayoran |  | 46 | 177 | [14 empty] | NET-B-000018 Apartment The Mansion Jasmine | 2000 | 2024-06-18 | 2024-06-29 | 0104/SVY-BMS/FMI/VI/2024 | Done | Rinjani | 2024-07-08 | 2024-07-08 | 965/SPLICE-RINJANI/FMI/VII/2024 | Done Splice |  |  | #REF! | #REF! | #REF!
73 | Apartment MT.Haryono Residence | NET-B-000019 | Apartment MT.Haryono Residence | FTTB | Reverse |  | Jakarta Timur | Jatinegara | Cawang | Apartemen | 640 | 47 |  | Non-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air |  | No Issue | On Air | - | [6 empty] | On Progress |  | Fahriah/Darto |  |  | 2024-03-19 | Astika | Done | 640 |  | 2024-05-29 | 2024-05-29 | 640 | Aris Setiawan | Done APD | Uploaded to Drive | FTTB Apartment MT.Haryono Residence | New Langji | BTS Cawang |  | 12 | 47 | [14 empty] | NET-B-000019 Apartment MT.Haryono Residence | 640 | 2024-05-31 |  |  | Done | Rinjani | 2024-06-06 | 2024-06-12 | 824/SPLICE-RINJANI/FMI/VI/2024 | Done Splice |  |  | #REF! | #REF! | #REF!
74 | Taman Fasco | KSO-H-000016 | FTTH Taman Fasco | FTTH | QODN |  | Tangerang Selatan | Ciputat | Serua | Perumahan | 380 | 42 | 42 | KSO | DMC Tangsel | Pak Agi +62 856-7216-966 | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | Pihak DMC masih mencoba atur dengan Kelurahan | 2024-04-01 |  |  |  |  | On Progress |  | DMC Tangsel | Free 3 Bulan |  |  |  |  | 380 |  | 2024-10-02 | 2024-10-02 | 380 | Muchamad Rivai | Done | Uploaded to Drive | FTTH Taman Fasco |  | BTS Pamulang | 3 | 7 | 42 | 37 |  | 2 | 2445 |  | 390 | [8 empty] | KSO-H-000016 FTTH Taman Fasco | 332 | 2024-10-28 | - | - | Done | Rinjani | 2024-11-04 | 2024-11-04 | 1602/SPLICE-RINJANI/FMI/XI/2024 | Done Splice | 2024-11-08 | 2024-11-25
75 | Cendana Residence | KSO-H-000017 | Cendana Residence | FTTH | cascade |  | Tangerang Selatan | Pamulang | Pondok Benda | Perumahan | 750 | 0 |  | KSO | DMC Tangsel | Pak Agi +62 856-7216-966 | LISMA | 1. Reject | Reject | SPK Sitac Survey Done |  |  | - | Pihak DMC masih mencoba atur dengan Kelurahan | 2024-04-01 |  |  |  |  | On Progress | [35 empty] | KSO-H-000017 Cendana Residence | [12 empty] | #REF! | #REF! | #REF!
76 | FTTX RW 008 Pasir Angin/Griya Alam Sentosa | NET-H-000039 | Perumahan Griya Alam Sentosa RW08 | FTTH | Cascade |  | Kab. Bogor | Cileungsi | Pasir Angin | Perumahan | 2651 | 180 |  | Non-KSO | Nethome |  | DSSI (Delia Solusi Sejahtera Indonesia) | 3. Civil Work | 6. Pole & ODN Instalation | Waiting Langji | Waiting Langji | Installation On Progress | - |  | 2024-04-01 |  |  |  |  | On Progress | [7 empty] | 2651 |  | 2024-05-28 | 2024-05-30 | 2651 | Aris Setiawan | Done APD | Uploaded to Drive | FTTH Perumahan Griya Alam Sentosa RW08 ( 2651 HP) |  | Plan BTS Langji |  | 6 | 180 | 282 |  |  |  | 4139 | 18936 | [8 empty] | NET-H-000039 Perumahan Griya Alam Sentosa RW08 | 1570 | 2024-05-30 | 2024-05-30 | 0006/SVYSPL-DSSI/FMI/V/2024 | On Going Project | [7 empty] | #REF! | #REF! | #REF!
77 | FTTX JL.Sandong RW05 | NET-H-000040 | FTTH - RW.05 Jl. Sandong - Kel. Pondok Pucung | FTTH | QODN |  | Kota Tangerang | Karang Tengah | Pondok Pucung | Open Area | 700 | 35 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 4. Electrical Work | 7. E2E Integration | Untuk team implementasi ODN diusahakan untuk pekerjaan dimalam hari guna menghindari pemberhentian pekerjaan oleh pihak lingkungan setempat | Untuk progress terkait implementasi diharuskan dimalam hari untuk menghindari pemberhentian pekerjaan oleh pihak lingkungan setempat | Implementation Issue | 0487/SPK-FMI/VII/24 | [6 empty] | On Progress |  | Toro | [5 empty] | 279 |  |  | 2024-07-30 | 279 | Uli | APD Done | Uploaded to Drive | FTTH - RW.05 Jl. Sandong - Kel. Pondok Pucung |  | Plan BTS Langji | 2 | 5 | 35 | 17 | 17 |  |  |  |  | 550 | [7 empty] | NET-H-000040 FTTH - RW.05 Jl. Sandong - Kel. Pondok Pucung | 0 | 2024-07-30 | 2024-07-30 | 0001/SVYSPL-SPT-FMI/VII/2024 | Done | SPT | 2024-07-30 | 2024-07-30 | 0001/SVYSPL-SPT-FMI/VII/2024 | Done Splice | 2024-09-30 | On Progress
78 | FTTX Jl. Sunan Giri RW04 | NET-H-000041 | FTTH - RW.04 Jl. Sunan Giri - Kel. Pondok Pucung | FTTH | QODN |  | Kota Tangerang | Karang Tengah | Pondok Pucung | Open Area | 600 | 24 | 2 | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 4. Electrical Work | 7. E2E Integration | Untuk team implementasi ODN diusahakan untuk pekerjaan dimalam hari guna menghindari pemberhentian pekerjaan oleh pihak lingkungan setempat | Untuk progress terkait implementasi diharuskan dimalam hari untuk menghindari pemberhentian pekerjaan oleh pihak lingkungan setempat | Implementation Issue | 0486/SPK-FMI/VII/24 | [6 empty] | On Progress |  | Toro | [5 empty] | 203 |  |  | 2024-07-30 | 187 | Uli | APD Done | Uploaded to Drive | FTTH - RW.04 Jl. Sunan Giri - Kel. Pondok Pucung |  | Plan BTS Langji | 1 | 3 | 24 | 12 | 12 | [12 empty] | NET-H-000041 FTTH - RW.04 Jl. Sunan Giri - Kel. Pondok Pucung | 16 | 2024-07-30 | 2024-07-30 | 0002/SVYSPL-SPT-FMI/VII/2024 | Done | SPT | 2024-07-30 | 2024-07-30 | 0001/SVYSPL-SPT-FMI/VII/2024 | Done Splice | 2024-09-30 | On Progress
79 | FTTH RW07Jatibening Baru | NET-H-000042 | FTTH RW.007 Kelurahan Jatibening Baru | FTTH | QODN |  | Kota Bekasi | Pondok Gede | Jatibening Baru | Open Area | 400 | 0 |  | NON-KSO | Nethome |  | TIT (Tauco Integra Telekomunikasi) | 1. Reject | Reject |  | No Issue | Vendor Issue | 0554/SPK-FMI/VIII/24 | New Area | [5 empty] | On Progress |  | Andi | [33 empty] | NET-H-000042 FTTH RW.007 Kelurahan Jatibening Baru | 0
80 | FTTX RW03 Telaga Asih | NET-H-000043 | FTTH RW.003 Kelurahan Telaga Asih | FTTH | QODN |  | Kab. Bekasi | Cikarang Barat | Telaga Asih | Open Area | 1000 | 0 |  | NON-KSO | Nethome |  | TIT (Tauco Integra Telekomunikasi) | 1. Reject | Reject | Jarak > 8km ke BTS terdekat & ada Plan peluasan diarea sekitar Kelurahan Telaga Asih dan Plan Langji/BTS diarea tsb | Menunggu hasil survey Plan titik POP | Distance Issue | 0524/SPK-FMI/VII/24 | New Area | [5 empty] | On Progress |  | Andi | [5 empty] | 531 | [27 empty] | NET-H-000043 FTTH RW.003 Kelurahan Telaga Asih | 0
81 | FTTX RW02 Telaga Asih | NET-H-000044 | FTTH RW.002 Kelurahan Telaga Asih | FTTH | QODN |  | Kab. Bekasi | Cikarang Barat | Telaga Asih | Open Area | 600 | 0 |  | NON-KSO | Nethome |  | TIT (Tauco Integra Telekomunikasi) | 1. Reject | Reject | Jarak > 8km ke BTS terdekat & ada Plan peluasan diarea sekitar Kelurahan Telaga Asih dan Plan Langji/BTS diarea tsb | Menunggu hasil survey Plan titik POP | Distance Issue | 0523/SPK-FMI/VII/24 | New Area | [5 empty] | On Progress |  | Andi | [5 empty] | 262 | [27 empty] | NET-H-000044 FTTH RW.002 Kelurahan Telaga Asih | 0
82 | FTTX RW 07 & RW25 Desa Cicadas | NET-H-000045 | FTTH RW 07 & 25 Kelurahan Cicadas | FTTH | QODN |  | Kab. Bogor | Gunung Putri | Cicadas | Open Area | 2100 | 0 |  | NON-KSO | Nethome |  | DSSI (Delia Solusi Sejahtera Indonesia) | 1. Reject | Reject | SPK Sitac Survey Done | No Issue | Permit Issue | - | [6 empty] | On Progress |  | Rino | [33 empty] | NET-H-000045 FTTH RW 07 & 25 Kelurahan Cicadas
83 | FTTX RW 04 Desa Cicadas | NET-H-000046 | FTTH RW 04 Kelurahan Cicadas | FTTH | QODN |  | Kab. Bogor | Gunung Putri | Cicadas | Open Area | 300 | 0 |  | NON-KSO | Nethome |  | DSSI (Delia Solusi Sejahtera Indonesia) | 1. Reject | Reject | Review Strand (Revisi) | Perijinan dibatalkan RW karena terlalu lama tidak ada progres construction sehingga sudah masuk provider lainnya | Permit Issue | - | [6 empty] | On Progress |  | Rino | [33 empty] | NET-H-000046 FTTH RW 04 Kelurahan Cicadas
84 | FTTX RW013 Cipinang Muara | NET-H-000047 | FTTH RW 13 Kelurahan Cipinang Muara | FTTH | QODN |  | Jakarta Timur | Jatinegara | Cipinang Muara | Open Area | 800 | 0 |  | NON-KSO | Nethome |  | TIT (Tauco Integra Telekomunikasi) | 1. Reject | Reject |  | Perijinan dibatalkan RW karena terlalu lama tidak ada progres construction sehingga sudah masuk provider lainnya | Vendor Issue | 0555/SPK-FMI/VIII/24 | New Area | [5 empty] | On Progress |  | Andi | [33 empty] | NET-H-000047 FTTH RW 13 Kelurahan Cipinang Muara | 0
85 | FTTB Saladdin Mansion Apartment | NET-B-000020 | FTTB Saladdin Mansion Apartment | FTTB | Reverse |  | Kota Depok | Pancoran Mas | Depok | Apartement | 1242 | 90 |  | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air |  | No Issue | On Air | - | [6 empty] | On Progress |  | Rino |  |  | 2024-05-08 | Aris Tegar | Done | 1242 |  | 2024-05-08 | 2024-05-08 | 1242 | Aris Setiawan | Done APD | Uploaded to Drive | FTTB Saladdin Mansion Apartment | New Langji | BTS Graha Sentosa |  | 23 | 90 | 2 | [5 empty] | 700 | [7 empty] | NET-B-000020 FTTB Saladdin Mansion Apartment | 1242 | 2024-07-16 |  |  | On Going | [7 empty] | #N/A | #N/A | #N/A
86 | FTTH RW 02 Kelurahan Jatirahayu | NET-H-000048 | FTTH RW 02 Kelurahan Jatirahayu | FTTH | QODN |  | Kota Bekasi | Pondok Melati | Jatirahayu | Open Area | 350 | 24 |  | NON-KSO | Nethome |  | DSSI (Delia Solusi Sejahtera Indonesia) | 1. Reject | Reject | Persiapan Material & Konfrim ke pihak RW setempat untuk memulai implementasi | No Issue | Waiting Implementation | - | [6 empty] | On Progress |  | Rino | [5 empty] | 350 |  | 2024-09-09 | 2024-09-09 | 350 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH Jatirahayu RW 02 |  | BTS Pondok Gede | 3 | 5 | 24 | 43 |  |  | 2107 |  | 830 | [8 empty] | NET-H-000048 FTTH RW 02 Kelurahan Jatirahayu
87 | FTTH TAMAN CIKUNIR INDAH (RW.011 Kel. Jakamulya) | NET-H-000049 | FTTH TAMAN CIKUNIR INDAH (RW.011 Kel. Jakamulya) | FTTH | QODN |  | Kota Bekasi | Bekasi Selatan | Jakamulya | Perumahan | 500 | 77 |  | NON-KSO | Nethome |  | - | 1. Reject | Reject | RW sudah deal dengan Biznet kompensasi 1jt per tiang" dengan "RW sudah deal dengan Biznet kompensasi 1jt per tiang | High Price Issue | High Price | 0485/SPK-FMI/VII/24 | New Area | [5 empty] | On Progress |  | Andi | [5 empty] | 591 |  | 2024-07-26 | 2024-07-29 | 591 | Aris Setiawan | Done APD | Uploaded to Drive | FTTH TAMAN CIKUNIR INDAH (RW.011 Kel. Jakamulya) | Menunggu Lokasi Plan Langji Untuk bisa Drawing BB dan Feeder | Plan New Langji | 3 | 3 | 77 | 92 | 0 |  | 5947 | [10 empty] | NET-H-000049 FTTH TAMAN CIKUNIR INDAH (RW.011 Kel. Jakamulya) | 0
88 | FTTX RW09 Jatikramat | NET-H-000050 | FTTH RW 09 KELURAHAN JATI KRAMAT | FTTH | QODN |  | Kota Bekasi | Jati Asih | Jati Kramat | Open Area | 800 | 60 | 60 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | New Area | [5 empty] | BA Done |  | Andi | Free 3 Bulan |  |  |  |  | 478 |  | 2024-08-01 | 2024-08-01 | 478 | Muchamad Rivai | Done APD | Uploaded to Drive | FTTH RW 09 KELURAHAN JATI KRAMAT |  | BTS Jatibening Baru | 3 | 10 | 60 | 68 | 0 |  | 5210 |  | 1325 | [8 empty] | NET-H-000050 FTTH RW 09 KELURAHAN JATI KRAMAT | 478 | 2024-08-19 | 2024-08-20 | 0001/SVY-MSP/FMI/VIII/2024 | Done | Belacom | 2024-08-27 | 2024-08-27 | 343/SPLICE-BELACOM/FMI/VIII/2024 | Done Splice | 2024-09-04 | 2024-09-04
89 | FTTX RW04 Sumur Batu | NET-H-000051 | FTTH RW 04 KELURAHAN SUMUR BATU | FTTH | QODN |  | Kota Bekasi | Bantar Gebang | Sumur Batu | Open Area | 500 | 68 |  | NON-KSO | Nethome |  | DSSI (Delia Solusi Sejahtera Indonesia) | 3. Civil Work | 6. Pole & ODN Instalation | Progress Civil & Pemasangan Tiang | No Issue | Installation On Progress | - | [6 empty] | On Progress |  | Zahrudin | [5 empty] | 902 |  | 2024-09-12 | 2024-09-12 | 902 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH QODN RW 04 KELURAHAN SUMUR BATU |  | BTS Setu | 5 | 12 | 68 | 154 |  |  | 7585 |  | 1325 |  | 1625 | [6 empty] | NET-H-000051 FTTH RW 04 KELURAHAN SUMUR BATU | 0 | 2024-09-12 | 2024-09-12 | 0009/SVYSPL-DSSI/FMI/IX/2024 | On Progress
90 | FTTX RW02 Semper Timur | NET-H-000052 | FTTH Jl. Kebantenan IV RW.02 KEL. SEMPER TIMUR | FTTH | QODN |  | Jakarta Utara | Cilincing | Semper Timur | Open Area | 400 | 23 | 23 | NON-KSO | Nethome |  | TIT (Tauco Integra Telekomunikasi) | 5. Ready For Service | 8. Area On Air | Splice Done Waiting Pulling Cable DW (Progress harus dilakukan dimalam hari) | Untuk progress terkait implementasi diharuskan dimalam hari dikarenakan ada acara 17 agustusan, & untuk selanjutnya progress harus dilakukan dimalam hari | On Air | 0498/SPK-FMI/VII/24 | New Area | [5 empty] | On Progress |  | Toro |  |  | 2024-07-27 |  |  | 181 |  | 2024-07-27 | 2024-07-30 | 181 | Aris Setiawan | Done APD | Uploaded to Drive | FTTH Jl. Kebantenan IV RW.02 KEL. SEMPER TIMUR |  | BTS Ramli Kalibaru | 1 | 1 | 23 | 16 | 16 |  | 1062 |  | 20 | 210 | [7 empty] | NET-H-000052 FTTH Jl. Kebantenan IV RW.02 KEL. SEMPER TIMUR | 181 | 2024-07-30 | 2024-07-30 | 0002/SVYSPL-TIT-FMI/VII/2024 | Done | Belacom | 2024-08-28 | 2024-08-28 | 345/SPLICE-BELACOM/FMI/VIII/2024 | Done Splice | 2024-09-03 | On Progress
91 | FTTX RW04 Semper Timur | NET-H-000053 | FTTH Jl. Kebantenan IV RW.04 KEL. SEMPER TIMUR | FTTH | QODN |  | Jakarta Utara | Cilincing | Semper Timur | Open Area | 600 | 41 |  | NON-KSO | Nethome |  | TIT (Tauco Integra Telekomunikasi) | 1. Reject | Reject | persiapan material & homebase | No Issue | Installation On Progress | 0497/SPK-FMI/VII/24 | New Area | [5 empty] | On Progress |  | Toro |  |  | 2024-07-27 |  |  | 318 |  | 2024-07-30 | 2024-07-30 | 318 | Aris Setiawan | Done APD | Uploaded to Drive | FTTH Jl. Kebantenan IV RW.04 KEL. SEMPER TIMUR |  | BTS Ramli Kalibaru | 3 | 2 | 41 | 34 | 5 |  | 2189 |  | 40 | 690 | [7 empty] | NET-H-000053 FTTH Jl. Kebantenan IV RW.04 KEL. SEMPER TIMUR | 0 | 2024-07-30
92 | FTTH Jl. Kebantenan V RW.06 KEL. SEMPER TIMUR | NET-H-000054 | FTTH Jl. Kebantenan V RW.06 KEL. SEMPER TIMUR | FTTH | QODN |  | Jakarta Utara | Cilincing | Semper Timut | Open Area | 400 | 0 |  | NON-KSO | Nethome |  | - | 1. Reject | Reject | RW membatalkan | Permit Issue By RW | Permit Issue | - | New Area | [5 empty] | On Progress |  | Toro | [33 empty] | NET-H-000054 FTTH Jl. Kebantenan V RW.06 KEL. SEMPER TIMUR | 0
93 | FTTX RW01 Kemiri Muka | NET-H-000055 | FTTH RW.001 KELURAHAN KEMIRI MUKA | FTTH | QODN |  | Depok | Beji | Kemiri Muka | Open Area | 800 | 44 | 44 | NON-KSO | Nethome |  | FIB (Fajar Indonesia Berdikari) | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | 0518/SPK-FMI/VII/24 | New Area | [5 empty] | On Progress |  | Andi | Free 3 Bulan |  | 2024-08-23 | FIB |  | 345 |  |  | 2024-08-26 | 345 | Muchamad Rivai | Done APD | Uploaded to Drive | FTTH RW.001 KELURAHAN KEMIRI MUKA |  | BTS Apartment Saladdin Mansion | 4 | 8 | 44 | 57 |  |  | 2626 |  | 780 | [8 empty] | NET-H-000055 FTTH RW.001 KELURAHAN KEMIRI MUKA | 393 | 2024-08-26 | 2024-08-26 | 0003/SVY-FIB/FMI/VIII/2024 | Done | Rinjani | 2024-10-26 | 2024-10-26 | 1557/SPLICE-RINJANI/FMI/X/2024 | Done Splice | 2024-11-15 | 2024-12-09
94 | FTTX RW018 Kemiri Muka | NET-H-000056 | FTTH RW.018 KELURAHAN KEMIRI MUKA | FTTH | QODN |  | Depok | Beji | Kemiri Muka | Open Area | 500 | 38 | 38 | NON-KSO | Nethome |  | FIB (Fajar Indonesia Berdikari) | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | 0516/SPK-FMI/VII/24 | New Area | [5 empty] | On Progress |  | Andi | Free 3 Bulan |  | 2024-08-16 | FIB |  | 301 |  |  | 2024-08-20 | 301 | Muchamad Rivai | Done APD | Uploaded to Drive | FTTH RW.018 KELURAHAN KEMIRI MUKA |  | BTS Apartment Saladdin Mansion | 5 | 8 | 38 | 41 |  |  | 2015 |  | 755 | [8 empty] | NET-H-000056 FTTH RW.018 KELURAHAN KEMIRI MUKA | 345 | 2024-08-20 | 2024-08-20 | 0001/SVY-FIB/FMI/VIII/2024 | Done | Rinjani | 2024-10-23 | 2024-10-23 | 1529/SPLICE-RINJANI/FMI/X/2024 | Done Splice | 2024-11-30 | 2024-12-10
95 | FTTX RW07 Johar Baru | NET-H-000057 | FTTH RW.007 KELURAHAN JOHAR BARU | FTTH | QODN |  | Jakarta Pusat | Johar Baru | Johar Baru | Open Area | 800 |  |  | NON-KSO | Nethome |  | - | 1. Reject | Reject | Belum ada info lanjut dari RW | Permit Issue By RW | Permit Issue | - | New Area | [5 empty] | On Progress |  | Andi | [33 empty] | NET-H-000057 FTTH RW.007 KELURAHAN JOHAR BARU | 0
96 | FTTX RW012 Kemiri Muka | NET-H-000058 | FTTH RW.012 KELURAHAN TANAH TINGGI | FTTH | QODN |  | Jakarta Pusat | Tanah Tinggi | Tanah Tinggi | Open Area | 400 |  |  | NON-KSO | Nethome |  | - | 1. Reject | Reject | Belum ada info lanjut dari RW | Permit Issue By RW | Permit Issue | - | New Area | [5 empty] | On Progress |  | Andi | [33 empty] | NET-H-000058 FTTH RW.012 KELURAHAN TANAH TINGGI | 0
97 | FTTB Apartment The Brooklyn | NET-B-000021 | FTTB Apartment The Brooklyn | FTTB | Reverse |  | Kota Tangerang | Serpong Utara | Pakualam | Apartment | 914 | 64 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | Pengajuan Kerjasama dengan gedung | No Issue | Sitac On Process | - | [6 empty] | On Progress | [7 empty] | 914 |  | 2024-06-19 | 2024-06-19 | 914 | Aris Setiawan | Done APD | Uploaded to Drive | FTTB Apartment The Brooklyn | - | Plan Wireless/Microwave |  | 16 | 64 | [14 empty] | NET-B-000021 FTTB Apartment The Brooklyn | 914 | [11 empty] | #REF! | #REF! | #REF!
98 | FTTH Perumahan Griya Inti Sentosa | NET-H-000059 | FTTH Perumahan Griya Inti Sentosa | FTTH | Cascade |  | Jakarta Utara | Tanjung Priok | Sunter Agung | Perumahan | 613 |  |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue |  | - | [6 empty] | On Progress | [7 empty] | 613 |  | 2024-06-19 | 2024-06-19 | 613 | Aris Setiawan | Done APD | Uploaded to Drive | FTTH Perumahan Griya Inti Sentosa |  | Plan Langji Baru/BTS Kemayoran |  | 15 | 54 |  |  |  |  | 4330 | 5150 | 309 | [7 empty] | NET-H-000059 FTTH Perumahan Griya Inti Sentosa | 613 | [11 empty] | #REF! | #REF! | #REF!
99 | FTTH Grahayana Homes Site Karawang by PT CITANUSA | NET-H-000060 | FTTH Grahayana Homes Site Karawang by PT CITANUSA | FTTH | Reverse |  | Karawang | Karawang Barat | Adiarsa Barat | Perumahan | 356 |  |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue |  | - | [6 empty] | On Progress |  | Izul Marketing | [5 empty] | 356 |  | 2024-06-06 | 2024-06-06 | 356 | Aris Setiawan | Done APD | Uploaded to Drive | FTTH Grahayana Homes Site Karawang by PT CITANUSA |  | BTS Karawang Pamitran |  | 8 | 20 |  |  |  |  | 161 | 1727 | [8 empty] | NET-H-000060 FTTH Grahayana Homes Site Karawang by PT CITANUSA | 356 | [11 empty] | #REF! | #REF! | #REF!
100 | FTTX RW08 Kemiri Muka | NET-H-000061 | FTTH RW.008 KELURAHAN KEMIRI MUKA | FTTH | QODN |  | Depok | Beji | Kemiri Muka | Open Area | 400 | 31 | 31 | NON-KSO | Nethome |  | FIB (Fajar Indonesia Berdikari) | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | 0517/SPK-FMI/VII/24 | New Area | [5 empty] | On Progress |  | Andi | Free 3 Bulan |  | 2024-08-21 | FIB |  | 250 |  |  | 2024-08-23 | 244 | Muchamad Rivai | Done APD | Uploaded to Drive | FTTH RW.008 KELURAHAN KEMIRI MUKA |  | BTS Apartment Saladdin Mansion | 2 | 5 | 31 | 28 |  |  | 1512 |  | 520 | [8 empty] | NET-H-000061 FTTH RW.008 KELURAHAN KEMIRI MUKA | 244 | 2024-08-24 | 2024-08-24 | 0002/SVY-FIB/FMI/VIII/2024 | Done | Rinjani | 2024-10-23 | 2024-10-23 | 1530/SPLICE-RINJANI/FMI/X/2024 | Done Splice | 2024-11-11 | 2024-11-14
101 | FTTB Rumah Susun Harum Tebet | NET-B-000022 | FTTB Rumah Susun Harum Tebet | FTTB | Reverse |  | Jakarta Selatan | Tebet | Tebet Bara | Rumah Susun | 320 | 24 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | Pengajuan Kerjasama dengan gedung | No Issue | Sitac On Process | - | [6 empty] | On Progress |  | Rino |  |  | 2024-06-21 | Wildan Aulia | Done | 320 |  | 2024-07-02 | 2024-07-02 | 320 | Aris Setiawan | Done APD | Uploaded to Drive | FTTB Rumah Susun Harum Tebet | - | BTS Soepomo |  | 8 | 24 | 1 | [5 empty] | 140 | [7 empty] | NET-B-000022 FTTB Rumah Susun Harum Tebet | 320 | [11 empty] | #REF! | #REF! | #REF!
102 | FTTH Kelurahan Baktijaya RW.14 (Protelindo Sky) | NET-H-000062 | FTTH Kelurahan Baktijaya RT.03 RW.14 (Protelindo Sky) | FTTH | Cascade |  | Depok | Sukmajaya | Baktijaya | Perumahan | 119 | 8 | 8 | NON-KSO | Nethome |  | Oemerta Karya | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | [6 empty] | On Progress |  | Zahrudin | [8 empty] | 2024-07-02 | 119 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH Baktijaya RW 14 |  | BTS Langji Depok |  | 2 | 8 | 11 |  |  | - |  | 580 | [8 empty] | NET-H-000062 FTTH Kelurahan Baktijaya RT.03 RW.14 (Protelindo Sky) | 119 | [10 empty] | 2024-07-22 | #REF! | #REF! | #REF!
103 | FTTH Jatirasa RW.01 | NET-H-000063 | FTTH Jatirasa RW.01 | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatirasa | Open Area | 326 | 0 |  | NON-KSO | Nethome |  | INHOUSE | 1. Reject | Reject | - | High Price Issue | High Price | - | New Area | [5 empty] | On Progress |  | Rino | [33 empty] | NET-H-000063 FTTH Jatirasa RW.01 | 0
104 | FTTH RW.007 KELURAHAN JATIMAKMUR | NET-H-000064 | FTTH RW.007 KELURAHAN JATIMAKMUR | FTTH | QODN |  | Kota Bekasi | Pondok Gede | Jatimakmur | Open Area | 800 | 67 |  | NON-KSO | Nethome |  | INHOUSE | 1. Reject | Reject | - | High Price Issue | High Price | - | New Area | [5 empty] | On Progress |  | Andi | [5 empty] | 531 |  |  | 2024-08-05 | 531 | Uli | APD Done | Uploaded to Drive | FTTH RW.007 Kelurahan Jatimakmur |  | BTS Jatibening Baru | 3 | 10 | 67 | 44 | 0 |  | 5269 | [10 empty] | NET-H-000064 FTTH RW.007 KELURAHAN JATIMAKMUR | 0
105 | FTTH RW.009 KELURAHAN UTAN KAYU UTARA | NET-H-000065 | FTTH RW.009 KELURAHAN UTAN KAYU UTARA | FTTH | QODN |  | Jakarta Timur | Matraman | Utan Kayu Utara | Open Area | 450 | 0 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | Assign Vendor | No Issue | Assign Vendor | - | New Area | [5 empty] | NY Start Permit |  | Andi | [33 empty] | NET-H-000065 FTTH RW.009 KELURAHAN UTAN KAYU UTARA | 0
106 | FTTH Kelurahan Tridaya Sakti RT.02 RW.01 | KSO-H-000018 | FTTH Kelurahan Tridaya Sakti RT.02 RW.01 | FTTH | QODN |  | Kabupaten Bekasi | Tambun Selatan | Tridaya Sakti | Open Area | 333 | 42 | 42 | KSO | Pak Rahmat |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | New Area | [5 empty] | On Progress |  | Pak Rahmat | [5 empty] | 333 |  | 2024-07-07 | 2024-07-31 | 333 | Aris Setiawan | Done APD | Uploaded to Drive | FTTH Kelurahan Tridaya Sakti RT.02 RW.01 | New Langji | New Langji/BTS Tambun | 2 | 2 | 42 | 26 | 9 |  | 2836 |  |  |  |  | 415 | [5 empty] | KSO-H-000018 FTTH Kelurahan Tridaya Sakti RT.02 RW.01 | 333 | 2024-08-07 | 2024-08-12 | 0001/SVY-RAHMAT/FMI/VIII/2024 | Done | Belacom | 2024-09-23 | 2024-09-23 | 391/SPLICE-BELACOM/FMI/IX/2024 | Done Splice | 2024-10-09 | 2024-10-15
107 | ProSky FTTH Pakulonan Serpong RW.01 | NET-H-000066 | ProSky FTTH Pakulonan Serpong RW.01 | FTTH | QODN |  | Tangerang Selatan | Serpong Utara | Pakulonan | Open Area | 112 | 14 | 14 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | [6 empty] | On Progress |  | Toro | Free 3 Bulan |  |  |  |  | 112 |  |  | 2024-07-08 | 112 | Uli | APD Done | Uploaded to Drive | ABD |  | BTS Serpong | 1 | 2 | 14 | 8 | 8 |  |  |  | 300 | [8 empty] | NET-H-000066 ProSky FTTH Pakulonan Serpong RW.01 | 112 | 2024-07-09 | 2024-07-12 | - | Done | Rinjani | 2024-07-11 | 2024-07-11 | 988/SPLICE-RINJANI/FMI/VII/2024 | Done Splice | 2024-07-19 | 2024-07-23
108 | Kelurahan Serpong RW 02 | NET-H-000067 | FTTH Kelurahan Serpong RW 02 | FTTH | QODN |  | Tangerang Selatan | Serpong | Serpong | Open Area | 1107 | 0 |  | NON-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process | Memanfaatkan progres Fase 3 & BB Doddy yg sudah Cascade | No Issue | Survey On Process | - | New Area | [5 empty] | NY Start Permit | [35 empty] | NET-H-000067 FTTH Kelurahan Serpong RW 02 | 0
109 | Kelurahan Serpong RW 03 | NET-H-000068 | FTTH Kelurahan Serpong RW 03 | FTTH | QODN |  | Tangerang Selatan | Serpong | Serpong | Open Area | 324 | 0 |  | NON-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process | Memanfaatkan progres Fase 3 & BB Doddy yg sudah Cascade | No Issue | Survey On Process | - | New Area | [5 empty] | NY Start Permit | [35 empty] | NET-H-000068 FTTH Kelurahan Serpong RW 03 | 0
110 | FTTH Kelurahan Cilenggang RW 02 | NET-H-000069 | FTTH Kelurahan Cilenggang RW 02 | FTTH | QODN |  | Tangerang Selatan | Serpong | Cilenggang | Open Area | 534 | 78 | 78 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | New Area | [5 empty] | On Progress |  | Toro | Free 3 Bulan |  |  |  |  | 624 |  | 2024-08-26 | 2024-08-26 | 624 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH Kelurahan Cilenggang RW 02 |  | BTS Doddy | 7 | 14 | 78 | 65 |  | 5 | 1303 |  | 1525 | [8 empty] | NET-H-000069 FTTH Kelurahan Cilenggang RW 02 | 624 | 2024-08-26 | 2024-08-26 | 0010/SVYSPL-MSP/FMI/VIII/2024 | Done | Belacom | 2024-08-30 | 2024-08-30 | 354/SPLICE-BELACOM/FMI/VIII/2024 | Done Splice | 2024-09-18 | 2024-10-04
111 | FTTH Kelurahan Cilenggang RW 03 | NET-H-000070 | FTTH Kelurahan Cilenggang RW 03 | FTTH | QODN |  | Tangerang Selatan | Serpong | Cilenggang | Open Area | 300 | 25 | 25 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | On Progress |  | INHOUSE | Free 3 Bulan |  |  |  |  | 198 |  | 2024-09-02 | 2024-09-02 | 198 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH Cilenggang RW 03 |  | BTS Doddy | 5 | 6 | 25 | 26 | 26 | 5 | 1690 | [10 empty] | NET-H-000070 FTTH Kelurahan Cilenggang RW 03 | 198 | 2024-09-03 | - | - | Done | Belacom | 2024-09-03 | 2024-09-03 | 358/SPLICE-BELACOM/FMI/IX/2024 | Done Splice | 2024-09-18 | 2024-10-07
112 | FTTH Kelurahan Cilenggang RW 04 | NET-H-000071 | FTTH Kelurahan Cilenggang RW 04 | FTTH | QODN |  | Tangerang Selatan | Serpong | Cilenggang | Open Area | 352 | 44 | 44 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | - | New Area | [5 empty] | On Progress |  | INHOUSE | Free 3 Bulan |  |  |  |  | 352 |  |  |  | 352 | Uli | Done | Uploaded to Drive | FTTH Kelurahan Cilenggang RW 04 |  | BTS Doddy | 2 | 6 | 44 | 44 | 38 |  | 4264 | [10 empty] | NET-H-000071 FTTH Kelurahan Cilenggang RW 04 | 352 | - | - | - | Done | Lisma | 2024-07-24 | 2024-07-24 | 004/SPLICE-LISMA/FMI/VII/2024 | Done Splice | 2024-08-02 | 2024-08-07
113 | FTTH Kelurahan Cilenggang RW 05 | NET-H-000072 | FTTH Kelurahan Cilenggang RW 05 | FTTH | QODN |  | Tangerang Selatan | Serpong | Cilenggang | Open Area | 125 | 19 |  | NON-KSO | Nethome |  | INHOUSE | 3. Civil Work | 5. Waiting Implementation | Memanfaatkan progres Fase 3 & BB Doddy yg sudah Cascade | No Issue | Waiting Implementation | - | New Area | [13 empty] | 148 |  | 2025-01-17 | 2025-01-17 | 148 | Muchamad Rivai | APD Done | Uploaded to Drive | APD NET-H-000072 FTTH Kelurahan Cilenggang RW 05 (148 HP) |  | BTS Doddy | 2 | 3 | 19 |  | 4 |  | 1931 | [10 empty] | NET-H-000072 FTTH Kelurahan Cilenggang RW 05 | 0
114 | FTTH Kelurahan Cibarusah Jaya RW 08 | NET-H-000073 | FTTH Kelurahan Cibarusah Jaya RW 08 | FTTH | QODN |  | Kota Bekasi | Cibarusah | Cibarusah jaya | Perumahan | 1500 | 188 | 64 | NON-KSO | Nethome |  | MIP (Mitra Inovasi Persada) | 4. Electrical Work | 7. E2E Integration | Progress instal ODN | Waiting Instal Langji / BTS Cibarusah | Installation On Progress | 0490/SPK-FMI/VII/24 | [6 empty] | On Progress |  | Toro | [5 empty] | 1423 |  | 2024-07-26 | 2024-07-26 | 1423 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH Kelurahan Cibarusah Jaya RW 08 |  | Plan Langji Baru | 6 | 24 | 179 | 197 | 101 |  | 12028 |  |  | 1520 | [7 empty] | NET-H-000073 FTTH Kelurahan Cibarusah Jaya RW 08 | 512 | 2024-07-26 | 2024-07-27 | 0001/SVYSPL-MIP-FMI/VII/2024 | Done | MIP | 2024-07-26 | 2024-07-27 | 0001/SVYSPL-MIP-FMI/VII/2024 | On Progress
115 | FTTH Taman Sari 1 & 2 | NET-H-000074 | FTTH Taman Sari 1 & 2 | FTTH | QODN |  | Kota Bekasi | Setu | Tamansari | Perumahan | 1916 | 0 |  | NON-KSO | Nethome |  | MIP (Mitra Inovasi Persada) | 2. Survey, Sitac & Design | 2. OG Survey | Pole & HP sudah Survey, 3. OG Survey POP | Butuh New POP | Survey On Process | 0489/SPK-FMI/VII/24 | Survey baru diijinkan setelah Agustusan | [41 empty] | NET-H-000074 FTTH Taman Sari 1 & 2 | 0
116 | FTTH Griya Kencana 2 | NET-H-000075 | FTTH Griya Kencana 2 | FTTH | QODN |  | Kota Tangerang | Ciledug | Sudimara | Perumahan | 800 | 0 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 1. Reject | Reject | Waiting Hasil Survey | Menunggu progress FTTH yg sedang berjalan selesai implementasi | Survey On Process | 0488/SPK-FMI/VII/24 | [42 empty] | NET-H-000075 FTTH Griya Kencana 2 | 0
117 | FTTX RW08 Depok | NET-H-000076 | FTTH RW.008 KELURAHAN DEPOK | FTTH | QODN |  | Depok | Pancoran Mas | Depok | Open Area | 500 | 63 |  | NON-KSO | Nethome |  | FIB (Fajar Indonesia Berdikari) | 3. Civil Work | 6. Pole & ODN Instalation | Start Implementasi akan dilakukan di Week 44 | No Issue | Installation On Progress | 0515/SPK-FMI/VII/24 | [6 empty] | On Progress |  | Andi |  |  | 2024-08-29 |  |  | 396 |  | 2024-08-30 | 2024-08-30 | 396 | Aris Setiawan | Done APD | Uploaded to Drive | FTTH RW.008 KELURAHAN DEPOK | - | BTS Apartment Saladdin Depok | 5 | 5 | 47 | 53 |  | 6 | 2664 |  | 236 | [8 empty] | NET-H-000076 FTTH RW.008 KELURAHAN DEPOK | 0 | 2024-08-30 | 2024-08-31 | 0004/SVY-FIB/FMI/VIII/2024 | Done
118 | FTTH Kelurahan Sudimara Selatan RW 06 dan RW 07 | NET-H-000077 | FTTH Kelurahan Sudimara Selatan RW 06 dan RW 07 | FTTH | QODN |  | Kota Tangerang | Ciledug | Sudimara Selatan | Open Area | 800 | 0 |  | NON-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 2. OG Survey | Cek On Desktop HP ¦ Untuk Kompensasi 30rb/HP | Menunggu progress FTTH yg sedang berjalan selesai implementasi | Survey On Process | 0525/SPK-FMI/VII/24 | [6 empty] | On Progress |  | Toro | [33 empty] | NET-H-000077 FTTH Kelurahan Sudimara Selatan RW 06 dan RW 07 | 0
119 | FTTH Kelurahan Pondok Kacang Timur RW 02 | NET-H-000078 | FTTH Kelurahan Pondok Kacang Timur RW 02 | FTTH | QODN |  | Tangerang Selatan | Pondok Aren | Pondok Kacang Timur | Open Area | 416 | 52 | 52 | NON-KSO | Nethome |  | INHOUSE | 4. Electrical Work | 7. E2E Integration | Menunggu Backbone Tangerang Selatan_Fatah Aviary (Jl. Raya Pd. Jagung - Jl. Dr. Setia Budi) | Waiting Implementasi Backbone | Waiting New Backbone | [15 empty] | 416 |  | 2024-07-31 | 2024-07-31 | 416 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH Pondok Kacang Timur RW 02 |  | BTS Raden Fatah | 2 | 8 | 52 | 50 | 47 |  | 4090 |  |  |  | 925 | [6 empty] | NET-H-000078 FTTH Kelurahan Pondok Kacang Timur RW 02 | 416 | 2024-08-24 | - | - | Done
120 | Cluster Citronela | KSO-H-000019 | FTTH KSO Cluster Citronela | FTTH | QODN |  | Kota Depok | Sawangan | Bedahan | Perumahan | 336 | 21 | 20 | KSO | ICN Media |  | iFiber | 5. Ready For Service | 8. Area On Air | On Progress e2e ODN | No Issue | Installation On Progress | [7 empty] | On Progress |  | ICN | [5 empty] | 332 |  | 2024-10-24 | 2024-10-24 | 332 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH KSO Cluster Citronela |  | BTS Abdul Wahab | 1 | 4 | 22 | 22 |  |  |  |  | 380 | [8 empty] | KSO-H-000019 FTTH KSO Cluster Citronela | 300 | 2024-10-28 | 2024-10-28 | 0002/SVY-IFR/FMI/X/2024 | Done | Rinjani | 2024-11-26 | 2024-11-28 | 1767/SPLICE-RINJANI/FMI/XI/2024 | Done Splice | 2024-12-05 | 2024-12-26
121 | FTTX RW09 Jatimekar | NET-H-000079 | FTTH Jatimekar RW 09 | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatimekar | Open Area | 385 | 0 |  | NON-KSO | Nethome |  | - | 1. Reject | Reject | Terdapat RT/RW net diarea tersebut | Terdapat RT/RW net diarea tersebut | Permit Issue | [7 empty] | On Progress |  | Rino Patty | [33 empty] | NET-H-000079 FTTH Jatimekar RW 09 | 0
122 | FTTH Taman Firdaus 1 & 2 | NET-H-000080 | FTTH Taman Firdaus 1 & 2 | FTTH | QODN |  | Kab. Bekasi | Cibarusah | CibarusahKota | Perumahan | 2500 | 313 | 294 | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 3. Civil Work | 6. Pole & ODN Instalation | Progress Instal ODN | Waiting Instal Langji / BTS Cibarusah | Installation On Progress | [7 empty] | On Progress |  | Toro | [5 empty] | 2921 |  | 2024-09-14 | 2024-09-14 | 2899 | Muchamad Rivai | APD Done | Uploaded to Drive | APD FTTH QODN Taman Firdaus 1 & 2 |  | Langji Cibarusah | 12 | 42 | 295 | 321 |  |  | 17363 |  | 2625 |  | 550 | [6 empty] | NET-H-000080 FTTH Taman Firdaus 1 & 2 | 2352 | 2024-10-17 | 2024-10-17 | 0001/SVYSPL-RPS/FMI/X/2024 | Done | RPS | 2024-10-17 | 2024-10-17 | 0001/SVYSPL-RPS/FMI/X/2024 | On Progress
123 | FTTH Jl. Masjid Baitulsalam | NET-H-000081 | FTTH Jl. Masjid Baitulsalam | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatiasih | Open Area | 200 | 25 | 25 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | Non Sitac |  | Non Sitac | Reguler |  |  |  |  | 200 |  |  |  | 200 | Iyat | APD Done | Uploaded to Drive | FTTH Jl. Masjid Baitussalam (QODN MSP) |  | BTS KOMSEN | 2 | 4 | 25 | 0 | 0 | 21 | 1170 | [10 empty] | NET-H-000081 FTTH Jl. Masjid Baitulsalam | 200 | - | - | - | Done | Rinjani | 2024-08-05 | 2024-08-06 | 1137/SPLICE-RINJANI/RA/VIII/2024 | Done Splice | 2024-08-07 | 2024-08-08
124 | FTTX Komp KOPASSUS Cijantung | NET-H-000082 | FTTH KOMPLEK KOPASSUS CIJANTUNG | FTTH | QODN |  | Jakarta Timur | Pasar Rebo | Cijantung | Perumahan | 1550 | 194 |  | NON-KSO | Nethome |  | Zareen Global Prima | 3. Civil Work | 6. Pole & ODN Instalation | Zareen meminta kepastian kapan Progress Implementasi dapat dilanjutkan, apabila tidak ada kejelasan Zareen meminta untuk di opname & mengundurkan diri | Setelah hasil pertemuan dengan pihak kopassus (W2 Januari 2025), untuk implementasi sudah dapat dilakukan kembali progressnya di W4 Januari | Implementation Issue | - | [6 empty] | On Progress |  | Andi |  |  | 2024-08-19 | PT. Zareen | Done | 1382 |  | 2024-08-23 | 2024-08-23 | 1382 | Aris Setiawan | Done APD | Uploaded to Drive | FTTH KOMPLEK KOPASSUS CIJANTUNG | New Langji | New Langji/BTS Gudang Air | 13 | 13 | 178 | 235 |  |  | 13585 |  | 1667 | [8 empty] | NET-H-000082 FTTH KOMPLEK KOPASSUS CIJANTUNG | 0 | 2024-08-23 | 2024-08-23 | 0001/SVYSPL-Zareen-FMI/VIII/2024 | On Progress | Zareen | 2024-08-23 | 2024-08-23 | 0001/SVYSPL-Zareen-FMI/VIII/2024 | On Progress
125 | FTTH Jl. Muri Salim | NET-H-000083 | FTTH Jl. Muri Salim | FTTH | QODN |  | Tangerang Selatan | Ciputat Timur | Pisangan | Open Area | 192 | 24 | 24 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | Non Sitac |  | Non Sitac | Reguler |  |  |  |  | 192 |  |  |  | 192 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH Jl.H.Muri Salim (QODN MSP) | Hub Box 02 terdapat 2 line active (Idle) | BTS Legoso | 2 | 3 | 24 | 0 | 0 | 21 | 1870 | [10 empty] | NET-H-000083 FTTH Jl. Muri Salim | 192 | - | - | - | Done | Rinjani | 2024-08-07 | 2024-08-07 | 1146/SPLICE-RINJANI/FMI/VIII/2024 | Done Splice | 2024-08-14 | 2024-08-16
126 | FTTH Cibarusah Indah RW 07 | NET-H-000084 | FTTH Cibarusah Indah RW 07 | FTTH | QODN |  | Kota Bekasi | Cibarusah | Cibarusah jaya | Perumahan | 800 | 100 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 3. Civil Work | 6. Pole & ODN Instalation | Progress Penanaman Pole | Pihak RW menolak untuk pembangunan infra area tsb | Installation On Progress | [7 empty] | On Progress |  | Toro | [5 empty] | 712 |  | 2024-09-26 | 2024-09-26 | 869 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH Cibarusah Indah RW 07 |  | Langji Cibarusah | 4 | 14 | 89 | 116 |  |  | 6205 |  | 1180 | [8 empty] | NET-H-000084 FTTH Cibarusah Indah RW 07 | 0 | 2024-10-23 | 2024-11-04 | 0004/SVYSPL-RPS/FMI/X/2024 | On Progress | RPS | 2024-10-23 | 2024-11-04 | 0004/SVYSPL-RPS/FMI/X/2024 | On Progress
127 | FTTH Taman Persada RW 10 | NET-H-000085 | FTTH Taman Persada RW 10 | FTTH | QODN |  | Kota Bekasi | Cibarusah | Cibarusah jaya | Perumahan | 1500 | 188 | 10 | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 3. Civil Work | 6. Pole & ODN Instalation | Progress Penanaman Pole | Waiting Instal Langji / BTS Cibarusah | Installation On Progress | [7 empty] | On Progress |  | Toro |  |  | 2024-08-10 | PT. Zareen | Done | 1114 |  | 2024-09-18 | 2024-09-18 | 989 | M. Raul Habib | APD Done | Uploaded to Drive | FTTH Taman Persada RW 10 |  | BTS Plan Cibarusah | 4 | 15 | 106 | 126 | 0 | 3 | 7.262 |  | 80 |  | 850 | [6 empty] | NET-H-000085 FTTH Taman Persada RW 10 | 80 | 2024-10-23 | 2024-10-23 | 0002/SVYSPL-RPS/FMI/X/2024 | On Progress | RPS | 2024-10-23 | 2024-10-23 | 0002/SVYSPL-RPS/FMI/X/2024 | On Progress
128 | FTTH Taman Firdaus 3 & 4 | NET-H-000086 | FTTH Taman Firdaus 3 & 4 | FTTH | QODN |  | Kota Bekasi | Cibarusah | Cibarusah jaya | Perumahan | 800 | 100 | 40 | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 3. Civil Work | 6. Pole & ODN Instalation | Progress Penanaman Pole | Waiting Instal Langji / BTS Cibarusah | Installation On Progress | [7 empty] | On Progress |  | Toro |  |  | 2024-08-10 | PT. Zareen |  | 729 |  | 2024-09-25 | 2024-09-25 | 729 | M. Raul Habib | APD Done | Uploaded to Drive | FTTH Taman Firdaus 3 & 4 (729 HP) |  | BTS Plan Cibarusah | 4 | 10 | 74 | 96 | 0 | 5 | 4699 |  | 930 | [8 empty] | NET-H-000086 FTTH Taman Firdaus 3 & 4 | 320 | 2024-10-23 | 2024-10-23 | 0003/SVYSPL-RPS/FMI/X/2024 | On Progress | RPS | 2024-10-23 | 2024-10-23 | 0003/SVYSPL-RPS/FMI/X/2024 | On Progress
129 | FTTH Jl.Perintis - Pisangan | NET-H-000087 | FTTH Jl.Perintis - Pisangan | FTTH | QODN |  | Tangerang Selatan | Ciputat Timur | Pisangan | Open Area | 64 | 8 | 8 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | Non Sitac |  | Non Sitac | Reguler |  |  |  |  | 64 |  |  |  | 64 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH Jl.Perintis (QODN MSP) |  | BTS Legoso | 1 | 1 | 8 | 0 | 0 | 8 | 558 | [10 empty] | NET-H-000087 FTTH Jl.Perintis - Pisangan | 64 | - | - | - | Done | Rinjani | 2024-08-09 | 2024-08-09 | 1153/SPLICE-RINJANI/FMI/VIII/2024 | Done Splice | 2024-08-29 | 2024-08-31
130 | FTTH Jl. Lobak - Pondok Cabe Ilir | NET-H-000088 | FTTH Jl. Lobak - Pondok Cabe Ilir | FTTH | QODN |  | Tangerang Selatan | Pamulang | Pondok Cabe Ilir | Open Area | 112 | 14 | 14 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | Non Sitac |  | Non Sitac | Reguler |  |  |  |  | 112 |  |  |  | 112 | Uli | APD Done | Uploaded to Drive | FTTH Jl. Lobak (QODN MSP) |  | BTS Legoso | 1 | 2 | 14 | 0 | 0 | 8 | [11 empty] | NET-H-000088 FTTH Jl. Lobak - Pondok Cabe Ilir | 112 | - | - | - | Done | Rinjani | 2024-08-07 | 2024-08-08 | 1152/SPLICE-RINJANI/FMI/VIII/2024 | Done Splice | 2024-08-20 | 2024-08-24
131 | FTTH JL. BUKIT RAYA II - PISANGAN | NET-H-000089 | FTTH JL. BUKIT RAYA II - PISANGAN | FTTH | QODN |  | Tangerang Selatan | Ciputat Timur | Pisangan | Open Area | 64 | 8 | 8 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | Non Sitac |  | Non Sitac | Reguler |  |  |  |  | 64 |  |  |  | 64 | Iyat | APD Done | Uploaded to Drive | FTTH JL. BUKIT RAYA II - PISANGAN (QODN MSP) |  | BTS Legoso | 1 | 1 | 8 | 0 | 0 | 8 | [11 empty] | NET-H-000089 FTTH JL. BUKIT RAYA II - PISANGAN | 64 | - | - | - | Done | Rinjani | 2024-08-09 | 2024-08-09 | 1164/SPLICE-RINJANI/FMI/VIII/2024 | Done Splice | 2024-08-20 | 2024-08-22
132 | FTTH Jl. Sinar Asih - Jatiasih RT01 RW08 | NET-H-000090 | FTTH Jl. Sinar Asih - Jatiasih RT01 RW08 | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatiasih | Open Area | 192 | 24 | 24 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | On Progress |  | Zinda | Free 3 Bulan |  |  |  |  | 192 |  |  |  | 192 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH Jl. Sinar Asih - Jatiasih RT01 RW08 (QODN MSP) |  | BTS Komsen | 2 | 3 | 24 | 17 | 16 | 2 | 1642 |  | 90 | [8 empty] | NET-H-000090 FTTH Jl. Sinar Asih - Jatiasih RT01 RW08 | 192 | - | - | - | Done | Rinjani | 2024-08-09 | 2024-08-09 | 1166/SPLICE-RINJANI/FMI/VIII/2024 | Done Splice | 2024-08-20 | 2024-08-21
133 | FTTH Jl. H. Taip | NET-H-000091 | FTTH Jl. H. Taip | FTTH | QODN |  | Tangerang Selatan | Pamulang | Kedaung | Open Area | 128 | 16 | 13 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | Non Sitac |  | Non Sitac | Reguler |  |  |  |  | 104 |  |  |  | 104 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH Jl. H. Taip (QODN MSP) |  | BTS Legoso | 1 | 2 | 13 | 0 | 0 | 8 | 722 | [10 empty] | NET-H-000091 FTTH Jl. H. Taip | 104 | - | - | - | Done | Rinjani | 2024-08-13 | 2024-08-13 | 1181/SPLICE-RINJANI/FMI/VIII/2024 | Done Splice | 2024-09-26 | 2024-11-01
134 | FTTH Jl.H. Abdul Gani-Cempaka Putih,Tangsel | NET-H-000092 | FTTH Jl.H. Abdul Gani-Cempaka Putih,Tangsel | FTTH | QODN |  | Tangerang Selatan | Ciputat Timur | Ciputat Timur | Open Area | 64 | 8 | 8 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | Non Sitac |  | Non Sitac | Reguler |  |  |  |  | 64 |  |  |  | 64 | Iyat | APD Done | Uploaded to Drive | FTTH Jl.H. Abdul Gani-Cempaka Putih,Tangsel |  | BTS Legoso | 1 | 1 | 8 | 0 | 0 | 7 | [11 empty] | NET-H-000092 FTTH Jl.H. Abdul Gani-Cempaka Putih,Tangsel | 64 | - | - | - | Done | Rinjani | 2024-08-16 | 2024-08-16 | 1209/SPLICE-RINJANI/FMI/VIII/2024 | Done Splice | 2024-08-30 | 2024-08-31
135 | Fttx rt 02 rw 15, kaliabang tengah | KSO-H-000020 | FTTX KSO RT.02 RW.015 KALIABANG TENGAH-1 | FTTH | QODN |  | Kota Bekasi | Bekasi Utara | Kaliabang Tengah | Open Area | 64 | 8 | 8 | KSO | FiberHome | pak Sarno | BMS | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air |  | Done Splice ./ On Air | [5 empty] | BA Done |  | Pak Sarno | [5 empty] | 64 |  |  |  | 64 | KSO | APD Done | Uploaded to Drive | FTTX jl lokomotif Kaliabang tengah RT 02 RW 15 |  | BTS Kaliabang | 1 | 1 | 8 | 8 | 8 | [12 empty] | KSO-H-000020 FTTX KSO RT.02 RW.015 KALIABANG TENGAH-1 | 64 | [10 empty] | 2024-08-13
136 | FTTX RW 09 JATIASIH | NET-H-000093 | FTTH Jatiasih RW 09 | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatiasih | Open Area | 700 | 0 |  | NON-KSO | Nethome |  | INHOUSE | 1. Reject | Reject |  | High Price | High Price | [43 empty] | NET-H-000093 FTTH Jatiasih RW 09 | 0
137 | FTTX RW010 Cawang | NET-H-000094 | FTTH RW.10 KELURAHAN CAWANG | FTTH | QODN |  | Jakarta Timur | Kramatjati | Cawang | Open Area | 200 | 33 | 33 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | BA Done |  | Reno | Free 3 Bulan |  |  |  |  | 261 |  | 2024-08-28 | 2024-08-28 | 261 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH RW.10 Kelurahan Cawang |  | BTS Cawang | 3 | 5 | 33 | 20 | 21 | 10 | 1260 |  | 860 | [8 empty] | NET-H-000094 FTTH RW.10 KELURAHAN CAWANG | 261 | 2024-08-28 | 2024-08-28 | 0002/SVY-MSP/FMI/VIII/2024 | Done | Rinjani | 2024-09-07 | 2024-09-07 | 1318/SPLICE-RINJANI/FMI/IX/2024 | Done Splice | 2024-09-24 | 2024-10-03
138 | FTTX RW 005 Jatiasih | NET-H-000095 | FTTH Jatiasih RW 05 | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatiasih | Open Area | 400 | 0 |  | NON-KSO | Nethome |  | FIB (Fajar Indonesia Berdikari) | 2. Survey, Sitac & Design | 1. Sitac Process | Waitng Survey & Sitac | high compentation | Sitac On Process | [7 empty] | NY Start Permit |  | Toro |  | Sudah divisit 2 kali tapi RW masih belum bisa di temui dan belum ada kabar lebih lanjut | [31 empty] | NET-H-000095 FTTH Jatiasih RW 05 | 0
139 | FTTX RW 006 Jatiasih | NET-H-000096 | FTTH Jatiasih RW 06 | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatiasih | Open Area | 600 | 0 |  | NON-KSO | Nethome |  | FIB (Fajar Indonesia Berdikari) | 2. Survey, Sitac & Design | 1. Sitac Process | sitac mengirimkan boundary untuk perhitungan homepass by desktop untuk ke CH (18/09/24) | No Issue | Sitac On Process | [7 empty] | NY Start Permit |  | Toro |  | Sudah divisit 2 kali tapi RW masih belum bisa di temui dan belum ada kabar lebih lanjut | [31 empty] | NET-H-000096 FTTH Jatiasih RW 06 | 0
140 | FTTH RT 02 TAMAN RAHAYU | KSO-H-000021 | FTTH RT 02 TAMAN RAHAYU | FTTH | QODN |  | Kab. Bekasi | Setu | Taman Rahayu | Open Area | 64 | 8 | 8 | KSO | Pak Sarto |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | Non Sitac |  | Non Sitac | [5 empty] | 64 |  |  |  | 64 | Iyat | APD Done | Uploaded to Drive | FTTH RT 02 TAMAN RAHAYU |  | BTS Sevennet | 1 | 1 | 8 | 5 | 5 | 2 | [11 empty] | KSO-H-000021 FTTH RT 02 TAMAN RAHAYU | 64 | - | - | - | Done | Rinjani | 2024-08-20 | 2024-08-20 | 1225/SPLICE-RINJANI/FMI/VIII/2024 | Done Splice | 2024-08-30 | 2024-09-02
141 | Fttx RT.23 RW.03 kel. Babelan Kota, babelan | KSO-H-000022 | KSO-BMS RT.23 RW.03 BABELAN-1 | FTTH | QODN |  | Kab. Bekasi | Babelan | Babelan | Open Area | 64 | 8 | 8 | KSO | FiberHome | pak Sarno | BMS | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air |  | Done Splice ./ On Air | [5 empty] | BA Done |  | Pak Sarno | [5 empty] | 64 |  |  |  | 64 | [9 empty] | 5 | 5 | [12 empty] | KSO-H-000022 KSO-BMS RT.23 RW.03 BABELAN-1 | 64 | [10 empty] | 2024-09-13
142 | FTTH Bantar Gebang RW 09 | KSO-H-000023 | FTTH Bantar Gebang RW 09 | FTTH | QODN |  | Kab. Bekasi | Bantar Gebang | Bantar Gebang | Open Area | 1000 | 68 |  | KSO | Belacom | Rio Karabas | INHOUSE | 1. Reject | Reject | menunggu kabar dari KSO & RW | No Issue | Survey On Process | [7 empty] | On Progress |  | Rio Karabas | [5 empty] | 1080 |  |  |  | 1080 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH BANTAR GEBANG RW 09 (KSO BELACOM) |  | BTS Jatirasa Swatantra | 5 | 11 | 68 | 51 |  | 10 | 3758 |  | 965 | [8 empty] | KSO-H-000023 FTTH Bantar Gebang RW 09 | 0
143 | FTTX RW 003 Sumur Batu | NET-H-000097 | FTTX RW 003 Sumur Batu | FTTH | QODN |  | Kota Bekasi | Bantar Gebang | Sumur Batu | Open Area | 500 | 0 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | On going Sitac (cek HP by Desk) | Cek HP by Desk untuk menghitung kompensasi 25jt | High Price | [7 empty] | NY Start Permit |  | Zahrudin | [33 empty] | NET-H-000097 FTTX RW 003 Sumur Batu | 0
144 | FTTB Landmark Pluit | NET-B-000023 | FTTB Landmark Pluit | FTTB | Reverse |  | Jakarta Utara | Pluit | Pluit | Perkantoran | 136 | 0 |  | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air |  | No Issue | On Air | - | [6 empty] | On Progress |  | Vian Marketing |  |  | 2024-07-22 | Aris Tegar | Done | 136 |  | 2024-08-21 | 2024-08-21 | 136 | Aris Setiawan | Done APD | Uploaded to Drive | FTTB Landmark Pluit | Menggunakan Metode Centralize | BTS Pluit dan BTS Tambora |  | 6 |  |  |  | 19 | [11 empty] | NET-B-000023 FTTB Landmark Pluit | 136 | 2024-08-21 |  |  |  | Rinjani | 2024-08-30 | 2024-08-31 | No. 1287/SPLICE-RINJANI/FMI/VIII/2024 | On Progress |  |  | #N/A | #N/A | #N/A
145 | FTTH Komplek BPN Tonjong | KSO-H-000024 | FTTH Perumahan BPN Tonjong | FTTH | QODN |  | Kabupaten Bogor | Tajur Halang | Tonjong | Perumahan | 350 | 19 | 19 | KSO | ICN Media |  | IFiber | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | On Progress |  | ICN | [5 empty] | 299 |  | 2024-09-04 | 2024-09-04 | 299 | Muchamad Rivai | Done APD | Uploaded to Drive | FTTH QODN Perumahan BPN Tonjong |  | BTS Pura | 2 | 4 | 19 | 25 | 1 |  | 1855 |  | 730 | [8 empty] | KSO-H-000024 FTTH Perumahan BPN Tonjong | 299 | 2024-09-04 | 2024-09-04 | 0001/SVY-IFR/FMI/IX/2024 | Done | Belacom | 2024-09-23 | 2024-09-23 | 389/SPLICE-BELACOM/FMI/IX/2024 | Done Splice | 2024-08-01 | 2024-10-31
146 | FTTX Desa Kalijaya | NET-H-000098 | FTTX Desa Kalijaya | FTTH | QODN |  | Kab Bekasi | Cikarang Barat | Kalijaya |  | 2000 | 0 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | NY Start Permit |  | Andi Noor | [33 empty] | NET-H-000098 FTTX Desa Kalijaya | 0
147 | FTTX RW010 Danamon Green Hill Jatisari | NET-H-000099 | FTTX RW010 Danamon Green Hill Jatisari | FTTH | QODN |  | Kota Bekasi | Bekasi Barat | Jatisari |  | 1200 | 0 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | Akan dikunjungi kembali di Week IV September untuk proses sitac inhouse | No Issue | Sitac On Process | [7 empty] | NY Start Permit |  | Toro | [33 empty] | NET-H-000099 FTTX RW010 Danamon Green Hill Jatisari | 0
148 | FTTX Kelurahan Sindang Sari | NET-H-000100 | FTTX Kelurahan Sindang Sari | FTTH | QODN |  | Bogor |  | Sindang Sari |  | 2000 | 0 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | Menunggu proses pilkada selesai dan akan dikunjungi kembali di bulan oktober | No Issue | Sitac On Process | [7 empty] | NY Start Permit |  | Toro | [33 empty] | NET-H-000100 FTTX Kelurahan Sindang Sari | 0
149 | FTTX Kelurahan Katulampa | NET-H-000101 | FTTX Kelurahan Katulampa | FTTH | QODN |  | Bogor |  | Katulampa |  | 2000 | 0 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | Menunggu proses pilkada selesai dan akan dikunjungi kembali di bulan oktober | No Issue | Sitac On Process | [7 empty] | NY Start Permit |  | Toro | [33 empty] | NET-H-000101 FTTX Kelurahan Katulampa | 0
150 | FTTX RW05 Darusalam | NET-H-000102 | FTTX RW05 Darusalam | FTTH | QODN |  | Jakarta Barat | Kosambi | Ketapang |  | 500 | 0 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | On going Sitac (cek HP by Desk) / Bang Toro mengirimkan boundary update cluster (18/09/24) | No Issue | Sitac On Process | [7 empty] | NY Start Permit |  | Toro | [33 empty] | NET-H-000102 FTTX RW05 Darusalam | 0
151 | FTTX RW04 & RW03 Taman Heulang | NET-H-000103 | FTTX RW04 & RW03 Taman Heulang | FTTH | QODN |  | Bogor | Tanah Sereal | Tanah Sereal |  | 400 | 0 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | Belum dikunjungi | Belum dikunjungi Sitac | Sitac On Process | [7 empty] | NY Start Permit |  | Zahrudin | [33 empty] | NET-H-000103 FTTX RW04 & RW03 Taman Heulang | 0
152 | FTTX RW05 RT03 Caltex dsk, RT01 & RT02 | NET-H-000104 | FTTX RW05 RT03 Caltex dsk, RT01 & RT02 | FTTH | QODN |  | Depok | Beji | Beji Timur |  | 200 | 0 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | Sitac Done untuk RT.03 & sedang proses untuk 01&02 akan difollow up kembali sampai akhir bulan september | kompensasi 25rb/HP & CSR 3 titik | High Price | [7 empty] | NY Start Permit |  | Zahrudin | [33 empty] | NET-H-000104 FTTX RW05 RT03 Caltex dsk, RT01 & RT02 | 0
153 | FTTX Komp.Orchid , Beji | NET-H-000105 | FTTX Komp.Orchid , Beji | FTTH | QODN |  | Depok | Beji | Beji Timur |  | 130 | 0 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | Belum dikunjungi | Belum dikunjungi Sitac | Sitac On Process | [7 empty] | NY Start Permit |  | Zahrudin | [33 empty] | NET-H-000105 FTTX Komp.Orchid , Beji | 0
154 | FTTX RW012 Kelurahan Depok | NET-H-000106 | FTTX RW012 Kemiri Muka | FTTH | QODN |  | Depok | Beji | Kemiri Muka |  | 400 | 27 |  | NON-KSO | Nethome |  | FIB (Fajar Indonesia Berdikari) | 3. Civil Work | 5. Waiting Implementation |  | Terdapat existing di area tsb (KSO) | Waiting Implementation | [7 empty] | On Progress |  | Zahrudin |  |  | 2025-01-09 | FIB |  | 243 |  | 2025-01-15 | 2025-01-15 | 242 | Muchamad Rivai | Done APD | Uploaded to Drive | APD NET-H-000106 FTTX RW012 Kemiri Muka (242 HP) |  | BTS Graha Sentosa | 1 | 4 | 27 | 27 |  |  | 2009 |  | 350 | [8 empty] | NET-H-000106 FTTX RW012 Kemiri Muka | 0
155 | FTTX RW015 Jatisari | NET-H-000107 | FTTX RW015 Jatisari | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatisari |  | 300 | 0 |  | NON-KSO | Nethome |  | - | 1. Reject | Reject | Untuk Implementasi (UG) | Untuk Implementasi (UG) | Permit Issue | [7 empty] | On Progress |  | Rino Patty | [33 empty] | NET-H-000107 FTTX RW015 Jatisari | 0
156 | FTTX RW011 Jatirasa | NET-H-000108 | FTTX RW011 Jatirasa | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatirasa |  | 300 | 0 |  | NON-KSO | Nethome |  | - | 1. Reject | Reject | Tidak mendapat persetujuan RT setempat | Tidak mendapat persetujuan RT setempat | Permit Issue | [7 empty] | On Progress |  | Rino Patty | [33 empty] | NET-H-000108 FTTX RW011 Jatirasa | 0
157 | FTTX RW014 Bhakti Jaya | NET-H-000109 | FTTX RW014 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 500 | 24 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 3. Civil Work | 5. Waiting Implementation | On Progress Sitac | No Issue | Waiting Implementation | [7 empty] | On Progress |  | Zahrudin | [5 empty] | 253 |  | 2024-12-11 | 2024-12-13 | 253 | Aris Setiawan | Done APD | Uploaded to Drive | APD NET-H-000109 FTTX RW014 Bakti Jaya (253 HP) |  | BTS Protel Bakti Jaya | 1 | 4 | 24 | 26 |  | 1 | 1884 |  | 256 | [8 empty] | NET-H-000109 FTTX RW014 Bakti Jaya | 0 | 2024-12-13 | 2024-12-13 | 0007/SVYSPL-SPT-FMI/XII/2024 | On Progress | SPT | 2024-12-13 | 2024-12-13 | 0007/SVYSPL-SPT-FMI/XII/2024 | On Progress
158 | FTTX RW011 Bhakti Jaya | NET-H-000110 | FTTX RW011 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 300 | 35 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 3. Civil Work | 5. Waiting Implementation | On Progress Sitac | No Issue | Waiting Implementation | [7 empty] | On Progress |  | Toro | [5 empty] | 283 |  | 2024-12-11 | 2024-12-13 | 282 | Aris Setiawan | Done APD | Uploaded to Drive | APD NET-H-000110 FTTX RW011 Bakti Jaya (282 HP) |  | BTS Protel Bakti Jaya | 2 | 8 | 35 | 32 |  |  | 2718 |  |  | 789 | [7 empty] | NET-H-000110 FTTX RW011 Bakti Jaya | 0 | 2024-12-13 | 2024-12-13 | 0006/SVYSPL-SPT-FMI/XII/2024 | On Progress | SPT | 2024-12-13 | 2024-12-13 | 0006/SVYSPL-SPT-FMI/XII/2024 | On Progress
159 | FTTX RW012 Bhakti Jaya | NET-H-000111 | FTTX RW012 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 300 | 32 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 3. Civil Work | 5. Waiting Implementation | On Progress Sitac | No Issue | Waiting Implementation | [7 empty] | On Progress |  | Toro | [5 empty] | 346 |  | 2024-12-11 | 2024-12-13 | 332 | Aris Setiawan | Done APD | Uploaded to Drive | APD NET-H-000111 FTTX RW012 Bakti Jaya (332 HP) |  | BTS Protel Bakti Jaya | 2 | 5 | 32 | 30 |  |  | 2518 | [10 empty] | NET-H-000111 FTTX RW012 Bakti Jaya | 0 | 2024-12-13 | 2024-12-13 | 0004/SVYSPL-SPT-FMI/XII /2024 | On Progress | SPT | 2024-12-13 | 2024-12-13 | 0004/SVYSPL-SPT-FMI/XII /2024 | On Progress
160 | FTTX RW013 Bhakti Jaya | NET-H-000112 | FTTX RW013 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 300 | 39 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 3. Civil Work | 5. Waiting Implementation | On Progress Sitac | No Issue | Waiting Implementation | [7 empty] | On Progress |  | Zahrudin | [5 empty] | 340 |  | 2024-12-11 | 2024-12-13 | 342 | Aris Setiawan | Done APD | Uploaded to Drive | APD NET-H-000112 FTTX RW013 Bakti Jaya (342 HP) |  | BTS Protel Bakti Jaya | 2 | 6 | 39 | 32 |  |  | 2830 |  |  | 712 | [7 empty] | NET-H-000112 FTTX RW013 Bakti Jaya | 0 | 2024-12-13 | 2024-12-13 | 0005/SVYSPL-SPT-FMI/XII/2024 | On Progress | SPT | 2024-12-13 | 2024-12-13 | 0005/SVYSPL-SPT-FMI/XII/2024 | On Progress
161 | FTTX RW011 Kemiri Muka | NET-H-000113 | FTTX RW011 Kemiri Muka | FTTH | QODN |  | Depok | Pancoran mas | Kemiri Muka | Perumahan | 400 | 0 |  | NON-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process | On going Sitac (cek HP by Desk) / Bang Reno mengirimkan boundary update cluster (18/09/24) | No Issue | Sitac On Process | [7 empty] | NY Start Permit |  | Rino Patty | [33 empty] | NET-H-000113 FTTX RW011 Kemiri Muka | 0
162 | FTTX RW015 Bhakti Jaya | NET-H-000114 | FTTX RW015 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 300 | 8 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 3. Civil Work | 5. Waiting Implementation | On Progress Sitac | No Issue | Waiting Implementation | [7 empty] | On Progress |  | Toro | [5 empty] | 93 |  | 2024-12-11 | 2024-12-13 | 94 | Aris Setiawan | Done APD | Uploaded to Drive | APD NET-H-000114 FTTX RW015 Bakti Jaya (94 HP) |  | BTS Protel Bakti Jaya |  | 0 | 8 | 8 |  |  | 825 | [10 empty] | NET-H-000114 FTTX RW015 Bakti Jaya | 0 | 2024-12-14 | 2024-12-14 | 0011/SVYSPL-SPT-FMI/XII/2024 | On Progress | SPT | 2024-12-14 | 2024-12-14 | 0011/SVYSPL-SPT-FMI/XII/2024 | On Progress
163 | FTTX Taman Anyelir 3 | NET-H-000115 | FTTX Taman Anyelir 3 | FTTH | QODN |  | Depok | Cilodong | Kalimulya |  | 700 | 0 |  | NON-KSO | Nethome |  | - | 1. Reject | Reject | High Compentation | High Compentation | High Price | [7 empty] | On Progress |  | Toro | [33 empty] | NET-H-000115 FTTX Taman Anyelir 3 | 0
164 | FTTX Taman Anyelir 2 | NET-H-000116 | FTTX Taman Anyelir 2 | FTTH | QODN |  | Depok | Cilodong | Kalimulya |  | 400 | 0 |  | NON-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process | Info team untuk implementasi sitack untuk tagging polenya berbarengan dengan provider lain | No Issue | Sitac On Process | [7 empty] | NY Start Permit |  | Zahrudin | [33 empty] | NET-H-000116 FTTX Taman Anyelir 2 | 0
165 | FTTX RW07 Bhakti Jaya | NET-H-000117 | FTTX RW07 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 300 | 22 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 3. Civil Work | 5. Waiting Implementation | Pak Rw tidak mengijinkan adanya pemasangan tiang baru. | Pak Rw tidak mengijinkan adanya pemasangan tiang baru. | Waiting Implementation | [7 empty] | On Progress |  | Zahrudin | [5 empty] | 209 |  | 2024-12-11 | 2024-12-13 | 216 | Aris Setiawan | Done APD | Uploaded to Drive | APD NET-H-000117 FTTX RW07 Bakti Jaya (216 HP) |  | BTS Protel Bakti Jaya | 1 | 4 | 22 | 23 |  |  | 2031 |  | 83 | [8 empty] | NET-H-000117 FTTX RW07 Bakti Jaya | 0 | 2024-12-14 | 2024-12-14 | 0012/SVYSPL-SPT-FMI/XII/2024 | On Progress | SPT | 2024-12-14 | 2024-12-14 | 0012/SVYSPL-SPT-FMI/XII/2024 | On Progress
166 | FTTX RW01 Telaga Asih | NET-H-000118 | FTTX RW01 Telaga Asih | FTTH | QODN |  | Kota Bekasi | Cikarang Barat | Telaga Asih |  | 300 | 0 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | NY Start Permit |  | Andi Noor | [33 empty] | NET-H-000118 FTTX RW01 Telaga Asih | 0
167 | FTTX RW010 Jatimekar | NET-H-000119 | FTTX RW010 Jatimekar | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatimekar |  | 500 | 0 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | NY Start Permit |  | Andi Noor | [33 empty] | NET-H-000119 FTTX RW010 Jatimekar | 0
168 | FTTX RW09 Jatisari | NET-H-000120 | FTTX RW09 Jatisari | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatisari |  | 500 | 0 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | NY Start Permit |  | Andi Noor | [33 empty] | NET-H-000120 FTTX RW09 Jatisari | 0
169 | FTTX RW06 Bhakti Jaya | NET-H-000121 | FTTX RW06 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 300 | 0 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 2. Survey, Sitac & Design | 2. OG Survey | ada beberapa RT yg tidak mengijinkan adanya pemasangan tiang baru | ada beberapa RT yg tidak mengijinkan adanya pemasangan tiang baru | Survey On Process | [7 empty] | On Progress |  | Zahrudin | [33 empty] | NET-H-000121 FTTX RW06 Bakti Jaya | 0
170 | FTTX RW09 Bhakti Jaya | NET-H-000122 | FTTX RW09 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 300 | 23 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 3. Civil Work | 5. Waiting Implementation | On Progress Sitac | No Issue | Waiting Implementation | [7 empty] | On Progress |  | Zahrudin | [5 empty] | 259 |  | 2024-12-11 | 2024-12-13 | 259 | Aris Setiawan | Done APD | Uploaded to Drive | APD NET-H-000122 FTTX RW09 Bakti Jaya (259 HP) |  | BTS Protel Bakti Jaya | 1 | 4 | 23 | 24 |  |  | 2109 |  | 211 | [8 empty] | NET-H-000122 FTTX RW09 Bakti Jaya | 0 | 2024-12-14 | 2024-12-14 | 0013/SVYSPL-SPT-FMI/XII/2024 | On Progress | SPT | 2024-12-14 | 2024-12-14 | 0013/SVYSPL-SPT-FMI/XII/2024 | On Progress
171 | FTTB Apartment Bogor Icon | NET-B-000024 | FTTB Apartment Bogor Icon | FTTB | Reverse |  | Kota Bogor | Tanah Sereal | Cibadak | Apartment | 759 | 63 |  | NON-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 4. APD Done |  | No Issue | Installation On Progress | [7 empty] | On Progress |  | Fahriah |  |  | 2024-09-10 | Wildan Aulia Rahman | Done | 759 |  | 2024-09-05 | 2024-09-05 | 759 | Aris Setiawan | Done APD | Uploaded to Drive | FTTB Apartment Bogor Icon | Menunggu Hasil survey reschedule jadwal survey | BTS Pura/New Langji |  | 16 | 63 | [14 empty] | NET-B-000024 FTTB Apartment Bogor Icon | 759 |  |  |  |  | Rinjani | 2024-08-06 | 2024-08-06 | No. 1314/SPLICE-RINJANI/FMI/IX/2024 | On Progress |  |  | #N/A | #N/A | #N/A
172 | PERUM CIMANGGU CITY | NET-H-000123 | FTTH PERUM CIMANGGU CITY | FTTH | QODN |  | Kota Bogor | Tanah Sereal | Cibadak | Perumahan | 2568 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Untuk Sitac di area Bukit Cimanggu City & RW 11, saat ini belum menyetujui adanya penambahan provider baru (21/09/24) | No Issue | Sitac On Process | [7 empty] | Reject | High Kompensasi | RPS | [33 empty] | NET-H-000123 FTTH PERUM CIMANGGU CITY | 0
173 | VILLA MUTIARA BOGOR 2,3,4 | NET-H-000124 | FTTH VILLA MUTIARA BOGOR 2,3,4 | FTTH | QODN |  | Kota Bogor | Tanah Sereal | Mekarwangi | Perumahan | 1446 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Waiting Approval & SPK SItac Release | No Issue | Sitac On Process | [7 empty] | Reject | High Kompensasi | RPS | [33 empty] | NET-H-000124 FTTH VILLA MUTIARA BOGOR 2,3,4 | 0
174 | VILLA MUTIARA BOGOR 1 | NET-H-000125 | FTTH VILLA MUTIARA BOGOR 1 | FTTH | QODN |  | Kota Bogor | Tanah Sereal | Mekarwangi | Perumahan | 417 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Waiting Approval & SPK SItac Release | No Issue | Sitac On Process | [7 empty] | Reject | High Kompensasi | RPS | [33 empty] | NET-H-000125 FTTH VILLA MUTIARA BOGOR 1 | 0
175 | RS PMI BOGOR | NET-H-000126 | FTTH RS PMI BOGOR | FTTH | QODN |  | Kabupaten Bogor | Sukaraja | Cilebut Timur | Perumahan | 243 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Waiting Approval & SPK SItac Release | No Issue | Sitac On Process | [7 empty] | Reject | Tidak bole tanam Tiang | RPS | [33 empty] | NET-H-000126 FTTH RS PMI BOGOR | 0
176 | FTTX RW20 Bhakti Jaya | NET-H-000127 | FTTX RW20 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 1400 | 118 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 3. Civil Work | 6. Pole & ODN Instalation | Request material | No Issue | Waiting Implementation | [7 empty] | On Progress |  | Zahrudin | [5 empty] | 1227 |  | 2024-12-17 | 2024-12-17 | 1265 | Muchamad Rivai | APD Done | Uploaded to Drive | APD NET-H-000127 FTTX RW20 Bakti Jaya |  | BTS Protel Bakti Jaya | 5 | 19 | 118 | 107 |  |  | 8969 |  | 1370 | 360 | [7 empty] | NET-H-000127 FTTX RW20 Bakti Jaya | 0 | 2024-12-17 | 2024-12-17 | 0018/SVYSPL-SPT-FMI/XII/2024 | On Progress | SPT | 2024-12-17 | 2024-12-17 | 0018/SVYSPL-SPT-FMI/XII/2024 | On Progress
177 | FTTH Jatisampurna RW 04 & RW 05 | KSO-H-000025 | FTTH Jatisampurna RW 04 & RW 05 | FTTH | QODN |  | Kota Bekasi | Jatisampurna | Jatisampurna | Open Area | 136 | 17 | 17 | KSO | Pak Sarto |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | On Progress | [7 empty] | 136 |  | 2024-09-07 | 2024-09-07 | 136 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH QODN Jatisampurna RW 04 & RW 05 |  | BTS Jatiraden | 2 | 3 | 17 |  |  | 17 | 1139 | [10 empty] | KSO-H-000025 FTTH Jatisampurna RW 04 & RW 05 | 136 | - | - | - | Done | Rinjani | 2024-09-09 | 2024-09-09 | 1327/SPLICE-RINJANI/FMI/IX/2024 | Done Splice | 2024-09-17 | 2024-09-19
178 | FTTX RW08 Bhakti Jaya | NET-H-000128 | FTTX RW08 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 340 | 31 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 3. Civil Work | 5. Waiting Implementation | Pak Rw tidak mengijinkan adanya provieder baru | Pak Rw tidak mengijinkan adanya provieder baru | Waiting Implementation | [7 empty] | On Progress |  | Zahrudin | [5 empty] | 334 |  | 2024-12-11 | 2024-12-13 | 335 | Aris Setiawan | Done APD | Uploaded to Drive | APD NET-H-000128 FTTX RW08 Bakti Jaya (335 HP) |  | BTS Protel Bakti Jaya | 2 | 5 | 31 | 34 |  |  | 2712 | [10 empty] | NET-H-000128 FTTX RW08 Bakti Jaya | 0 | 2024-12-14 | 2024-12-14 | 0014/SVYSPL-SPT-FMI/XII/2024 | On Progress | SPT | 2024-12-14 | 2024-12-14 | 0014/SVYSPL-SPT-FMI/XII/2024 | On Progress
179 | FTTB Apartment Pluit Sea View | NET-B-000025 | FTTB Apartment Pluit Sea View | FTTB | Reverse |  | Jakarta Utara | Kali Baru | Penjaringan | Apartment | 984 | 72 |  | NON-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 3. OG APD |  | No Issue | On Progress APD | [7 empty] | On Progress |  | Fahriah |  |  | 2024-09-07 | Wildan Aulia Rahman | Done | 984 |  | 2024-09-09 | 2024-09-09 | 984 | M. Raul Habib | APD Done | Uploaded to Drive | FTTB Apartment Pluit Sea View | Menunggu Layout Gedung | BTS Pluit & BTS Tambora |  | 18 | 72 | 21 | 0 | 1 | [11 empty] | NET-B-000025 FTTB Apartment Pluit Sea View | 0
180 | FTTB Apartment Paradise Mansion | NET-B-000026 | FTTB Apartment Paradise Mansion | FTTB | Reverse |  | Jakarta Barat | Kalideres | Pegadungan | Apartment | 720 | 49 |  | NON-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 3. OG APD |  | No Issue | On Progress APD | [7 empty] | On Progress |  | Fahriah |  |  | 2024-09-07 | Wildan Aulia Rahman | Done | 720 |  | 2024-09-11 | 2024-09-11 | 720 | M. Raul Habib | APD Done | Uploaded to Drive | FTTB Apartment Paradise Mansion |  | BTS Cangkareng Maxindo & BTS Veteran |  | 13 | 49 | 31 | 0 | 23 | [11 empty] | NET-B-000026 FTTB Apartment Paradise Mansion | 0
181 | FTTH JL. GARUDA RW.05 KELURAHAN JATIRADEN | KSO-H-000026 | FTTH JL. GARUDA RW.05 KELURAHAN JATIRADEN | FTTH | QODN |  | Kota Bekasi | Jatisampurna | Jatisampurna | Open Area | 104 | 13 | 13 | KSO | Pak Sarto |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | On Progress | [7 empty] | 104 |  | 2024-09-09 | 2024-09-09 | 104 | Agung Iyat | APD Done | Uploaded to Drive | FTTH JL. GARUDA RW.05 KELURAHAN JATIRADEN |  | BTS Jatiraden | 1 | 2 | 13 | 0 | 0 | 13 | [11 empty] | KSO-H-000026 FTTH JL. GARUDA RW.05 KELURAHAN JATIRADEN | 104 | - | - | - | Done | Rinjani | 2024-09-10 | 2024-09-10 | 1332/SPLICE-RINJANI/FMI/IX/2024 | Done Splice | 2024-09-23 | 2024-10-22
182 | FTTH Jatiasih RW12 | NET-H-000129 | FTTH Jatiasih RW12 | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatiasih | Open Area | 1000 | 0 |  | NON-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process | Sitac Process | No Issue | Sitac On Process | [7 empty] | NY Start Permit |  | MSP | [33 empty] | NET-H-000129 FTTH Jatiasih RW12 | 0
183 | FTTH Jatiasih RT 03/09 | NET-H-000130 | FTTH Jatiasih RT 03/09 | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatiasih | Open Area | 150 | 32 | 29 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | On Progress |  | MSP | Free 3 Bulan |  |  |  |  | 256 |  | 2024-09-11 | 2024-09-11 | 256 | Agung Iyat | APD Done | Uploaded to Drive | FTTH Jatiasih RT03/09 |  | BTS Komsen | 2 | 5 | 32 | 22 |  | 1 | 1390 |  | 571 | [8 empty] | NET-H-000130 FTTH Jatiasih RT 03/09 | 232 | - | - | - | Done | Belacom | 2024-09-19 | 2024-09-19 | 378/SPLICE-BELACOM/FMI/IX/2024 | Done Splice | 2024-09-26 | 2024-10-07
184 | FTTH Jatiasih RT 02/08 | NET-H-000131 | FTTH Jatiasih RT 02/08 | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatiasih | Open Area | 200 | 21 | 21 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | On Progress |  | MSP | Free 3 Bulan |  |  |  |  | 161 |  | 2024-09-11 | 2024-09-11 | 161 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH QODN Jatiasih RT02 RW08 |  | BTS Komsen | 1 | 4 | 21 | 16 |  |  | 1377 |  | 300 | [8 empty] | NET-H-000131 FTTH Jatiasih RT 02/08 | 161 | 2024-09-12 | - | - | Done | Belacom | 2024-09-13 | 2024-09-13 | 370/SPLICE-BELACOM/FMI/IX/2024 | Done Splice | 2024-10-08 | 2024-10-16
185 | FTTH Pesona Bella Casa | KSO-H-000027 | FTTH Pesona Bella Casa | FTTH | Cascade |  | Kabupaten Bekasi | Babelan | Babelan Kota | Perumahan | 500 | 63 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 4. APD Done |  |  | Waiting Implementation | [7 empty] | On Progress |  | Wahyu Marketing |  |  | 2024-09-11 | Haikal | Done | 475 |  | 2024-09-12 | 2024-09-12 | 475 | Aris Setiawan | Done APD | Uploaded to Drive | FTTH Pesona Bella Casa | Beauty contest dengan Pengelola Perumahan | BTS Babelan |  | 2 | 63 | 43 |  | 1 |  | 277 | 3723 | 342 | [7 empty] | KSO-H-000027 FTTH Pesona Bella Casa | 475
186 | FTTH Jatimekar RW06 | NET-H-000132 | FTTH Jatimekar RW06 | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatimekar | Open Area | 358 | 46 | 43 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | On Progress |  | MSP | Free 3 Bulan |  |  |  |  | 358 |  | 2024-09-20 | 2024-09-20 | 358 | Muchamad Rivai | APD Done | Uploaded to Drive | APD FTTH RW 06 JATIMEKAR |  | BTS Komsen | 4 | 8 | 46 | 36 |  |  | 2058 |  | 980 | [8 empty] | NET-H-000132 FTTH Jatimekar RW06 | 334 | 2024-09-20 | - | - | Done | Rinjani | 2024-10-09 | 2024-10-09 | 1459/SPLICE-RINJANI/FMI/X/2024 | Done Splice | 2024-10-15 | 2024-10-31
187 | FTTB Casablanca East Residences | NET-B-000027 | FTTB Casablanca East Residences | FTTB | Reverse |  | Jakarta Timur | Duren Sawit | Pd. Bambu | Rumah Susun | 1136 | 87 |  | NON-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 3. OG APD |  | No Issue | On Progress APD | [7 empty] | On Progress |  | Fahriah |  |  | 2024-09-11 | Wildan Aulia Rahman | Done | 1136 |  | 2024-09-13 | 2024-09-13 | 1136 | M. Raul Habib | On Progress | Uploaded to Drive | FTTB Casablanca East Residences |  | BTS Prima & Cawang |  | 27 | 87 |  | 0 | [12 empty] | NET-B-000027 FTTB Casablanca East Residences | 0
188 | Fttx RT.24 RW.03 kel. Babelan Kota, babelan | KSO-H-000028 | KSO-BMS RT.24 RW 03 BABELAN-1 | FTTH | QODN |  | Kab. Bekasi | Babelan | Babelan | Open Area | 152 | 19 | 19 | KSO | FiberHome | pak Sarno | BMS | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air |  | Done Splice ./ On Air | [5 empty] | BA Done |  | Pak Sarno | [5 empty] | 152 |  |  |  | 152 | [23 empty] | KSO-H-000028 KSO-BMS RT.24 RW 03 BABELAN-1 | 152 | [10 empty] | 2024-09-13
189 | Fttx RT.05 & 06 RW.01 kel. Babelan Kota, babelan | KSO-H-000029 | KSO-BMS RT.5 & RT.6 RW.01 BABELAN-1 | FTTH | QODN |  | Kab. Bekasi | Babelan | Babelan | Open Area | 200 | 25 | 29 | KSO | FiberHome | pak Sarno | BMS | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air |  | Done Splice ./ On Air | [5 empty] | BA Done |  | Pak Sarno | [5 empty] | 232 |  |  |  | 232 | [23 empty] | KSO-H-000029 KSO-BMS RT.5 & RT.6 RW.01 BABELAN-1 | 232 | [10 empty] | 2024-10-09
190 | Fttx RT.01 RW.01 kel. Babelan Kota, babelan | KSO-H-000030 | KSO-BMS -Fttx RT.01 RW.01 Babelan Kota, Babelan--1 | FTTH | QODN |  | Kab. Bekasi | Babelan | Babelan | Open Area | 152 | 19 | 16 | KSO | FiberHome | pak Sarno | BMS | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air |  | Done Splice ./ On Air | [5 empty] | BA Done |  | Pak Sarno | [5 empty] | 128 |  |  |  | 128 | [23 empty] | KSO-H-000030 KSO-BMS -Fttx RT.01 RW.01 Babelan Kota, Babelan--1 | 128 | [10 empty] | 2024-09-23
191 | Fttx RT.02,03,04,07,19,20,29 RW.01kel. Babelan Kota, babelan | KSO-H-000031 | KSO-BMS -Fttx RT.19,20,29,02,03,04,07 RW.01 Babelan Kota, Babelan-1 | FTTH | QODN |  | Kab. Bekasi | Babelan | Babelan | Open Area | 400 | 50 | 88 | KSO | FiberHome | pak Sarno | BMS | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air |  | Done Splice ./ On Air | [5 empty] | BA Done |  | Pak Sarno | [5 empty] | 704 |  |  |  | 704 | [23 empty] | KSO-H-000031 KSO-BMS -Fttx RT.19,20,29,02,03,04,07 RW.01 Babelan Kota, Babelan-1 | 704 | [10 empty] | 2024-10-08
192 | Fttx rw.046 kel. Bahagia, babelan | KSO-H-000032 | KSO BMS RW 46 KEL. BAHAGIA BABELAN-3 | FTTH | QODN |  | Kab. Bekasi | Babelan | Bahagia | Open Area | 800 | 100 | 121 | KSO | FiberHome | pak Sarno | BMS | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air |  | Done Splice ./ On Air | [5 empty] | BA Done |  | Pak Sarno | [5 empty] | 968 |  |  |  | 968 | [23 empty] | KSO-H-000032 KSO BMS RW 46 KEL. BAHAGIA BABELAN-3 | 968 | [10 empty] | 2024-10-31
193 | FTTB Apartment Bogor Valley | NET-B-000028 | FTTB Apartment Bogor Valley | FTTB | Reverse |  | Kota Bogor | Tanah Sereal | Kedung Badak | Apartment | 728 | 60 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 4. APD Done |  | No Issue | Sitac On Process | [7 empty] | On Progress |  | Fahriah |  |  | 2024-09-10 | Wildan Aulia Rahman | Done | 728 |  | 2024-09-21 | 2024-09-21 | 728 | Aris Setiawan | Done APD | Uploaded to Drive | FTTB Apartment Bogor Valley | New Backbone -+ 13km | BTS Pura/New Langji |  | 15 | 60 | [14 empty] | NET-B-000028 FTTB Apartment Bogor Valley | 728
194 | FTTH CURUG RW04 | NET-H-000133 | FTTH CURUG RW04 | FTTH | QODN |  | Kota Depok | Cimanggis | Curug | Open Area | 150 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process | Pihak RW mendukung tetapi akan koordinasi dulu dengan pengurus RT | No Issue | Sitac On Process | [7 empty] | Reject | Tidak bole tanam Tiang | Magna & Zahrudin |  | Hasil musyawarah Pengurus RW,masing" RT" dan sesepuh, pihak lingkungan tidak mengijinkan/menolak pemasangan Tiang Baru | [31 empty] | NET-H-000133 FTTH CURUG RW04 | 0
195 | FTTH CURUG RW05 | NET-H-000134 | FTTH CURUG RW05 | FTTH | QODN |  | Kota Depok | Cimanggis | Curug | Open Area | 120 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process | Pihak RW & RT setempat mendukung tetapi untuk RT 01 & 02 tidak hadir dan menunggu konfirm ke dua RT tsb | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | Menunggu sosialisasi all RT | Magna & Zahrudin |  | Menunggu keputusan RT 01,02 | [31 empty] | NET-H-000134 FTTH CURUG RW05 | 0
196 | FTTH CURUG RW07 | NET-H-000135 | FTTH CURUG RW07 | FTTH | QODN |  | Kota Depok | Cimanggis | Curug | Open Area | 500 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process | SPK Survey & Sitac Release | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | Menunggu sosialisasi all RT | Magna & Zahrudin |  | diundang untuk sosialisasi langsung dengan masing" RT secepatnya, mengingat di lingkungan sedang ada giat project sumur resapan | [31 empty] | NET-H-000135 FTTH CURUG RW07 | 0
197 | FTTH CURUG RW08 | NET-H-000136 | FTTH CURUG RW08 | FTTH | QODN |  | Kota Depok | Cimanggis | Curug | Open Area | 300 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process | SPK Survey & Sitac Release | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | Menunggu sosialisasi all RT | Magna & Zahrudin |  | RW akan mensosialisasikan ke RT RT | [31 empty] | NET-H-000136 FTTH CURUG RW08 | 0
198 | FTTH SUKATANI RW01 | NET-H-000137 | FTTH SUKATANI RW01 | FTTH | QODN |  | Kota Depok | Cimanggis | Sukatani | Open Area | 100 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 2. OG Survey | Pihak RW akan koordinasi dulu dengan pengurus RT | No Issue | Survey On Process | [7 empty] | On Progress |  | Magna & Zahrudin | [33 empty] | NET-H-000137 FTTH SUKATANI RW01 | 0
199 | FTTH SUKATANI RW02 | NET-H-000138 | FTTH SUKATANI RW02 | FTTH | QODN |  | Kota Depok | Tapos | Sukatani | Open Area | 120 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 2. OG Survey | SPK Survey & Sitac Release | No Issue | Survey On Process | [7 empty] | On Progress |  | Magna & Zahrudin | [33 empty] | NET-H-000138 FTTH SUKATANI RW02 | 0
200 | FTTH SUKATANI RW04 | NET-H-000139 | FTTH SUKATANI RW04 | FTTH | QODN |  | Kota Depok | Tapos | Sukatani | Open Area | 350 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 2. OG Survey | Pihak RW akan koordinasi dulu dengan pengurus RT | No Issue | Survey On Process | [7 empty] | On Progress |  | Magna & Zahrudin | [33 empty] | NET-H-000139 FTTH SUKATANI RW04 | 0
201 | FTTH SUKATANI RW08 | NET-H-000140 | FTTH SUKATANI RW08 | FTTH | QODN |  | Kota Depok | Tapos | Sukatani | Open Area | 220 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 2. OG Survey | Pengurus RW sedang tidak dilokasi & akan diinformasikan lebih lanjut untuk pertemuan | No Issue | Survey On Process | [7 empty] | On Progress |  | Magna & Zahrudin | [33 empty] | NET-H-000140 FTTH SUKATANI RW08 | 0
202 | FTTH SUKATANI RW10 | NET-H-000141 | FTTH SUKATANI RW10 | FTTH | QODN |  | Kota Depok | Tapos | Sukatani | Open Area | 1200 | 69 |  | NON-KSO | Nethome |  | Magna Energi | 3. Civil Work | 6. Pole & ODN Instalation | Progress Pulling & digging pole | No Issue | Installation On Progress | [7 empty] | BA Done |  | Magna & Zahrudin | [5 empty] | 758 |  | 2024-11-15 | 2024-11-15 | 758 | Aris Setiawan | Done APD | Uploaded to Drive | FTTH SUKATANI RW10 | Waiting info jalur feeder backbone BTS Pekapuran | New Langji/Pekapuran | 3 | 10 | 69 | 107 |  | 4 | 6375 |  |  | 1696 | [7 empty] | NET-H-000141 FTTH SUKATANI RW10 | 0 | 2024-11-25 | 2024-11-26 | 0001/SVYSPL-MAGNA/FMI/XI/2024 | On Progress | Magna | 2024-11-25 | 2024-11-26 | 0001/SVYSPL-MAGNA/FMI/XI/2024 | On Progress
203 | FTTH SUKATANI RW24 | NET-H-000142 | FTTH SUKATANI RW24 | FTTH | QODN |  | Kota Depok | Tapos | Sukatani | Open Area | 600 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 2. OG Survey | Pihak RW akan koordinasi dulu dengan pengurus RT | No Issue | Survey On Process | [7 empty] | On Progress |  | Magna & Zahrudin | [33 empty] | NET-H-000142 FTTH SUKATANI RW24 | 0
204 | FTTH SUKAMAJU BARU RW05 | NET-H-000143 | FTTH SUKAMAJU BARU RW05 | FTTH | QODN |  | Kota Depok | Tapos | Sukamaju Baru | Open Area | 550 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process | Pihak RW mendukung tetapi beberapa RT menolak akan koordinasi dulu dengan pengurus RT | No Issue | Sitac On Process | [7 empty] | Reject | Tidak bole tanam Tiang | Magna & Zahrudin | [33 empty] | NET-H-000143 FTTH SUKAMAJU BARU RW05 | 0
205 | FTTH SUKAMAJU BARU RW06 | NET-H-000144 | FTTH SUKAMAJU BARU RW06 | FTTH | QODN |  | Kota Depok | Tapos | Sukamaju Baru | Open Area | 1000 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process | Pihak RW mendukung tetapi akan koordinasi dulu dengan pengurus RT | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | Menunggu sosialisasi all RT | Magna & Zahrudin |  | Kunjungan Kedua, Belum bisa bertemu dengan Ketua RW masih di luar kota (info dari tetangga rumah). | [31 empty] | NET-H-000144 FTTH SUKAMAJU BARU RW06 | 0
206 | FTTH SUKAMAJU BARU RW07 | NET-H-000145 | FTTH SUKAMAJU BARU RW07 | FTTH | QODN |  | Kota Depok | Tapos | Sukamaju Baru | Open Area | 1000 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process | Pihak RW mendukung tetapi akan koordinasi dulu dengan pengurus RT | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | Menunggu sosialisasi all RT | Magna & Zahrudin |  | Hasil pertemuan dengan Ketua RW, beliau akan menjadwal untuk sosialisasi Hari Minggu tgl 19 Januari 2025. | [31 empty] | NET-H-000145 FTTH SUKAMAJU BARU RW07 | 0
207 | FTTH SUKAMAJU BARU RW09 | NET-H-000146 | FTTH SUKAMAJU BARU RW09 | FTTH | QODN |  | Kota Depok | Tapos | Sukamaju Baru | Open Area | 800 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process | Pihak RW mendukung tetapi akan koordinasi dulu dengan pengurus RT | No Issue | Sitac On Process | [7 empty] | Reject | Tidak bole tanam Tiang | Magna & Zahrudin | [33 empty] | NET-H-000146 FTTH SUKAMAJU BARU RW09 | 0
208 | FTTH QODN Jatisampurna RW 16 | KSO-H-000033 | FTTH QODN Jatisampurna RW 16 | FTTH | QODN |  | Kota Bekasi | Jatisampurna | Jatisampurna | Open Area | 96 | 12 | 12 | KSO | Pak Sarto |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | On Progress |  | Pak Sarno | [5 empty] | 96 |  | 2024-09-17 | 2024-09-17 | 96 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH QODN Jatisampurna RW 16 |  | BTS Jatiraden | 1 | 2 | 12 |  |  | 12 | 907 | [10 empty] | KSO-H-000033 FTTH QODN Jatisampurna RW 16 | 96 | - | - | - | Done | Rinjani | 2024-09-19 | 2024-09-19 | 1373/SPLICE-RINJANI/FMI/IX/2024 | Done Splice | 2024-09-23 | 2024-10-22
209 | FTTH JL. SAWO 2 RW 04 KELURAHAN JATISAMPURNA | KSO-H-000034 | FTTH JL. SAWO 2 RW 04 KELURAHAN JATISAMPURNA | FTTH | QODN |  | Kota Bekasi | Jatisampurna | Jatisampurna | Open Area | 128 | 16 | 16 | KSO | Pak Sarto |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | On Progress |  | Pak Sarno | [5 empty] | 128 |  | 2024-09-19 |  | 128 | Agung Iyat | APD Done | Uploaded to Drive | FTTH JL. SAWO 2 RW 04 KELURAHAN JATISAMPURNA |  | BTS Jatiraden | 1 | [16 empty] | KSO-H-000034 FTTH JL. SAWO 2 RW 04 KELURAHAN JATISAMPURNA | 128 | - | - | - | Done | Rinjani | 2024-09-19 | 2024-09-19 | 1375/SPLICE-RINJANI/FMI/IX/2024 | Done Splice | 2024-09-24 | 2024-10-17
210 | FTTH KSO Maxpro Desa Karangmukti | KSO-H-000035 | FTTH KSO Maxpro Desa Karangmukti | FTTH | QODN |  | Purwakarta | Bungursari | Karangmukti | Open Area | 1500 | 94 |  | KSO | Maxpro | Pak Anto 0857-1558-5955 | INHOUSE | 3. Civil Work | 5. Waiting Implementation | On going Proses Permit oleh Pak Budi Polisi | No Issue | Waiting Implementation | [7 empty] | On Progress | [7 empty] | 982 |  | 2024-10-04 | 2024-10-04 | 982 | Aris Setiawan | Done APD | Uploaded to Drive | FTTH KSO Maxpro Desa Karangmukti | Waiting info Permit | BTS Cikampek/New Langji | 8 | 12 | 63 | 67 |  |  | 5876 | [10 empty] | KSO-H-000035 FTTH KSO Maxpro Desa Karangmukti | 0
211 | FTTH KSO Maxpro Desa Cibodas | KSO-H-000036 | FTTH KSO Maxpro Desa Cibodas | FTTH | QODN |  | Purwakarta | Bungursari | Cibodas | Open Area | 2000 | 125 |  | KSO | Maxpro | Pak Anto 0857-1558-5955 | INHOUSE | 3. Civil Work | 5. Waiting Implementation | On going Proses Permit oleh Pak Budi Polisi | No Issue | Waiting Implementation | [15 empty] | 2067 |  | 2024-10-04 | 2024-10-04 | 2067 | M. Raul Habib | APD Done | Uploaded to Drive | FTTH KSO Maxpro Desa Cibodas |  | BTS Cikampek/New Langji | 15 | 22 | 130 | 146 |  |  | 10889 | [10 empty] | KSO-H-000036 FTTH KSO Maxpro Desa Cibodas | 0
212 | Kampung Pamahan RW08 RT01 | NET-H-000147 | FTTH Kampung Pamahan RW08 RT01 | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatimekar | Open Area | 284 | 36 | 35 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | On Progress |  | MSP | Free 3 Bulan |  | 2024-09-24 |  | Done | 384 |  | 2024-09-26 | 2024-09-26 | 284 | M. Raul Habib | APD Done | Uploaded to Drive | FTTH Kampung Pamahan RW08 RT01 |  | BTS Komsen | 3 | 4 | 35 | 25 | 0 | 4 | 1635 |  | 520 | [8 empty] | NET-H-000147 FTTH Kampung Pamahan RW08 RT01 | 271 | - | - | - | Done | Rinjani | 2024-10-09 | 2024-10-09 | 1458/SPLICE-RINJANI/FMI/X/2024 | Done Splice | 2024-10-12 | 2024-10-28
213 | RW09 RT02 Jl Bina Asih, Jatiasih | NET-H-000148 | FTTH Jatiasih RT02 RW09 | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatiasih | Open Area | 198 | 25 | 25 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | On Progress |  | MSP | Free 3 Bulan |  |  |  |  | 198 |  | 2024-10-02 | 2024-10-02 | 198 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH Jatiasih RT02 RW09 |  | BTS Komsen | 1 | 4 | 25 | 17 |  | 3 | 1297 |  | 295 | [8 empty] | NET-H-000148 FTTH Jatiasih RT02 RW09 | 198 | 2024-10-03 | - | - | Done | Rinjani | 2024-10-17 | 2024-10-17 | 1506/SPLICE-RINJANI/FMI/X/2024 | Done Splice | 2024-10-19 | 2024-11-11
214 | FTTH Jalur Relokasi Pekayon - Jatiasih (QODN Area 5) | NET-H-000149 | FTTH Komplek Jaka Kencana RT03 RW04 | FTTH | QODN |  | Kota Bekasi | Bekasi Selatan | Jaka Setia | Perumahan | 64 |  |  | NON-KSO | Nethome |  | INHOUSE | 1. Reject | Reject | Status Relokasi masih On Progress | No Issue | Waiting New Backbone | [7 empty] | BA Done |  | Reno | [5 empty] | 40 |  | 2024-09-26 | 2024-09-26 | 40 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH Komplek Jaka Kencana RT03 RW04 |  |  | 1 | [16 empty] | NET-H-000149 FTTH Komplek Jaka Kencana RT03 RW04 | 0
215 | Fttx perumahan kyra residence 3 | KSO-H-000037 | KSO-BMS Fttx perumahan kyra residence 3 | FTTH | QODN |  | Kab. Bekasi | Babelan | Bahagia | Open Area | 128 | 16 | 16 | KSO | FiberHome | pak Sarno | BMS | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air |  | Done Splice ./ On Air | [5 empty] | BA Done |  | Pak Sarno | [5 empty] | 128 |  |  |  | 128 | [23 empty] | KSO-H-000037 KSO-BMS Fttx perumahan kyra residence 3 | 128 | [10 empty] | 2024-10-08
216 | FTTH Jatimulya RT. 01, 02, 03 RW.10 | NET-H-000150 | FTTH Jatimulya RW.10 | FTTH | QODN |  | Kota Bekasi | Mustika Jaya | Mustikasari | Open Area | 2855 | 357 | 195 | NON-KSO | Nethome |  | INHOUSE | 3. Civil Work | 6. Pole & ODN Instalation | Progress Penarikan Kabel Backbone & Feeder | Survey reroute jalur subfeeder | Installation On Progress | [7 empty] | BA Done |  | MSP | Free 3 Bulan |  |  |  |  | 1775 |  | 2024-10-14 | 2024-10-14 | 1728 | Muchamad Rivai | APD Done | Uploaded to Drive | APD FTTH Jatimulya RW10 |  | BTS Pondok Timur | 10 | 32 | 217 | 148 |  |  | 10583 | [10 empty] | NET-H-000150 FTTH Jatimulya RW.10 | 1560 | 2024-10-14 | - | - | Done
217 | Kampung Pamahan RT02 RW08 | NET-H-000151 | FTTH Kampung Pamahan RT02 RW08 | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatimekar | Open Area | 342 | 43 |  | NON-KSO | Nethome |  | INHOUSE | 1. Reject | Reject | pihak RT belum ACC soal program yang kita promosikan | pihak RT belum ACC soal program yang kita promosikan | Permit Issue | [7 empty] | On Progress |  | MSP | [5 empty] | 342 |  | 2024-10-05 | 2024-10-05 | 342 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH Kampung Pamahan RT02 RW08 |  | BTS Komsen | 3 | 6 | 44 | 40 |  |  | 1414 | [10 empty] | NET-H-000151 FTTH Kampung Pamahan RT02 RW08 | 0
218 | FTTH SUKATANI RW03 | NET-H-000152 | FTTH SUKATANI RW03 | FTTH | QODN |  | Kota Depok | Tapos | Sukatani | Open Area | 500 | 104 |  | NON-KSO | Nethome |  | Magna Energi | 3. Civil Work | 6. Pole & ODN Instalation | SPK Survey & Sitac Release | No Issue | Waiting Implementation | [7 empty] | On Progress |  | Magna & Zahrudin |  |  | 2025-01-09 | Magna Energi | Done | 964 |  | 2025-01-13 | 2025-01-13 | 822 | Muchamad Rivai | APD Done | Uploaded to Drive | APD NET-H-000152 FTTH SUKATANI RW03 (822 HP) | Pengurangan HP karna Ext BB-FTTX Crossing Tol Cinere - pertigaan Ciherang Segment 1 | BTS Sukatani Depok | 5 | 15 | 104 | 96 |  |  | 8229 |  | 440 | 740 |  | 720 | [5 empty] | NET-H-000152 FTTH SUKATANI RW03 | 0
219 | FTTB Graha Mandiri Inti Realty | NET-B-000029 | FTTB Graha Mandiri Inti Realty | FTTB | Reverse |  | Jakarta Timur | Pulo Gadung | Rawamangun | Perkantoran | 19 | 0 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process | OG SPK Marketing | No Issue | Sitac On Process | [7 empty] | On Progress |  | Marketing |  |  | 2024-10-03 |  | OG | 19 |  | 2024-10-07 | 2024-10-07 | 19 | M. Raul Habib | APD Done | Uploaded to Drive | FTTB Graha MIR (Mandiri Inti Realty) |  | BTS IS Plaza |  | 1 |  | 2 |  | 1 |  |  | 555 | [8 empty] | NET-B-000029 FTTB Graha Mandiri Inti Realty | 0
220 | FTTX KSO Maxpro Desa Karangmukti | KSO-H-000038 | FTTX KSO Maxpro Desa Karangmukti | FTTH | Cascade |  | Purwakarta | Bungursari | Karangmukti | Open Area | 200 | 44 |  | KSO | Maxpro | Pak Anto 0857-1558-5955 | BMS | 2. Survey, Sitac & Design | 4. APD Done | On going Proses Permit oleh Pak Budi Polisi | No Issue | Survey On Process | [7 empty] | On Progress | [7 empty] | 694 |  | 2024-10-04 | 2024-10-04 | 694 | Aris Setiawan | Done APD | Uploaded to Drive | FTTX KSO Maxpro Desa Karangmukti |  | BTS Cikampek/New Langji | 2 | 6 | 44 | 100 |  | 3 |  |  | 6136 | [8 empty] | KSO-H-000038 FTTX KSO Maxpro Desa Karangmukti | 0 | 2024-10-22 | 2024-10-22 | 0150/SVY-BMS/FMI/X/2024 | On Progress
221 | FTTX KSO Maxpro Desa Cibodas | KSO-H-000039 | FTTX KSO Maxpro Desa Cibodas | FTTH | Cascade |  | Purwakarta | Bungursari | Cibodas | Open Area | 200 | 46 |  | KSO | Maxpro | Pak Anto 0857-1558-5955 | BMS | 2. Survey, Sitac & Design | 4. APD Done | On going Proses Permit oleh Pak Budi Polisi | No Issue | Survey On Process | [15 empty] | 704 |  | 2024-10-04 | 2024-10-04 | 704 | M. Raul Habib | Done APD | Uploaded to Drive | FTTX KSO Maxpro Desa Cibodas |  | BTS Cikampek/New Langji | 2 | 6 | 46 | 143 |  | 1 |  |  | 8532 |  |  | 4066 | [5 empty] | KSO-H-000039 FTTX KSO Maxpro Desa Cibodas | 0 | 2024-10-22 | 2024-10-22 | 0151/SVY-BMS/FMI/X/2024 | On Progress
222 | Fttx RT.01 Rw.26 Tlanjung Udik | KSO-H-000040 | KSO-BMS RT 01 RW 026 Tlanjung Udik | FTTH | Reverse |  | Kab. Bogor | Gunung Putri | Tlajung Udik | Open Area | 64 | 8 | 8 | KSO | FiberHome | pak Sarno | BMS | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air |  | Done Splice ./ On Air | [5 empty] | BA Done |  | Pak Sarno | [5 empty] | 64 |  |  |  | 64 | [23 empty] | KSO-H-000040 KSO-BMS RT 01 RW 026 Tlanjung Udik | 64
223 | FTTH SUKATANI RW16 | NET-H-000153 | FTTH SUKATANI RW16 | FTTH | QODN |  | Kota Depok | Tapos | Sukatani | Open Area | 500 | 63 | 26 | NON-KSO | Nethome |  | Magna Energi | 3. Civil Work | 6. Pole & ODN Instalation | Progress Pulling & digging pole | No Issue | Installation On Progress | [7 empty] | BA Done |  | Magna & Zahrudin | [5 empty] | 262 |  | 2024-11-14 | 2024-11-14 | 262 | Aris Setiawan | Done APD | Uploaded to Drive | FTTH SUKATANI RW16 | Waiting info jalur feeder backbone BTS Pekapuran | New Langji/Pekapuran | 1 | 4 | 26 | 37 |  | 6 | 2900 | [10 empty] | NET-H-000153 FTTH SUKATANI RW16 | 208 | 2024-11-25 | 2024-11-25 | 0002/SVYSPL-MAGNA/FMI/XI/2024 | On Progress | Magna | 2024-11-25 | 2024-11-25 | 0002/SVYSPL-MAGNA/FMI/XI/2024 | On Progress
224 | KSO Indonesia Net - FTTH Kec. Tengah Tani Cirebon | KSO-H-000041 | KSO Indonesia Net - FTTH Kec. Tengah Tani Cirebon | FTTH | QODN |  | Kab. Cirebon | Tengah Tani | Kalibaru | Open Area | 20000 | 741 |  | KSO | Indonesia Net | pak Welly Seano | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 4. APD Done | Waiting SPK Kerjasama | No Issue | Waiting Implementation | [15 empty] | 11000 |  | 2024-11-12 | 2024-11-12 | 8375 | All | Done APD | Uploaded to Drive | KSO Indonesia Net - Kec. Tengah Tani Cirebon |  | New BTS Langji | 66 | 127 | 741 | 833 |  |  | 57950 |  | 7797 | 2850 |  | 1367 | [5 empty] | KSO-H-000041 KSO Indonesia Net - FTTH Kec. Tengah Tani Cirebon | 0
225 | FTTX RW001 Bhakti Jaya | NET-H-000154 | FTTX RW001 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 200 | 26 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 3. Civil Work | 5. Waiting Implementation | On Progress Sitac | No Issue | Waiting Implementation | [7 empty] | On Progress |  | Zahrudin | [5 empty] | 248 |  | 2024-12-16 | 2024-12-16 | 247 | Muchamad Rivai | APD Done | Uploaded to Drive | APD NET-H-000154 FTTX RW001 Bakti Jaya |  | BTS Protel Baktijaya | 1 | 4 | 26 | 28 |  |  | 2331 |  |  | 300 | [7 empty] | NET-H-000154 FTTX RW001 Bakti Jaya | 0 | 2024-12-16 | 2024-12-17 | 0017/SVYSPL-SPT-FMI/XII/2024 | On Progress | SPT | 2024-12-16 | 2024-12-17 | 0017/SVYSPL-SPT-FMI/XII/2024 | On Progress
226 | FTTX RW002 Bhakti Jaya | NET-H-000155 | FTTX RW002 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 300 | 34 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 3. Civil Work | 5. Waiting Implementation | On Progress Sitac | No Issue | Waiting Implementation | [7 empty] | On Progress |  | Zahrudin | [5 empty] | 322 |  | 2024-12-10 | 2024-12-10 | 322 | Muchamad Rivai | APD Done | Uploaded to Drive | APD NET-H-000155 FTTX RW002 Bakti Jaya |  | BTS Protel Baktijaya | 2 | 5 | 34 | 32 |  |  | 2418 |  |  | 375 | [7 empty] | NET-H-000155 FTTX RW002 Bakti Jaya | 0 | 2024-12-13 | 2024-12-13 | 0010/SVYSPL-SPT-FMI/XII/2024 |  | SPT | 2024-12-13 | 2024-12-13 | 0010/SVYSPL-SPT-FMI/XII/2024 | On Progress
227 | FTTX RW003 Bhakti Jaya | NET-H-000156 | FTTX RW003 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 550 | 41 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 3. Civil Work | 6. Pole & ODN Instalation | Request material | No Issue | Waiting Implementation | [7 empty] | On Progress |  | Zahrudin | [5 empty] | 588 |  | 2024-12-13 | 2024-12-13 | 630 | Muchamad Rivai | APD Done | Uploaded to Drive | APD NET-H-000156 FTTX RW003 Bakti Jaya |  | BTS Protel Baktijaya | 2 | 6 | 41 | 37 |  |  | 2943 |  |  | 440 | [7 empty] | NET-H-000156 FTTX RW003 Bakti Jaya | 0 | 2024-12-13 | 2024-12-13 | 0009/SVYSPL-SPT-FMI/XII/2024 |  | SPT | 2024-12-13 | 2024-12-13 | 0009/SVYSPL-SPT-FMI/XII/2024 | On Progress
228 | FTTX RW004 Bhakti Jaya | NET-H-000157 | FTTX RW004 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 450 | 45 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 3. Civil Work | 5. Waiting Implementation | On Progress Sitac | No Issue | Waiting Implementation | [7 empty] | On Progress |  | Zahrudin | [5 empty] | 493 |  | 2024-12-10 | 2024-12-10 | 491 | Muchamad Rivai | APD Done | Uploaded to Drive | APD NET-H-000157 FTTX RW004 Bakti Jaya |  | BTS Protel Baktijaya | 2 | 7 | 45 | 46 |  |  | 4234 |  |  | 300 | [7 empty] | NET-H-000157 FTTX RW004 Bakti Jaya | 0 | 2024-12-13 | 2024-12-13 | 0008/SVYSPL-SPT-FMI/XII/2024 |  | SPT | 2024-12-13 | 2024-12-13 | 0008/SVYSPL-SPT-FMI/XII/2024 | On Progress
229 | FTTX RW005 Bhakti Jaya | NET-H-000158 | FTTX RW005 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 700 | 81 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 3. Civil Work | 6. Pole & ODN Instalation | Request material | No Issue | Waiting Implementation | [7 empty] | On Progress |  | Zahrudin | [5 empty] | 727 |  | 2024-12-14 | 2024-12-14 | 737 | Muchamad Rivai | APD Done | Uploaded to Drive | APD NET-H-000158 FTTX RW005 Bakti Jaya |  | BTS Protel Baktijaya | 3 | 11 | 81 | 78 |  |  | 6805 |  |  | 660 | [7 empty] | NET-H-000158 FTTX RW005 Bakti Jaya | 0 | 2024-12-14 | 2024-12-14 | 0015/SVYSPL-SPT-FMI/XII/2024 |  | SPT | 2024-12-14 | 2024-12-14 | 0015/SVYSPL-SPT-FMI/XII/2024 | On Progress
230 | FTTX RW010 Bhakti Jaya | NET-H-000159 | FTTX RW010 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 250 | 24 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 3. Civil Work | 5. Waiting Implementation | On Progress Sitac | No Issue | Waiting Implementation | [7 empty] | On Progress |  | Zahrudin | [5 empty] | 256 |  | 2024-12-11 | 2024-12-13 | 272 | Aris Setiawan | Done APD | Uploaded to Drive | APD NET-H-000159 FTTX RW010 Bakti Jaya (272 HP) |  | BTS Protel Bakti Jaya | 1 | 4 | 24 | 21 |  |  | 1812 |  | 163 | [8 empty] | NET-H-000159 FTTX RW010 Bakti Jaya | 0 | 2024-12-14 | 2024-12-14 | 0016/SVYSPL-SPT-FMI/XII/2024 |  | SPT | 2024-12-14 | 2024-12-14 | 0016/SVYSPL-SPT-FMI/XII/2024 | On Progress
231 | FTTX RW016 Bhakti Jaya | NET-H-000160 | FTTX RW016 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 400 | 0 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 3. Civil Work | 5. Waiting Implementation |  | No Issue | Survey On Process | [7 empty] | On Progress |  | Zahrudin | [33 empty] | NET-H-000160 FTTX RW016 Bakti Jaya | 0
232 | FTTX RW021 Bhakti Jaya | NET-H-000161 | FTTX RW021 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 500 | 0 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Survey On Process | [7 empty] | On Progress |  | Zahrudin | [33 empty] | NET-H-000161 FTTX RW021 Bakti Jaya | 0
233 | FTTX RW026 Bhakti Jaya | NET-H-000162 | FTTX RW026 Bakti Jaya | FTTH | QODN |  | Depok | Sukmajaya | Bakti Jaya | Perumahan | 500 | 0 |  | NON-KSO | Nethome |  | SPT (Solusi Penerus Teknologi) | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Survey On Process | [7 empty] | On Progress |  | Zahrudin | [33 empty] | NET-H-000162 FTTX RW026 Bakti Jaya | 0
234 | Kebon Pala RT01 RW06 | NET-H-000163 | FTTH Kebon Pala RT01 RW06 | FTTH | QODN |  | Jakarta Timur | Makasar | Kebon Pala | Open Area | 200 | 25 | 16 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | BA Done |  | Reno | Free 3 Bulan |  | 2024-10-22 | Reno | Done | 114 |  |  |  | 121 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH Kebon Pala RT01 RW06 |  | BTS CAWANG | 1 | 2 | 16 | 14 |  |  | 1153 | [10 empty] | NET-H-000163 FTTH Kebon Pala RT01 RW06 | 121 | 2024-10-30 | 2024-10-30 | 0011/SVYSPL-MSP/FMI/X/2024 | Done | Rinjani | 2024-10-29 | 2024-10-30 | 1570/SPLICE-RINJANI/FMI/X/2024 | Done Splice | 2024-12-07 | 2024-12-12
236 | FTTB Apartment Teluk Intan | NET-B-000030 | FTTB Apartment Teluk Intan | FTTB | Reverse |  | Jakarta Utara | Penjaringan | Pejagalan | Apartment | 1620 | 108 |  | NON-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | On Progress |  | Fahriah Marketing | [5 empty] | 1620 |  | 2024-11-04 | 2024-11-04 | 1620 | M. Raul Habib | APD Done | Uploaded to Drive | FTTB Aparatemen Teluk Intan |  | BTS Pluit & Cengkareng | [17 empty] | NET-B-000030 FTTB Apartment Teluk Intan | 0
237 | FTTH Karang Taruna RW35,36,37 | KSO-H-000042 | FTTH Sumber Jaya RW35,36,37 | FTTH | QODN |  | Kab. Bekasi | Tambun | Sumberjaya | Open Area | 300 | 0 |  | NON-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | On Progress APD | [7 empty] | BA Done |  | Izul Marketing | [33 empty] | KSO-H-000042 FTTH Sumber Jaya RW35,36,37 | 0
237 | FTTH Jatirasa RT04 RW05 | NET-H-000165 | FTTH Jatirasa RT04 RW05 | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatirasa | Open Area | 445 | 55 | 58 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | BA Done |  | Ridho | Free 3 Bulan |  |  |  |  | 445 |  | 2024-11-02 | 2024-11-02 | 476 | M. Raul Habib | APD Done | Uploaded to Drive | FTTH QODN Jatirasa RT04 RW05 (445 HP) |  | BTS KOMSEN | 3 | 8 | 59 | 40 |  | 1 | 3350 |  | 795 | [8 empty] | NET-H-000165 FTTH Jatirasa RT04 RW05 | 476 | 2024-11-05 | - | - | Done | Rinjani | 2024-11-11 | 2024-11-12 | 1635/SPLICE-RINJANI/FMI/XI/2024 | Done Splice | 2024-12-10 | 2024-12-18
238 | FTTH Kampung Pamahan RT03 RW08 | NET-H-000166 | FTTH Kampung Pamahan RT03 RW08 | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatimekar | Open Area | 160 | 21 |  | NON-KSO | Nethome |  | INHOUSE | 3. Civil Work | 5. Waiting Implementation | Untuk Infra yang terbangun disana akan di relokasi / digusur dikarenakan akan dibuat untuk jalan tol | Untuk Infra yang terbangun disana akan di relokasi / digusur dikarenakan akan dibuat untuk jalan tol | Waiting Implementation | [7 empty] | BA Done |  | Ridho | Free 3 Bulan |  |  |  |  | 168 |  | 2024-10-31 | 2024-10-31 | 168 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH Kampung Pamahan RT03 RW08 |  | BTS KOMSEN | 1 | 2 | 21 | 12 |  |  | 1030 |  | 295 | [8 empty] | NET-H-000166 FTTH Kampung Pamahan RT03 RW08 | 0 | 2024-11-05 | - | - | On Progress
239 | fttx rt.01 rw 01 babelan | KSO-H-000043 | KSO-BMS RW.01 Babelan (jalur tambahan) | FTTH | QODN |  | Kab. Bekasi | Babelan | Bahagia | Open Area | 120 | 15 | 15 | KSO | FiberHome | pak Sarno | BMS | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air |  | Done Splice ./ On Air | [5 empty] | BA Done |  | Pak Sarno | [5 empty] | 120 |  |  |  | 120 | [23 empty] | KSO-H-000043 KSO-BMS RW.01 Babelan (jalur tambahan) | 120 | [10 empty] | 2024-11-29
240 | Fttx rt.14,16,17,18 rw 03 babelan | KSO-H-000044 | KSO-BMS rt 14,16,17,18 rw 03 babelan | FTTH | QODN |  | Kab. Bekasi | Babelan | Bahagia | Open Area | 576 | 72 | 64 | KSO | FiberHome | pak Sarno | BMS | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air |  | Done Splice ./ On Air | [5 empty] | BA Done |  | Pak Sarno | [5 empty] | 576 |  |  |  | 576 | [23 empty] | KSO-H-000044 KSO-BMS rt 14,16,17,18 rw 03 babelan | 512 | [10 empty] | 2024-11-29
241 | Perumahan Total Persada | NET-H-000167 | FTTH Perumahan Total Persada Kel. Gembor | FTTH | QODN |  | Kota Tangerang | Periuk | Gembor | Open Area | 2000 | 0 |  | NON-KSO | Nethome |  | Techbros | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Reject | Reject karena RT RW Net milik CH |  |  | RW Net jadi pihak warga dan RW menolak, dari RW net dari pihak pengelola ada pemasukan ke kas RW serta kebanyakan tanah warga | [31 empty] | NET-H-000167 FTTH Perumahan Total Persada Kel. Gembor | 0
242 | Pondok Alam Permai | NET-H-000168 | FTTH Pondok Alam Permai Kel. Gembor | FTTH | QODN |  | Kota Tangerang | Periuk | Gembor | Open Area | 1400 | 0 |  | NON-KSO | Nethome |  | Techbros | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Reject | Reject karena RT RW Net milik CH |  |  | RW Net jadi pihak warga dan RW menolak, dari RW net dari pihak pengelola ada pemasukan ke kas RW serta kebanyakan tanah warga | [31 empty] | NET-H-000168 FTTH Pondok Alam Permai Kel. Gembor | 0
243 | Wisma Harapan | NET-H-000169 | FTTH Wisma Harapan Kel. Gembor | FTTH | QODN |  | Kota Tangerang | Periuk | Gembor | Open Area | 2100 | 0 |  | NON-KSO | Nethome |  | Techbros | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Reject | Reject karena RT RW Net milik CH |  |  | RW Net jadi pihak warga dan RW menolak, dari RW net dari pihak pengelola ada pemasukan ke kas RW serta kebanyakan tanah warga | [31 empty] | NET-H-000169 FTTH Wisma Harapan Kel. Gembor | 0
244 | FTTH Bedahan RW02 | NET-H-000170 | FTTH Kel. Bedahan RW02 | FTTH | QODN |  | Kota Depok | Sawangan | Bedahan | Open Area | 800 | 0 |  | NON-KSO | Nethome |  | Fibeart | 2. Survey, Sitac & Design | 1. Sitac Process | HIGH KOMPENSASI | No Issue | High Price | [7 empty] | Sosialisasi Permit | High compensation |  |  | Visit done, kompensasi minta 50 juta /RW | [31 empty] | NET-H-000170 FTTH Kel. Bedahan RW02 | 0
245 | FTTH Bedahan RW04 | NET-H-000171 | FTTH Kel. Bedahan RW04 | FTTH | QODN |  | Kota Depok | Sawangan | Bedahan | Open Area | 2000 | 0 |  | NON-KSO | Nethome |  | Fibeart | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | High compensation |  |  | Visit done, kompensasi minta 50 juta /RW | [31 empty] | NET-H-000171 FTTH Kel. Bedahan RW04 | 0
246 | FTTH Bedahan RW08 | NET-H-000172 | FTTH Kel. Bedahan RW08 | FTTH | QODN |  | Kota Depok | Sawangan | Bedahan | Open Area | 500 | 0 |  | NON-KSO | Nethome |  | Fibeart | 1. Reject | Reject | HIGH KOMPENSASI | Estimasi Jarak alur kurang lebih 5 km dari BTS tedekat | Distance Issue | [43 empty] | NET-H-000172 FTTH Kel. Bedahan RW08 | 0
247 | FTTH Bedahan RW09 | NET-H-000173 | FTTH Kel. Bedahan RW09 | FTTH | QODN |  | Kota Depok | Sawangan | Bedahan | Open Area | 600 | 0 |  | NON-KSO | Nethome |  | Fibeart | 2. Survey, Sitac & Design | 1. Sitac Process | HIGH KOMPENSASI | No Issue | High Price | [7 empty] | Sosialisasi Permit | High compensation |  |  | Visit done, kompensasi minta 50 juta /RW | [31 empty] | NET-H-000173 FTTH Kel. Bedahan RW09 | 0
248 | Backbobe & FTTX KSO Cakrawala Kelurahan Pegadungan | KSO-H-000045 | Backbobe & FTTX KSO Cakrawala Kelurahan Pegadungan | FTTH | Cascade |  | Jakarta Barat | Kalideres | Pegadungan | Open Area |  | 0 |  | KSO | Cakrawala |  | - | 2. Survey, Sitac & Design | 4. APD Done |  |  | On Progress APD | [43 empty] | KSO-H-000045 Backbobe & FTTX KSO Cakrawala Kelurahan Pegadungan | 0
249 | FTTH KSO Cakrawala RW01, & Rw07 Kelurahan Pegadungan | KSO-H-000046 | FTTH KSO Cakrawala RW01, & Rw07 Kelurahan Pegadungan | FTTH | QODN |  | Jakarta Barat | Kalideres | Pegadungan | Open Area | 500 | 72 |  | KSO | Cakrawala |  | - | 3. Civil Work | 6. Pole & ODN Instalation | Menunggu penarikan sub feeder | No Issue | Installation On Progress | [7 empty] | On Progress | [7 empty] | 576 |  | 2024-11-22 | 2024-11-22 | 576 | Muchamad Rivai | APD Done | Uploaded to Drive | FTTH KSO Cakrawala RW01, & Rw07 Kelurahan Pegadungan |  | BTS Pegadungan | 4 | 11 | 72 | 80 |  |  | 5740 |  | 1550 | 175 |  |  | 365 |  |  |  |  | KSO-H-000046 FTTH KSO Cakrawala RW01, & Rw07 Kelurahan Pegadungan | 0 | 2024-11-22 | 2024-11-25 | 0001/SVY-CAKRAWALA/FMI/XI/2024 | On Progress
250 | FTTX Komplek Ruko Harmoni Mas | NET-H-000174 | FTTX Komplek Ruko Harmoni Mas | FTTH | Cascade |  | Jakarta Utara | Penjaringan | Pejagalan | Ruko | 223 | 28 |  | NON-KSO | Nethome |  | - | 3. Civil Work | 5. Waiting Implementation |  |  | Waiting Implementation | [12 empty] | 2024-10-30 | Budi Siswanto | Done |  | Survey Pole dan jalur |  | 2024-11-05 | 223 |  |  |  | FTTX Komplek Ruko Harmoni Mas |  | BTS TAMBORA |  | 4 | 28 | 21 |  | 13 | [11 empty] | NET-H-000174 FTTX Komplek Ruko Harmoni Mas | 0
251 | FTTH Karangsatria RT02 RW04 (KSO Pak Rahmat) | KSO-H-000047 | FTTH Karangsatria RT02 RW04 (KSO Pak Rahmat) | FTTH | QODN |  | Kabupaten Bekasi | Tambun Utara | Karangsatria | Open Area | 55 | 8 | 8 | KSO | Pak Rahmat |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | On Progress | [5 empty] | Pak Rahmat |  | 55 |  | 2024-11-01 | 2024-11-01 | 55 | Aris Setiawan | Done APD | Uploaded to Drive | FTTH Karangsatria RT02 RW04 (KSO Pak Rahmat) |  | BTS TAMBUN BARU | 1 | 1 | 8 | 9 | 9 | 5 | 575 |  | 238 | [8 empty] | KSO-H-000047 FTTH Karangsatria RT02 RW04 (KSO Pak Rahmat) | 63 | 2024-11-01 | 2024-11-02 | 0015/SPLICE-MSP/FMI/XI/2024 | Done | Rinjani | 2024-11-11 | 2024-11-12 | 1636/SPLICE-RINJANI/FMI/XI/2024 | Done Splice | 2024-12-02 | 2024-12-11
252 | FTTH PURI KAHURIPAN 7 (KSO PAK SATRO) | KSO-H-000048 | FTTH PURI KAHURIPAN 7 (KSO PAK SATRO) | FTTH | QODN |  | Kab. Bogor | Cileungsi | Dayeuh | Perumahan | 500 | 76 |  | KSO | Pak Sarto |  | - | 2. Survey, Sitac & Design | 4. APD Done |  | No Issue | Waiting Implementation | [7 empty] | On Progress | [5 empty] | Pak Sarto |  | 806 |  | 2024-11-07 | 2024-11-07 | 806 | Aris Setiawan | Done APD | Uploaded to Drive | FTTH PURI KAHURIPAN 7 (KSO PAK SATRO) | Waiting Jalur Backbone | BTS Cileungsi | 4 | 13 | 76 | 98 |  |  | 5600 |  | 264 | 646 | [7 empty] | KSO-H-000048 FTTH PURI KAHURIPAN 7 (KSO PAK SATRO) | 0
253 | Depok Jaya | NET-H-000175 | FTTH KELURAHAN DEPOK JAYA | FTTH | QODN |  | Kota Depok | Pancoran mas | Depok Jaya | Perumahan | 5000 | 0 |  | NON-KSO | Nethome |  | SBMU (Sembilan Belas Multi Usaha) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Done approaching site | on progress approach ke beberapa RW dalam satu funnel |  |  | Total 31 RW, Reject 21 RW karena Sudah terlalu banyak provider, tiang dan kabel sudan semrawut | [31 empty] | NET-H-000175 FTTH KELURAHAN DEPOK JAYA | 0
254 | Mekarjaya | NET-H-000176 | FTTH KELURAHAN MEKAR JAYA | FTTH | QODN |  | Kota Depok | Sukmajaya | Mekar Jaya | Perumahan | 7900 | 0 |  | NON-KSO | Nethome |  | SBMU (Sembilan Belas Multi Usaha) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Done approaching site | on progress approach ke beberapa RW dalam satu funnel |  |  | Total 15 RW, Reject 9 RW karena sudah terlalu banyak provider, tiang kabel semrawut | [31 empty] | NET-H-000176 FTTH KELURAHAN MEKAR JAYA | 0
255 | Sukasari Barat | NET-H-000177 | FTTH SUKASARI BARAT KELURAHAN SUKASARI | FTTH | QODN |  | Kota Tangerang | Tangerang | Sukasari | Open Area | 3500 | 0 |  | NON-KSO | Nethome |  | Techbros | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Done approaching site | Butuh ijin kelurahan dan kotamadya |  |  | memberikan info bahwa kita harus perijinan ke kelurahan dan kotamadya, ini sempat kejadian dengan ISP lain | [31 empty] | NET-H-000177 FTTH SUKASARI BARAT KELURAHAN SUKASARI | 0
256 | Sukasari Timur | NET-H-000178 | FTTH SUKASARI TIMUR KELURAHAN SUKASARI | FTTH | QODN |  | Kota Tangerang | Tangerang | Sukasari | Open Area | 1000 | 0 |  | NON-KSO | Nethome |  | Techbros | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Done approaching site | Butuh ijin kelurahan dan kotamadya |  |  | memberikan info bahwa kita harus perijinan ke kelurahan dan kotamadya, ini sempat kejadian dengan ISP lain | [31 empty] | NET-H-000178 FTTH SUKASARI TIMUR KELURAHAN SUKASARI | 0
257 | Malaka Jaya | NET-H-000179 | FTTH KELURAHAN MALAKA JAYA | FTTH | QODN |  | Jakarta Timur | Duren Sawit | Malaka Jaya | Open Area | 5000 | 0 |  | NON-KSO | Nethome |  | Gen Power | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Done approaching site | on progress approach ke beberapa RW dalam satu funnel |  |  | Dari total 13 RW, done visit 4 RW (1 RW minta design, 1 RW reject, 2 RW butuh sosialisasi) sisa RW on plan visit | [31 empty] | NET-H-000179 FTTH KELURAHAN MALAKA JAYA | 0
258 | Malaka Sari | NET-H-000180 | FTTH KELURAHAN MALAKA SARI | FTTH | QODN |  | Jakarta Timur | Duren Sawit | Malaka Sari | Open Area | 4600 | 0 |  | NON-KSO | Nethome |  | Gen Power | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Done approaching site | on progress approach ke beberapa RW dalam satu funnel |  |  | Dari total 11 RW, done visit 5 RW (2 RW minta design, 2 RW belum bisa di temui, 1 RW minta kompensasi masih negosiasi) | [31 empty] | NET-H-000180 FTTH KELURAHAN MALAKA SARI | 0
259 | Perumahan Pondok Bambu Selatan | NET-H-000181 | FTTH Perumahan Pondok Bambu Selatan | FTTH | QODN |  | Jakarta Timur | Duren Sawit | Pondok Bambu | Perumahan | 6800 | 0 |  | NON-KSO | Nethome |  | Gen Power | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Sitac On Process | [43 empty] | NET-H-000181 FTTH Perumahan Pondok Bambu Selatan | 0
260 | Perum Taman Permata Indah | NET-H-000182 | FTTH Perum Taman Permata Indah | FTTH | QODN |  | Kota Bekasi | Kedungwaringin | Waringinjaya | Perumahan | 2200 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 1. Reject | Reject | TECHNICAL ISSUE | TECHNICAL ISSUE | Permit Issue | [43 empty] | NET-H-000182 FTTH Perum Taman Permata Indah | 0
261 | Open Area Karangsambung | NET-H-000183 | FTTH Kelurahan Karangsambung | FTTH | QODN |  | Kota Bekasi | Kedungwaringin | Karangsambung | Open Area | 4500 | 164 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 3. Civil Work | 5. Waiting Implementation |  | No Issue | Waiting Implementation | [12 empty] | 2025-01-06 | RPS | Done | 1553 |  | 2025-01-09 | 2025-01-09 | 1153 | M. Raul Habib | Done APD | Uploaded to Drive | NET-H-000183-FTTH Kelurahan Karangsambung |  | BTS IYOM KEDUNG WARINGIN | 13 | 26 | 164 | 267 |  | 32 | 17215 |  | 3420 |  |  | 1397 | [5 empty] | NET-H-000183 FTTH Kelurahan Karangsambung | 0 | 2025-01-09 | 2025-01-09 | 0001/SVYSPL-RPS/FMI/I/2025 | On Progress | RPS | 2025-01-09 | 2025-01-09 | 0001/SVYSPL-RPS/FMI/I/2025 | On Progress
262 | Bumi Waringin Indah 1 | NET-H-000184 | FTTH Bumi Waringin Indah 1 | FTTH | QODN |  | Kota Bekasi | Kedungwaringin | Waringinjaya | Perumahan | 2000 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 1. Reject | Reject | TECHNICAL ISSUE | TECHNICAL ISSUE | Permit Issue | [43 empty] | NET-H-000184 FTTH Bumi Waringin Indah 1 | 0
263 | Bumi Waringin Indah 2 | NET-H-000185 | FTTH Bumi Waringin Indah 2 | FTTH | QODN |  | Kota Bekasi | Kedungwaringin | Waringinjaya | Perumahan | 1800 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 1. Reject | Reject | TECHNICAL ISSUE | TECHNICAL ISSUE | Permit Issue | [43 empty] | NET-H-000185 FTTH Bumi Waringin Indah 2 | 0
264 | Perum Telaga Murni | NET-H-000186 | FTTH Perum Telaga Murni | FTTH | QODN |  | Kota Bekasi | Cikarang Barat | Telagamurni | Perumahan | 2700 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 1. Reject | Reject | TECHNICAL ISSUE | TECHNICAL ISSUE | Permit Issue | [43 empty] | NET-H-000186 FTTH Perum Telaga Murni | 0
265 | Perum Telaga Pesona | NET-H-000187 | FTTH Perum Telaga Pesona | FTTH | QODN |  | Kota Bekasi | Cikarang Barat | Telagamurni | Perumahan | 3000 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Survey On Process | [43 empty] | NET-H-000187 FTTH Perum Telaga Pesona | 0
266 | Telaga Sakinah | NET-H-000188 | FTTH Telaga Sakinah | FTTH | QODN |  | Kota Bekasi | Cikarang Barat | Telagamurni | Perumahan | 500 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 1. Reject | Reject | TECHNICAL ISSUE | TECHNICAL ISSUE | Permit Issue | [43 empty] | NET-H-000188 FTTH Telaga Sakinah | 0
267 | Perum Telaga Harapan | NET-H-000189 | FTTH Perum Telaga Harapan | FTTH | QODN |  | Kota Bekasi | Cikarang Barat | Telagamurni | Perumahan | 2500 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 1. Reject | Reject | HIGH KOMPENSASI | HIGH KOMPENSASI | High Price | [43 empty] | NET-H-000189 FTTH Perum Telaga Harapan | 0
268 | Open Area Sukadanau | NET-H-000190 | FTTH Sukadanau | FTTH | QODN |  | Kota Bekasi | Cikarang Barat | Sukadanau | Open Area | 1500 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Survey On Process | [43 empty] | NET-H-000190 FTTH Sukadanau | 0
269 | Open Area Bojong Koneng | NET-H-000191 | FTTH Bojong Koneng | FTTH | QODN |  | Kota Bekasi | Cikarang Barat | Telagamurni | Open Area | 3300 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Survey On Process | [43 empty] | NET-H-000191 FTTH Bojong Koneng | 0
270 | KSO Indonesia Net - Backbobe & FTTX Kec. Tengah Tani Cirebon | KSO-H-000049 | KSO Indonesia Net - Backbobe & FTTX Kec. Tengah Tani Cirebon | FTTH | Cascade |  | Kab. Cirebon | Tengah Tani | Kalibaru | Open Area | 2000 | 149 |  | KSO | Indonesia Net | pak Welly Seano | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 4. APD Done | Waiting SPK Kerjasama | No Issue | Sitac On Process | [17 empty] | 2024-11-12 | 2024-11-12 | 1684 | All | Done APD | Uploaded to Drive | KSO Indonesia Net - Kec. Tengah Tani Cirebon |  | New BTS Langji | 7 | 22 | 149 | 443 |  |  |  |  | 13225 |  |  | 3985 | 3076 | 4384 |  |  |  | KSO-H-000049 KSO Indonesia Net - Backbobe & FTTX Kec. Tengah Tani Cirebon | 0
271 | Project FTTH QODN Cirebon Bitek Vihara Batch 1 (iForte) | NET-H-000192 | FTTH Vihara 1 Cirebon FASE 1 (1650) | FTTH | QODN |  | Kota Cirebon | Hajarmukti | Larangan | Open Area | 1650 | 207 | 126 | NON-KSO | Nethome |  | MIP, Oemerta, INHOUSE | 5. Ready For Service | 8. Area On Air | Waiting Interconnetion Iforte | Waiting Interconnetion Iforte | Installation On Progress | [7 empty] | On Progress |  | INHOUSE | [5 empty] | 1650 |  |  |  | 1650 | Collabs Planning | APD Done | Uploaded to Drive | FTTH Vihara 1 Cirebon FASE 1 (1650) |  | New Langji Vihara 1 | [17 empty] | NET-H-000192 FTTH Vihara 1 Cirebon FASE 1 (1650) | 1638 | 2024-11-01 | 2024-11-02 | 0010/SVYSPL-OemertaKarya/FMI/XI/2024 / 0003/SVYSPL-MIP-FMI/XI/2024 | Done | MIP | 2024-11-01 | 2024-11-02 | 0010/SVYSPL-OemertaKarya/FMI/XI/2024 / 0003/SVYSPL-MIP-FMI/XI/2024 | On Progress
272 | Project FTTH QODN Cirebon Bitek Vihara Batch 2 (iForte) | NET-H-000193 | FTTH Vihara 1 Cirebon FASE 2 (1768) | FTTH | QODN |  | Kota Cirebon | Hajarmukti | Larangan | Open Area | 1768 | 221 | 127 | NON-KSO | Nethome |  | MIP, Oemerta, INHOUSE | 5. Ready For Service | 8. Area On Air | Waiting Interconnetion Iforte | Waiting Interconnetion Iforte | Installation On Progress | [7 empty] | On Progress |  | INHOUSE | [5 empty] | 1768 |  |  |  | 1768 | Collabs Planning | APD Done | Uploaded to Drive | FTTH Vihara 1 Cirebon FASE 2 (1768) |  | New Langji Vihara 1 | [17 empty] | NET-H-000193 FTTH Vihara 1 Cirebon FASE 2 (1768) | 1651 | 2024-11-01 | 2024-11-02 | 0010/SVYSPL-OemertaKarya/FMI/XI/2024 / 0003/SVYSPL-MIP-FMI/XI/2024 | Done | MIP | 2024-11-01 | 2024-11-02 | 0010/SVYSPL-OemertaKarya/FMI/XI/2024 / 0003/SVYSPL-MIP-FMI/XI/2024 | On Progress
273 | Project FTTH QODN Cirebon Bitek Vihara Batch 3 (iForte) | NET-H-000194 | FTTH Vihara 1 Cirebon FASE 3 (2413) | FTTH | QODN |  | Kota Cirebon | Hajarmukti | Larangan | Open Area | 2413 | 302 | 173 | NON-KSO | Nethome |  | MIP, Oemerta, INHOUSE | 5. Ready For Service | 8. Area On Air | Waiting Interconnetion Iforte | Waiting Interconnetion Iforte | Installation On Progress | [7 empty] | On Progress |  | INHOUSE | [5 empty] | 2413 |  |  |  | 2413 | Collabs Planning | APD Done | Uploaded to Drive | FTTH Vihara 1 Cirebon FASE 3 (2413) |  | New Langji Vihara 1 | [17 empty] | NET-H-000194 FTTH Vihara 1 Cirebon FASE 3 (2413) | 2249 | 2024-11-01 | 2024-11-02 | 0010/SVYSPL-OemertaKarya/FMI/XI/2024 / 0003/SVYSPL-MIP-FMI/XI/2024 | Done | MIP | 2024-11-01 | 2024-11-02 | 0010/SVYSPL-OemertaKarya/FMI/XI/2024 / 0003/SVYSPL-MIP-FMI/XI/2024 | On Progress
274 | Project FTTH QODN Cirebon Bitek Vihara Batch 4 (iForte) | NET-H-000195 | FTTH Vihara 1 Cirebon FASE 4 (1771) | FTTH | QODN |  | Kab. Cirebon | Hajarmukti | Larangan | Open Area | 1771 | 222 | 74 | NON-KSO | Nethome |  | MIP, Oemerta, INHOUSE | 3. Civil Work | 6. Pole & ODN Instalation | Progress Civil & Pemasangan ODN | Progress terhambat dikarenakan sedang ada progress dari provider lain disalah satu RW | Installation On Progress | [7 empty] | On Progress |  | INHOUSE | [5 empty] | 1771 |  |  |  | 1771 | Collabs Planning | APD Done | Uploaded to Drive | FTTH Vihara 1 Cirebon FASE 4 (1771) |  | New Langji Vihara 1 | [17 empty] | NET-H-000195 FTTH Vihara 1 Cirebon FASE 4 (1771) | 962 | 2024-11-01 | 2024-11-02 | 0010/SVYSPL-OemertaKarya/FMI/XI/2024 / 0003/SVYSPL-MIP-FMI/XI/2024 | On Progress | MIP | 2024-11-01 | 2024-11-02 | 0010/SVYSPL-OemertaKarya/FMI/XI/2024 / 0003/SVYSPL-MIP-FMI/XI/2024 | On Progress
275 | Project FTTH QODN Cirebon Bitek Vihara Batch 5 (iForte) | NET-H-000196 | FTTH Vihara 2 Cirebon FASE 5 (2627) | FTTH | QODN |  | Kota Cirebon | Hajarmukti | Larangan | Open Area | 2627 | 329 | 92 | NON-KSO | Nethome |  | MIP, Oemerta, INHOUSE | 3. Civil Work | 6. Pole & ODN Instalation | Progress Civil & Pemasangan ODN | No Issue | Installation On Progress | [7 empty] | On Progress |  | INHOUSE | [5 empty] | 2627 |  |  |  | 2627 | Collabs Planning | APD Done | Uploaded to Drive | FTTH Vihara 2 Cirebon FASE 5 (2627) |  | New Langji Vihara 2 | [17 empty] | NET-H-000196 FTTH Vihara 2 Cirebon FASE 5 (2627) | 1196 | 2024-11-01 | 2024-11-02 | 0010/SVYSPL-OemertaKarya/FMI/XI/2024 / 0003/SVYSPL-MIP-FMI/XI/2024 | On Progress | MIP | 2024-11-01 | 2024-11-02 | 0010/SVYSPL-OemertaKarya/FMI/XI/2024 / 0003/SVYSPL-MIP-FMI/XI/2024 | On Progress
276 | Project FTTH QODN Cirebon Bitek Vihara Batch 6 (iForte) | NET-H-000197 | FTTH Vihara 2 Cirebon FASE 6 (1759) | FTTH | QODN |  | Kota Cirebon | Hajarmukti | Larangan | Open Area | 1759 | 220 | 132 | NON-KSO | Nethome |  | MIP, Oemerta, INHOUSE | 3. Civil Work | 6. Pole & ODN Instalation | Progress Penarikan Kabel Backbone | No Issue | Installation On Progress | [7 empty] | On Progress |  | INHOUSE | [5 empty] | 1759 |  |  |  | 1759 | Collabs Planning | APD Done | Uploaded to Drive | FTTH Vihara 2 Cirebon FASE 6 (1759) |  | New Langji Vihara 2 | [17 empty] | NET-H-000197 FTTH Vihara 2 Cirebon FASE 6 (1759) | 1716 | 2024-11-01 | 2024-11-02 | 0010/SVYSPL-OemertaKarya/FMI/XI/2024 / 0003/SVYSPL-MIP-FMI/XI/2024 | On Progress | MIP | 2024-11-01 | 2024-11-02 | 0010/SVYSPL-OemertaKarya/FMI/XI/2024 / 0003/SVYSPL-MIP-FMI/XI/2024 | On Progress
277 | Project FTTH QODN Cirebon Bitek Vihara Batch 7 (iForte) | NET-H-000198 | FTTH Vihara 2 Cirebon FASE 7 (2009) | FTTH | QODN |  | Kab. Cirebon | Hajarmukti | Larangan | Open Area | 2009 | 252 | 149 | NON-KSO | Nethome |  | MIP, Oemerta, INHOUSE | 3. Civil Work | 6. Pole & ODN Instalation | Progress Civil & Pemasangan ODN | No Issue | Installation On Progress | [7 empty] | On Progress |  | INHOUSE | [5 empty] | 2009 |  |  |  | 2009 | Collabs Planning | APD Done | Uploaded to Drive | FTTH Vihara 2 Cirebon FASE 7 (2009) |  | New Langji Vihara 2 | [17 empty] | NET-H-000198 FTTH Vihara 2 Cirebon FASE 7 (2009) | 1937 | 2024-11-01 | 2024-11-02 | 0010/SVYSPL-OemertaKarya/FMI/XI/2024 / 0003/SVYSPL-MIP-FMI/XI/2024 | On Progress | MIP | 2024-11-01 | 2024-11-02 | 0010/SVYSPL-OemertaKarya/FMI/XI/2024 / 0003/SVYSPL-MIP-FMI/XI/2024 | On Progress
278 | FTTH RT08 RW01 KELURAHAN KALIDERES | NET-H-000199 | FTTH RT08 RW01 KELURAHAN KALIDERES | FTTH | QODN |  | Jakarta Barat | Kalideres | Kalideres | Open Area | 102 | 13 | 13 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | On Progress |  | Toro | Free 3 Bulan |  | 2024-11-07 | TORO | Done | 102 |  | 2024-11-12 | 2024-11-12 | 102 | Agung Iyat | APD Done | Uploaded to Drive | FTTH RT01 RW08 KELURAHAN KALIDERES |  | BTS CANGKARENG MAXINDO | 1 | 2 | 13 | 4 |  | 3 | 500 | [10 empty] | NET-H-000199 FTTH RT08 RW01 KELURAHAN KALIDERES | 102 | 2024-11-16 | - | - | Done | Rinjani | 2024-11-16 | 2024-11-16 | 1672/SPLICE-RINJANI/FMI/XI/2024 | Done Splice | 2024-12-13 | 2024-12-23
279 | FTTH KOMPLEK MABAD RW11 REMPOA (314 HP) | NET-H-000200 | FTTH KOMPLEK MABAD RW11 REMPOA (314 HP) | FTTH | QODN |  | Tangerang Selatan | Ciputat Timur | Rempoa | Open Area | 314 | 39 | 39 | NON-KSO | Nethome |  | INHOUSE | 4. Electrical Work | 7. E2E Integration | Progress Splice Pelurusan Core | No Issue | Installation On Progress | [7 empty] | On Progress |  | INHOUSE | Free 3 Bulan |  |  |  |  | 314 |  | 2024-11-12 | 2024-11-12 | 314 | M. Raul Habib | APD Done | Uploaded to Drive | FTTH KOMPLEK MABAD RW11 REMPOA (314 HP) |  | BTS LEGOSO | 2 | 6 | 39 | 37 |  | 12 | 2725 |  | 785 | [8 empty] | NET-H-000200 FTTH KOMPLEK MABAD RW11 REMPOA (314 HP) | 507 | 2024-11-12 | - | - | Done | Rinjani | 2025-01-10 | 2025-01-10 | 0069/SPLICE-RINJANI/FMI/I/2025 | On Progress
280 | FTTH RT09,10,11,12 RW05 Kelurahan Cawang | NET-H-000201 | FTTH RT09,10,11,12 RW05 Kelurahan Cawang | FTTH | QODN |  | Jakarta Timur | Kramat Jati | Cawang | Open Area | 142 | 18 | 18 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | On Progress |  | Reno | Free 3 Bulan |  | 2024-11-13 | Reno | Done | 142 |  | 2024-11-13 | 2024-11-13 | 142 | Aris Setiawan | Done APD | Uploaded to Drive | FTTH RT09,10,11,12 RW05 Kelurahan Cawang |  | BTS Cawang | 1 | 3 | 18 | 13 |  | 2 | 950 |  | 268 | [8 empty] | NET-H-000201 FTTH RT09,10,11,12 RW05 Kelurahan Cawang | 142 | 2024-11-25 | - | - | Done | Rinjani | 2024-12-17 | 2024-12-17 | 1879/SPLICE-RINJANI/FMI/XII/2024 | Done Splice | 2024-12-23 | 2024-12-27
281 | Komplek DDN | NET-H-000202 | FTTH Komplek DDN | FTTH | QODN |  | Kota Bekasi | Sukadanau | Cikarang Barat | Open Area | 100 | 0 | 0 | KSO-INTERNAL | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000202 FTTH Komplek DDN
282 | RW 015 Kemiri Muka | NET-H-000204 | FTTH RW 015 Kemiri Muka | FTTH | QODN |  | Kota Depok | Beji | Kemiri Muka | Open Area | 700 | 0 |  | KSO-INTERNAL | Nethome |  | FIB (Fajar Indonesia Berdikari) | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Survey On Process | [7 empty] | On Progress |  | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000204 FTTH RW 015 Kemiri Muka
283 | FTTH RW07 Kelurahan Jatiasih | NET-H-000205 | FTTH RW07 Kelurahan Jatiasih | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatiasih | Open Area | 414 | 0 |  | NON-KSO | Nethome |  | - | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | NY Start Permit |  | INHOUSE | Free 3 Bulan | [32 empty] | NET-H-000205 FTTH RW07 Kelurahan Jatiasih
284 | FTTH RW06 Kelurahan Sukadamai | NET-H-000206 | FTTH RW06 Kelurahan Sukadamai | FTTH | QODN |  | Kota Bogor | Tanah Sereal | Sukadamai | Open Area | 266 | 26 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 3. Civil Work | 6. Pole & ODN Instalation | Prepare Material | No Issue | Installation On Progress | [7 empty] | On Progress |  |  |  |  | 2024-11-15 | RPS | Done | 266 |  | 2024-11-29 | 2024-11-29 | 266 | M. Raul Habib | Done APD | Uploaded to Drive | APD NET-H-000209 FTTH RW06 Kelurahan Sukadamai |  |  | 2 | 4 | 26 | 49 | 0 | 2 | 2375 |  |  | 470 | [7 empty] | NET-H-000206 FTTH RW06 Kelurahan Sukadamai | 0 | 2024-12-02 | 2024-12-05 | 0006/SVYSPL-RPS/FMI/XII/2024 | On Progress | RPS | 2024-12-02 | 2024-12-05 | 0006/SVYSPL-RPS/FMI/XII/2024 | On Progress
285 | FTTH RW07 Kelurahan Sukadamai | NET-H-000207 | FTTH RW07 Kelurahan Sukadamai | FTTH | QODN |  | Kota Bogor | Tanah Sereal | Sukadamai | Open Area | 174 | 19 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 3. Civil Work | 6. Pole & ODN Instalation | Prepare Material | No Issue | Installation On Progress | [7 empty] | On Progress |  |  |  |  | 2024-11-15 | RPS | Done | 174 |  | 2024-11-29 | 2024-11-29 | 174 | Muchamad Rivai | APD Done | Uploaded to Drive | APD NET-H-000207 FTTH RW07 Kelurahan Sukadamai |  |  | 1 | 3 | 19 | 29 |  | 4 | 1603 |  | 370 | [8 empty] | NET-H-000207 FTTH RW07 Kelurahan Sukadamai | 0 | 2024-12-02 | 2024-12-05 | 0008/SVYSPL-RPS/FMI/XII/2024 | On Progress | RPS | 2024-12-02 | 2024-12-05 | 0008/SVYSPL-RPS/FMI/XII/2024 | On Progress
286 | FTTH RW05 Kelurahan Kedung Jaya | NET-H-000208 | FTTH RW05 Kelurahan Kedung Jaya | FTTH | QODN |  | Kota Bogor | Tanah Sereal | Kedung Jaya | Open Area | 291 | 32 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 3. Civil Work | 6. Pole & ODN Instalation | Progress Civil | No Issue | Installation On Progress | [7 empty] | On Progress |  |  |  |  | 2024-11-15 | RPS | Done | 291 |  | 2024-11-29 | 2024-11-29 | 291 | M. Raul Habib | Done APD | Uploaded to Drive | APD NET-H-000208 FTTH RW05 Kelurahan Kedung Jaya |  |  | 2 | 4 | 32 | 48 | 0 | 0 | 2900 |  |  | 295 | [7 empty] | NET-H-000208 FTTH RW05 Kelurahan Kedung Jaya | 0 | 2024-12-02 | 2024-12-05 | NET-H-000208 FTTH RW05 | On Progress | RPS | 2024-12-02 | 2024-12-05 | NET-H-000208 FTTH RW05 | On Progress
287 | FTTH RW09 Kelurahan Kedung Jaya | NET-H-000209 | FTTH RW09 Kelurahan Kedung Jaya | FTTH | QODN |  | Kota Bogor | Tanah Sereal | Kedung Jaya | Open Area | 282 | 28 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 3. Civil Work | 5. Waiting Implementation | Prepare Material | No Issue | Waiting Implementation | [7 empty] | On Progress |  |  |  |  | 2024-11-15 | RPS | Done | 282 |  | 2024-11-29 | 2024-11-29 | 282 | Muchamad Rivai | APD Done | Uploaded to Drive | APD NET-H-000209 FTTH RW09 Kelurahan Kedung Jaya |  |  | 1 | 4 | 28 | 41 |  |  | 2081 |  | 340 | [8 empty] | NET-H-000209 FTTH RW09 Kelurahan Kedung Jaya | 0 | 2024-12-02 | 2024-12-05 | 0007/SVYSPL-RPS/FMI/XII/2024 | On Progress | RPS | 2024-12-02 | 2024-12-05 | 0007/SVYSPL-RPS/FMI/XII/2024 | On Progress
288 | FTTH RW 06 Kemiri Muka | NET-H-000210 | FTTH RW 06 Kemiri Muka | FTTH | QODN |  | Kota Depok | Beji | Kemiri Muka | Open Area | 400 | 0 |  | NON-KSO | Nethome |  | FIB (Fajar Indonesia Berdikari) | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Survey On Process | [43 empty] | NET-H-000210 FTTH RW 06 Kemiri Muka
289 | Open Area Panunggangan Utara | NET-H-000211 | FTTH KELURAHAN PANUNGGANGAN UTARA | FTTH | QODN |  | Kota Tangerang | Pinang | Panunggangan Utara | Open Area | 3000 | 0 |  | NON-KSO | Nethome |  | Techbros | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Survey On Process | [43 empty] | NET-H-000211 FTTH KELURAHAN PANUNGGANGAN UTARA
290 | FTTH RW 10 Kemiri Muka | NET-H-000212 | FTTH RW 10 Kemiri Muka | FTTH | QODN |  | Kota Depok | Beji | Kemiri Muka | Open Area | 700 | 0 |  | NON-KSO | Nethome |  | FIB (Fajar Indonesia Berdikari) | 2. Survey, Sitac & Design | 3. OG APD |  | No Issue | On Progress APD | [12 empty] | 2025-01-09 | FIB |  | 470 | [27 empty] | NET-H-000212 FTTH RW 10 Kemiri Muka
291 | FTTH RW 16 Kemiri Muka | NET-H-000213 | FTTH RW 16 Kemiri Muka | FTTH | QODN |  | Kota Depok | Beji | Kemiri Muka | Open Area | 1000 | 0 |  | NON-KSO | Nethome |  | FIB (Fajar Indonesia Berdikari) | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Survey On Process | [43 empty] | NET-H-000213 FTTH RW 16 Kemiri Muka
292 | RW 03 Karang satria | NET-H-000214 | FTTH RW 03 Karang satria | FTTH | QODN |  | Kab. Bekasi | Tambun Utara | Karang Satria | Open Area | 550 | 0 |  | KSO-INTERNAL | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000214 FTTH RW 03 Karang satria
293 | RW 04 Karang satria | NET-H-000215 | FTTH RW 04 Karang satria | FTTH | QODN |  | Kab. Bekasi | Tambun Utara | Karang Satria | Open Area | 900 | 0 |  | KSO-INTERNAL | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Survey On Process | [7 empty] | On Progress |  | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000215 FTTH RW 04 Karang satria
294 | RW 05 Karang satria | NET-H-000216 | FTTH RW 05 Karang satria | FTTH | QODN |  | Kab. Bekasi | Tambun Utara | Karang Satria | Open Area | 1200 | 0 |  | KSO-INTERNAL | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Survey On Process | [7 empty] | On Progress |  | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000216 FTTH RW 05 Karang satria
295 | RW 003 Kali Jambe Lambangsari, Tambun Selatan | NET-H-000217 | FTTH RW 03 Kali Jambe Lambangsar | FTTH | QODN |  | Kab. Bekasi | Tambun Selatan | Lambangsari | Open Area | 500 | 0 |  | KSO-INTERNAL | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000217 FTTH RW 03 Kali Jambe Lambangsar
296 | RW 003 Bengkong Padurenan, Mustikajaya | NET-H-000218 | FTTH Komplek DDN RW 003 Bengkong Padurenan | FTTH | QODN |  | Kota Bekasi | Mustika Jaya | Padurenan | Open Area | 550 | 0 |  | KSO-INTERNAL | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000218 FTTH Komplek DDN RW 003 Bengkong Padurenan
297 | Kel. Kecapi RW 01 | NET-H-000219 | FTTH Kelurahan Kecapi RW 01 | FTTH | QODN |  | Kota Cirebon | Harjamukti | Kecapi | Open Area | 400 | 0 |  | NON-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000219 FTTH Kelurahan Kecapi RW 01
298 | Kel. Kecapi RW 02 | NET-H-000220 | FTTH Kelurahan Kecapi RW 02 | FTTH | QODN |  | Kota Cirebon | Harjamukti | Kecapi | Open Area | 450 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000220 FTTH Kelurahan Kecapi RW 02
299 | Kel. Kecapi RW 03 | NET-H-000221 | FTTH Kelurahan Kecapi RW 03 | FTTH | QODN |  | Kota Cirebon | Harjamukti | Kecapi | Open Area | 450 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000221 FTTH Kelurahan Kecapi RW 03
300 | Kel. Kecapi RW 04 | NET-H-000222 | FTTH Kelurahan Kecapi RW 04 | FTTH | QODN |  | Kota Cirebon | Harjamukti | Kecapi | Open Area | 450 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000222 FTTH Kelurahan Kecapi RW 04
301 | Komplek Kecapi City | NET-H-000223 | FTTH Komplek Kecapi City | FTTH | QODN |  | Kota Cirebon | Harjamukti | Kecapi | Perumahan | 250 | 0 |  | NON-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000223 FTTH Komplek Kecapi City
302 | Kel. Larangan RW 11-17 Perumnas Burung | NET-H-000224 | FTTH Kelurahan Larangan RW 11-17 Perumnas Burung | FTTH | QODN |  | Kota Cirebon | Harjamukti | Larangan | Open Area | 1300 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000224 FTTH Kelurahan Larangan RW 11-17 Perumnas Burung
303 | Kel. Kalijaga RW 10 | NET-H-000225 | FTTH Kelurahan Kalijaga RW 10 | FTTH | QODN |  | Kota Cirebon | Harjamukti | Kalijaga | Open Area | 500 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000225 FTTH Kelurahan Kalijaga RW 10
304 | Komplek Graha Keandra | NET-H-000226 | FTTH Komplek Graha Keandra | FTTH | QODN |  | Kota Cirebon | Harjamukti | Kalijaga | Perumahan | 1200 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000226 FTTH Komplek Graha Keandra
305 | Komplek Graha Arga | NET-H-000227 | FTTH Komplek Graha Arga | FTTH | QODN |  | Kota Cirebon | Harjamukti | Kalijaga | Perumahan | 500 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000227 FTTH Komplek Graha Arga
306 | Komplek Montana Kel. Kalijaga RW 15 | NET-H-000228 | FTTH Komplek Montana FTTH Kelurahan Kalijaga RW 15 | FTTH | QODN |  | Kota Cirebon | Harjamukti | Kalijaga | Perumahan | 250 | 0 |  | NON-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000228 FTTH Komplek Montana FTTH Kelurahan Kalijaga RW 15
307 | Kel. Kalijaga RW 09 | NET-H-000229 | FTTH Kelurahan Kalijaga RW 09 | FTTH | QODN |  | Kota Cirebon | Harjamukti | Kalijaga | Open Area | 900 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000229 FTTH Kelurahan Kalijaga RW 09
308 | Komplek Buana Kalijaga | NET-H-000230 | FTTH Komplek Buana Kalijaga | FTTH | QODN |  | Kota Cirebon | Harjamukti | Kalijaga | Perumahan | 450 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000230 FTTH Komplek Buana Kalijaga
309 | Kel. Kalijaga RW 02 | NET-H-000231 | FTTH Kelurahan Kalijaga RW 02 | FTTH | QODN |  | Kota Cirebon | Harjamukti | Kalijaga | Open Area | 610 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000231 FTTH Kelurahan Kalijaga RW 02
310 | Kel. Kalijaga RW 03 | NET-H-000232 | FTTH Kelurahan Kalijaga RW 03 | FTTH | QODN |  | Kota Cirebon | Harjamukti | Kalijaga | Open Area | 650 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000232 FTTH Kelurahan Kalijaga RW 03
311 | Kel. Kalijaga RW 04 | NET-H-000233 | FTTH Kelurahan Kalijaga RW 04 | FTTH | QODN |  | Kota Cirebon | Harjamukti | Kalijaga | Open Area | 620 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000233 FTTH Kelurahan Kalijaga RW 04
312 | Puri Indah Residence Banjarwangunan | NET-H-000234 | FTTH Puri Indah Residence Banjarwangunan | FTTH | QODN |  | Kab. Cirebon | Mundu | Banjarwangunan | Perumahan | 250 | 0 |  | NON-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000234 FTTH Puri Indah Residence Banjarwangunan
313 | Cluster Flamboyan Banjarwangunan | NET-H-000235 | FTTH Cluster Flamboyan Banjarwangunan | FTTH | QODN |  | Kab. Cirebon | Mundu | Banjarwangunan | Perumahan | 100 | 0 |  | NON-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000235 FTTH Cluster Flamboyan Banjarwangunan
314 | Cluster Raharja | NET-H-000236 | FTTH Cluster Raharja | FTTH | QODN |  | Kab. Cirebon | Mundu | Banjarwangunan | Perumahan | 80 | 0 |  | NON-KSO | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000236 FTTH Cluster Raharja
315 | Perum Taman Banjarwangunan RW 03 | NET-H-000237 | FTTH Perum Taman Banjarwangunan RW 03 | FTTH | QODN |  | Kab. Cirebon | Mundu | Banjarwangunan | Perumahan | 400 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000237 FTTH Perum Taman Banjarwangunan RW 03
316 | Banjarwangunan RW 04 | NET-H-000238 | FTTH Banjarwangunan RW 04 | FTTH | QODN |  | Kab. Cirebon | Mundu | Banjarwangunan | Open Area | 270 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000238 FTTH Banjarwangunan RW 04
317 | Banjarwangunan RW 05 | NET-H-000239 | FTTH Banjarwangunan RW 05 | FTTH | QODN |  | Kab. Cirebon | Mundu | Banjarwangunan | Open Area | 250 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000239 FTTH Banjarwangunan RW 05
318 | Perum Istana Banjar | NET-H-000240 | FTTH Perum Istana Banjar | FTTH | QODN |  | Kab. Cirebon | Mundu | Banjarwangunan | Perumahan | 250 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000240 FTTH Perum Istana Banjar
319 | Banjarwangunan RW 01 | NET-H-000241 | FTTH Banjarwangunan RW 01 | FTTH | QODN |  | Kab. Cirebon | Mundu | Banjarwangunan | Open Area | 450 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000241 FTTH Banjarwangunan RW 01
320 | Komplek Grand Aqeela Firdaus | NET-H-000242 | FTTH Komplek Grand Aqeela Firdaus | FTTH | QODN |  | Kab. Cirebon | Mundu | Banjarwangunan | Perumahan | 150 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [43 empty] | NET-H-000242 FTTH Komplek Grand Aqeela Firdaus
321 | RT 001 RW 012 Rawa Semut Margahayu, Kec. Bekasi Timur | NET-H-000243 | FTTH RT 001 RW 012 Kel. Margahayu | FTTH | QODN |  | Kota Bekasi | Bekasi Timur | Margahayu | Open Area | 300 | 0 |  | KSO-INTERNAL | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000243 FTTH RT 001 RW 012 Kel. Margahayu
322 | FTTH RW 01 Kel. Cilebut Barat | NET-H-000244 | FTTH RW 01 Kel. Cilebut Barat | FTTH | QODN |  | Kab. Bogor | Sukaraja | Cilebut barat | Open Area | 414 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Survey On Process | [43 empty] | NET-H-000244 FTTH RW 01 Kel. Cilebut Barat
323 | FTTH RW 16 Kel. Cilebut Barat | NET-H-000245 | FTTH RW 16 Kel. Cilebut Barat | FTTH | QODN |  | Kab. Bogor | Sukaraja | Cilebut barat | Open Area | 237 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Survey On Process | [43 empty] | NET-H-000245 FTTH RW 16 Kel. Cilebut Barat
324 | Perumahan Kirana Cibitung | NET-H-000246 | FTTH Perumahan Kirana Cibitung | FTTH | QODN |  | Kab. Bekasi | Cibitung | Wanajaya | Perumahan | 4500 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 1. Reject | Reject | HIGH KOMPENSASI | No Issue | High Price | [43 empty] | NET-H-000246 FTTH Perumahan Kirana Cibitung
325 | Perumahan Kirana Cikarang | NET-H-000247 | FTTH Perumahan Kirana Cikarang | FTTH | QODN |  | Kab. Bekasi | Cikarang Barat | Telaga Murni | Perumahan | 4000 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 1. Reject | Reject | TECHNICAL ISSUE | No Issue | Permit Issue | [43 empty] | NET-H-000247 FTTH Perumahan Kirana Cikarang
326 | Perum Karawang Jaya | NET-H-000248 | FTTH Perum Karawang Jaya | FTTH | QODN |  | Karawang | Klari | Gintungkerta | Perumahan | 1000 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 1. Reject | Reject | TECHNICAL ISSUE | No Issue | Permit Issue | [43 empty] | NET-H-000248 FTTH Perum Karawang Jaya
327 | Griya Kondang Asri | NET-H-000249 | FTTH Griya Kondang Asri | FTTH | QODN |  | Karawang | Karawang Timur | Kondangjaya | Perumahan | 2500 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 1. Reject | Reject | TECHNICAL ISSUE | No Issue | Permit Issue | [43 empty] | NET-H-000249 FTTH Griya Kondang Asri
328 | Mutiara Nirwana | NET-H-000250 | FTTH Mutiara Nirwana | FTTH | QODN |  | Karawang | Karawang Timur | Kondangjaya | Perumahan | 400 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 1. Reject | Reject | TECHNICAL ISSUE | No Issue | Permit Issue | [43 empty] | NET-H-000250 FTTH Mutiara Nirwana
329 | Open Area Krajan - Kondangjaya | NET-H-000251 | FTTH Open Area Krajan - Kondangjaya | FTTH | QODN |  | Karawang | Karawang Timur | Kondangjaya | Open Area | 1000 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 1. Reject | Reject | TECHNICAL ISSUE | No Issue | Permit Issue | [43 empty] | NET-H-000251 FTTH Open Area Krajan - Kondangjaya
330 | Palm Kondang Asri | NET-H-000252 | FTTH Palm Kondang Asri | FTTH | QODN |  | Karawang | Karawang Timur | Kondangjaya | Perumahan | 800 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 1. Reject | Reject | TECHNICAL ISSUE | No Issue | Permit Issue | [43 empty] | NET-H-000252 FTTH Palm Kondang Asri
331 | FTTH Gg. Mushola RT 11 Rw 01 Kel. Kalideres | NET-H-000253 | FTTH Gg. Mushola RT 11 Rw 01 Kel. Kalideres | FTTH | QODN |  | Jakarta Barat | Kalideres | Kalideres | Open Area | 149 | 18 |  | NON-KSO | Nethome |  | INHOUSE | 3. Civil Work | 5. Waiting Implementation | Penjadwalan di Week 3 Januari | No Issue | Waiting Implementation | [7 empty] | On Progress |  | Toro | Free 3 Bulan |  | 2024-11-29 | TORO |  | 149 |  | 2024-12-07 | 2024-12-07 | 140 | M. Raul Habib | Done APD | Uploaded to Drive | NET-H-000253 FTTH Gg. Mushola RT 11 RW 01 Kel. Kalideres |  | BTS CENGKARENG | 1 | 3 | 18 | 12 |  |  | 1100 |  | 385 | [8 empty] | NET-H-000253 FTTH Gg. Mushola RT 11 Rw 01 Kel. Kalideres | 0 | 2024-12-03 | - | - | On Progress
332 | FTTH Jl. Benda 3 RT 13 Rw 01 Kel. Kalideres | NET-H-000254 | FTTH Jl. Benda 3 RT 13 Rw 01 Kel. Kalideres | FTTH | QODN |  | Jakarta Barat | Kalideres | Kalideres | Open Area | 118 | 15 | 15 | NON-KSO | Nethome |  | INHOUSE | 5. Ready For Service | 8. Area On Air | On Air | No Issue | On Air | [7 empty] | On Progress |  | Toro | Free 3 Bulan |  | 2024-12-02 | TORO |  | 118 |  | 2024-12-07 | 2024-12-07 | 118 | M. Raul Habib | Done APD | Uploaded to Drive | NET-H-000254 FTTH Jl. Benda 3 RT13 RW01 Kel. Kalideres |  | BTS CENGKARENG | 1 | 2 | 15 | 8 |  | 4 | 800 |  | 470 | [8 empty] | NET-H-000254 FTTH Jl. Benda 3 RT 13 Rw 01 Kel. Kalideres | 120 | 2024-12-27 | - | - | Done | Rinjani | 2024-12-27 | 2024-12-27 | 1943/SPLICE-RINJANI/FMI/XII/2024 | Done Splice | 2025-01-03 | 2025-01-15
333 | FTTH RW 01 Kel. Meruyung | NET-H-000255 | FTTH RW 01 Kel. Meruyung | FTTH | QODN |  | Kota Depok | Limo | Meruyung | Open Area | 600 | 0 |  | NON-KSO | Nethome |  | Fibeart | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | High compensation |  |  | Proses approval LPM dan RW, masih tahap negosiasi | [31 empty] | NET-H-000255 FTTH RW 01 Kel. Meruyung
334 | FTTH RW 02 Kel. Meruyung | NET-H-000256 | FTTH RW 02 Kel. Meruyung | FTTH | QODN |  | Kota Depok | Limo | Meruyung | Open Area | 600 | 0 |  | NON-KSO | Nethome |  | Fibeart | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | High compensation |  |  | Proses approval LPM dan RW, masih tahap negosiasi | [31 empty] | NET-H-000256 FTTH RW 02 Kel. Meruyung
335 | FTTH RW 03 Kel. Meruyung | NET-H-000257 | FTTH RW 03 Kel. Meruyung | FTTH | QODN |  | Kota Depok | Limo | Meruyung | Open Area | 600 | 0 |  | NON-KSO | Nethome |  | Fibeart | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | High compensation |  |  | Proses approval LPM dan RW, masih tahap negosiasi | [31 empty] | NET-H-000257 FTTH RW 03 Kel. Meruyung
336 | FTTH RW 04 Kel. Meruyung | NET-H-000258 | FTTH RW 04 Kel. Meruyung | FTTH | QODN |  | Kota Depok | Limo | Meruyung | Open Area | 600 | 0 |  | NON-KSO | Nethome |  | Fibeart | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | High compensation |  |  | Proses approval LPM dan RW, masih tahap negosiasi | [31 empty] | NET-H-000258 FTTH RW 04 Kel. Meruyung
337 | FTTH RT 07 RW 13 Kel. Duren Sawit | NET-H-000259 | FTTH RT 07 RW 13 Kel. Duren Sawit | FTTH | QODN |  | Jakarta Timur | Duren Sawit | Duren Sawit | Open Area | 50 | 12 | 12 | NON-KSO | Nethome |  | INHOUSE | 4. Electrical Work | 7. E2E Integration | Progress Splice Pelurusan Core | No Issue | Installation On Progress |  | Waiting Hasil Survey Jalur Feeder oleh Ridho MSP | [5 empty] | On Progress |  | MSP | Free 3 Bulan |  | 2024-12-03 | Ridho | Done | 94 |  | 2024-12-04 | 2024-12-04 | 97 | Aris Setiawan | Done APD | Uploaded to Drive | NET-H-000259 FTTH RT 07 RW 13 Kel. Duren Sawit |  | BTS Prima | 1 | 2 | 12 | 12 |  |  | 903 |  | 615 | [8 empty] | NET-H-000259 FTTH RT 07 RW 13 Kel. Duren Sawit | 96 | 2024-12-27 | - | - | Done | Rinjani | 2025-01-08 | 2025-01-09 | 0061/SPLICE-RINJANI/FMI/I/2025 | On Progress
338 | Open Area Warakas | NET-H-000260 | FTTH KELURAHAN WARAKAS | FTTH | QODN |  | Jakarta Utara | Tanjung Priok | Warakas | Open Area | 6000 | 0 |  | NON-KSO | Nethome |  | RSI (Rangkaian Signal Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | Menunggu sosialisasi all RT |  |  | visit done. RW minta waktu untuk sosialisasi ke semua RT akan di infolebih lanjut | [31 empty] | NET-H-000260 FTTH KELURAHAN WARAKAS
339 | Open Area Sungai Bambu | NET-H-000261 | FTTH KELURAHAN SUNGAI BAMBU | FTTH | QODN |  | Jakarta Utara | Tanjung Priok | Sungai Bambu | Open Area | 1700 | 0 |  | NON-KSO | Nethome |  | RSI (Rangkaian Signal Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | Menunggu sosialisasi all RT |  |  | visit done. RW minta waktu untuk sosialisasi ke semua RT akan di infolebih lanjut | [31 empty] | NET-H-000261 FTTH KELURAHAN SUNGAI BAMBU
340 | Open Area Bahari | NET-H-000262 | FTTH KELURAHAN BAHARI | FTTH | QODN |  | Jakarta Utara | Tanjung Priok | Tanjung Priok | Open Area | 1600 | 0 |  | NON-KSO | Nethome |  | RSI (Rangkaian Signal Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | Menunggu sosialisasi all RT |  |  | visit done. RW minta waktu untuk sosialisasi ke semua RT akan di infolebih lanjut | [31 empty] | NET-H-000262 FTTH KELURAHAN BAHARI
341 | Open Area Swasembada | NET-H-000263 | FTTH KELURAHAN SWASEMBADA | FTTH | QODN |  | Jakarta Utara | Tanjung Priok | Kebon Bawang | Open Area | 5000 | 0 |  | NON-KSO | Nethome |  | RSI (Rangkaian Signal Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | Menunggu sosialisasi all RT |  |  | Total 9 RW, 2 RW approved (RW 3 dan 10) RW 11 sudah kasih kompensasi, sisa RW masih negosiasi | [31 empty] | NET-H-000263 FTTH KELURAHAN SWASEMBADA
342 | Open Area Kebon Bawang | NET-H-000264 | FTTH KELURAHAN KEBON BAWANG | FTTH | QODN |  | Jakarta Utara | Tanjung Priok | Kebon Bawang | Open Area | 2000 | 0 |  | NON-KSO | Nethome |  | RSI (Rangkaian Signal Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | Menunggu sosialisasi all RT |  |  | Total 7 RW, 2 RW approved (RW 2 & 8), 2 RW sudah mengeluarkan angka kompensasi (RW 7 & 16), 1 RW reject (06), sisanya masih on progres negosiasi | [31 empty] | NET-H-000264 FTTH KELURAHAN KEBON BAWANG
343 | Griya Setu Permai 1 | NET-H-000265 | FTTH Griya Setu Permai 1 | FTTH | QODN |  | Kab. Bekasi | Setu | Ciledug | Perumahan | 1500 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Reject | Tidak mau ada penambahan jaringan |  |  | Warga dan pengurus tidak mau ada penambahan jaringan wifi | [31 empty] | NET-H-000265 FTTH Griya Setu Permai 1
344 | Griya Setu Permai 2 & 3 | NET-H-000266 | FTTH Griya Setu Permai 2 & 3 | FTTH | QODN |  | Kab. Bekasi | Setu | Ciledug | Perumahan | 2300 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | Menunggu sosialisasi all RT |  |  | Pengurus lagi bermusyawarah dengan rt untuk mensosialisasikan perijinan penambahan jaringan wifi baru | [31 empty] | NET-H-000266 FTTH Griya Setu Permai 2 & 3
345 | Mustika Gandaria | NET-H-000267 | FTTH Mustika Gandaria | FTTH | QODN |  | Kab. Bekasi | Setu | Ciledug | Perumahan | 800 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | Menunggu sosialisasi all RT |  |  | Menunggu hasil rapat dengan rt | [31 empty] | NET-H-000267 FTTH Mustika Gandaria
346 | Griya Bekasi Permai 1 & 2 | NET-H-000268 | FTTH Griya Bekasi Permai 1 & 2 | FTTH | QODN |  | Kab. Bekasi | Setu | Cibening | Perumahan | 4000 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | Menunggu sosialisasi all RT |  |  | Pengurus lagi bermusyawarah dengan rt untuk mensosialisasikan perijinan penambahan jaringan wifi baru | [31 empty] | NET-H-000268 FTTH Griya Bekasi Permai 1 & 2
347 | Perum Graha Asri Residence | NET-H-000269 | FTTH Perum Graha Asri Residence | FTTH | QODN |  | Kab. Bekasi | Cikarang Barat | Telajung | Perumahan | 1200 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Reject | Tidak mau ada penambahan jaringan |  |  | Pengurus menolak penambahan jaringan wifi baru | [31 empty] | NET-H-000269 FTTH Perum Graha Asri Residence
348 | Perum Mustika Media | NET-H-000270 | FTTH Perum Mustika Media | FTTH | QODN |  | Kab. Bekasi | Setu | Lubang Buaya | Perumahan | 600 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Reject | Tidak mau ada penambahan jaringan |  |  | Pengurus menolak penambahan jaringan wifi baru | [31 empty] | NET-H-000270 FTTH Perum Mustika Media
349 | Perumahan Green Harmoni | NET-H-000271 | FTTH Perumahan Green Harmoni | FTTH | QODN |  | Kab. Bekasi | Setu | Lubang Buaya | Perumahan | 800 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | Menunggu sosialisasi all RT |  |  | Pengurus developer sedang berkoordinasi dengan ketua rt & rw untuk mensosialisasikan penambahan jaringan wifi baru | [31 empty] | NET-H-000271 FTTH Perumahan Green Harmoni
350 | Perum Graha Mustika Media | NET-H-000272 | FTTH Perum Graha Mustika Media | FTTH | QODN |  | Kab. Bekasi | Setu | Lubang Buaya | Perumahan | 2000 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Reject | Tidak mau ada penambahan jaringan |  |  | Pengurus menolak penambahan jaringan wifi baru | [31 empty] | NET-H-000272 FTTH Perum Graha Mustika Media
351 | Graha Mustika Media Blok B | NET-H-000273 | FTTH Graha Mustika Media Blok A-D | FTTH | QODN |  | Kab. Bekasi | Setu | Lubang Buaya | Perumahan | 800 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Reject | Tidak mau ada penambahan jaringan |  |  | Pengurus menolak penambahan jaringan wifi baru | [31 empty] | NET-H-000273 FTTH Graha Mustika Media Blok A-D
352 | Grand Mutiara Gading | NET-H-000274 | FTTH Grand Mutiara Gading | FTTH | QODN |  | Kab. Bekasi | Cikarang Barat | Telajung | Perumahan | 2500 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | Menunggu sosialisasi all RT |  |  | Pengurus developer sedang berkoordinasi dengan ketua rt & rw untuk mensosialisasikan penambahan jaringan wifi baru | [31 empty] | NET-H-000274 FTTH Grand Mutiara Gading
353 | Griya Kenari Mas Cileungsi | NET-H-000275 | FTTH Griya Kenari Mas Cileungsi | FTTH | QODN |  | Kab. Bogor | Cileungsi | Cileungsi Kidul | Perumahan | 1800 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | Menunggu sosialisasi all RT |  |  | untuk penanaman tiang baru pihak lingkungan merasa keberatan mengingat banyak komplain dr warga, tapi akan di coba untuk di sosialisasikan kepada RT RT terkait jaringan FMI dan akan di infokan. | [31 empty] | NET-H-000275 FTTH Griya Kenari Mas Cileungsi
354 | Grand Harmoni Cileungsi | NET-H-000276 | FTTH Grand Harmoni Cileungsi | FTTH | QODN |  | Kab. Bogor | Cileungsi | Cileungsi Kidul | Perumahan | 400 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | NY Start Permit | [35 empty] | NET-H-000276 FTTH Grand Harmoni Cileungsi
355 | Perum Cileungsi Indah | NET-H-000277 | FTTH Perum Cileungsi Indah | FTTH | QODN |  | Kab. Bogor | Cileungsi | Cileungsi Kidul | Perumahan | 700 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | Menunggu sosialisasi all RT |  |  | Hasil pertemuan dengan Ketua RW, beliau akan menjadwal untuk sosialisasi langsung dengan RT RT pada saat Arisan RW | [31 empty] | NET-H-000277 FTTH Perum Cileungsi Indah
356 | Perum Pondok Damai & Duta Mekar | NET-H-000278 | FTTH Perum Pondok Damai & Duta Mekar | FTTH | QODN |  | Kab. Bogor | Cileungsi | Cileungsi Kidul | Perumahan | 1500 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Reject | Tidak bole tanam Tiang |  |  | Hasil pertemuan dengan Ketua RW, beliau menjelaskan bahwa pihak pengurus RW dan RT serta warga sudah musyawah dari beberapa tahun yg lalu bahwa di lingkungan RW 15 tidak mengijinkan untuk penanaman tiang Baru kecuali UG/penarikan kabel (sharing tiang) | [31 empty] | NET-H-000278 FTTH Perum Pondok Damai & Duta Mekar
357 | Open Area RT02/10 Kampung Cikalagan | NET-H-000279 | FTTH Open Area RT02/10 Kampung Cikalagan | FTTH | QODN |  | Kab. Bogor | Cileungsi | Cileungsi | Open Area | 400 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | NY Start Permit | [35 empty] | NET-H-000279 FTTH Open Area RT02/10 Kampung Cikalagan
358 | Open Area RW 07 & 14 Cileungsi Kidul | NET-H-000280 | FTTH Open Area RW 07 & 14 Cileungsi Kidul | FTTH | QODN |  | Kab. Bogor | Cileungsi | Cileungsi Kidul | Open Area | 1600 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | NY Start Permit | [35 empty] | NET-H-000280 FTTH Open Area RW 07 & 14 Cileungsi Kidul
359 | Open Area Dusun III & IV Cileungsi | NET-H-000281 | FTTH Open Area Dusun III & IV Cileungsi | FTTH | QODN |  | Kab. Bogor | Cileungsi | Cileungsi | Open Area | 2500 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | NY Start Permit | [35 empty] | NET-H-000281 FTTH Open Area Dusun III & IV Cileungsi
360 | Komplek Griya Parama | NET-H-000282 | FTTH Komplek Griya Parama | FTTH | QODN |  | Kab. Bogor | Cileungsi | Cileungsi Kidul | Perumahan | 500 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | NY Start Permit | [35 empty] | NET-H-000282 FTTH Komplek Griya Parama
361 | Open Area Dusun I Cileungsi Kidul | NET-H-000283 | FTTH Open Area Dusun I Cileungsi Kidul | FTTH | QODN |  | Kab. Bogor | Cileungsi | Cileungsi Kidul | Open Area | 2000 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | NY Start Permit | [35 empty] | NET-H-000283 FTTH Open Area Dusun I Cileungsi Kidul
362 | Komplek Cileungsi Permai | NET-H-000284 | FTTH Komplek Cileungsi Permai | FTTH | QODN |  | Kab. Bogor | Cileungsi | Cileungsi | Perumahan | 300 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Done approaching site | CH belum bisa di temui |  |  | Ketua RW 12 Bp. Supri tidak bisa bertemu dg beliau karena lagi pulang kampung jenguk Ibu nya yg sedang sakit. | [31 empty] | NET-H-000284 FTTH Komplek Cileungsi Permai
363 | Perumahan Cileungsi Hijau | NET-H-000285 | FTTH Perumahan Cileungsi Hijau | FTTH | QODN |  | Kab. Bogor | Cileungsi | Cileungsi Kidul | Perumahan | 1500 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Done approaching site | CH belum bisa di temui |  |  | Ketua RW dan kluarga keluar kota dari hari Sabtu, info dari Danru Keamanan Komplek Bp. Saheri. | [31 empty] | NET-H-000285 FTTH Perumahan Cileungsi Hijau
364 | Open Area Dusun II Cileungsi Kidul | NET-H-000286 | FTTH Open Area Dusun II Cileungsi Kidul | FTTH | QODN |  | Kab. Bogor | Cileungsi | Cileungsi Kidul | Open Area | 1800 | 0 |  | NON-KSO | Nethome |  | Magna Energi | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | NY Start Permit | [35 empty] | NET-H-000286 FTTH Open Area Dusun II Cileungsi Kidul
365 | RW 012 Jatirasa | NET-H-000287 | FTTH RW 12 KELURAHAN JATIRASA | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatirasa | Open Area | 300 | 0 |  | KSO-INTERNAL | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 2. OG Survey | Update Tagging Pole | No Issue | Survey On Process | [7 empty] | On Progress |  | Darto Marketing | Free 3 Bulan |  | 2024-12-05 | Arifudin | Done | [28 empty] | NET-H-000287 FTTH RW 12 KELURAHAN JATIRASA
366 | RW 002 Bojong Kulur | NET-H-000288 | FTTH RW 02 KELURAHAN BOJONG KULUR | FTTH | QODN |  | Kab. Bogor | Gunung Putri | Bojong Kulur | Open Area | 1500 | 0 |  | KSO-INTERNAL | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 2. OG Survey | Update Tagging Pole | No Issue | Survey On Process | [7 empty] | On Progress |  | Darto Marketing | Free 3 Bulan |  | 2024-12-06 | Arifudin | On Progress | [28 empty] | NET-H-000288 FTTH RW 02 KELURAHAN BOJONG KULUR
367 | RW 08 Margahayu | NET-H-000289 | FTTH RW 08 KELURAHAN MARGAHAYU | FTTH | QODN |  | Kota Bekasi | Bekasi Timur | Margahayu | Open Area | 2200 | 60 |  | KSO-INTERNAL | Nethome |  | INHOUSE | 3. Civil Work | 5. Waiting Implementation |  | No Issue | Waiting Implementation | [7 empty] | On Progress |  | Darto Marketing | Free 3 Bulan |  | 2024-12-10 | Ridho | Done | 483 |  | 2025-01-14 | 2025-01-15 | 483 | Aris Setiawan | Done APD | Uploaded to Drive | APD NET-H-000289 FTTH RW 08 KELURAHAN MARGAHAYU (483 HP) |  | BTS Hoki Margahayu | 4 | 10 | 60 | 45 |  | 4 | 4398 |  | 1314 | [8 empty] | NET-H-000289 FTTH RW 08 KELURAHAN MARGAHAYU
368 | RW 06 Margahayu | NET-H-000290 | FTTH RW 06 KELURAHAN MARGAHAYU | FTTH | QODN |  | Kota Bekasi | Bekasi Timur | Margahayu | Open Area | 800 | 0 |  | KSO-INTERNAL | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Survey On Process | [7 empty] | On Progress |  | Darto Marketing | Free 3 Bulan |  | 2024-12-07 | Arifudin | Done | [28 empty] | NET-H-000290 FTTH RW 06 KELURAHAN MARGAHAYU
369 | Bekasi Jaya Indah Mekarsari | NET-H-000291 | FTTH Bekasi Jaya Indah Mekarsari | FTTH | QODN |  | Kota Bekasi | Bekasi Timur | Bekasi Jaya | Perumahan | 700 | 0 |  | NON-KSO | Nethome |  | Nusantara Duasatu Telematika (N21) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | high cost permit (500 rb/tiang) |  |  | cluster Bekasi jaya indah mekarsari yang bersangkutan tetap meminta kompensasi sebesar lebih dari 500 ribu pertiang (berdasarkan penawaran provider lain sebelumnya) | [31 empty] | NET-H-000291 FTTH Bekasi Jaya Indah Mekarsari
370 | Bekasi Permai RW 15 | NET-H-000292 | FTTH Bekasi Permai RW 15 | FTTH | QODN |  | Kota Bekasi | Bekasi Timur | Bekasi Jaya | Perumahan | 700 | 0 |  | NON-KSO | Nethome |  | Nusantara Duasatu Telematika (N21) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | NY Start Permit | [35 empty] | NET-H-000292 FTTH Bekasi Permai RW 15
371 | Bekasi Jaya Indah Irigasi | NET-H-000293 | FTTH Bekasi Jaya Indah Irigasi | FTTH | QODN |  | Kota Bekasi | Bekasi Timur | Bekasi Jaya | Perumahan | 1500 | 0 |  | NON-KSO | Nethome |  | Nusantara Duasatu Telematika (N21) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Reject | Kabel sudah semrawut |  |  | cluster Bekasi jaya indah irigasi ada 2 RW , RW 11 dan RW 13 untuk RW 11 menolak karena keadaaan kabel yang sudah semrawut, | [31 empty] | NET-H-000293 FTTH Bekasi Jaya Indah Irigasi
372 | Teluk Angsan Permai | NET-H-000294 | FTTH Teluk Angsan Permai | FTTH | QODN |  | Kota Bekasi | Bekasi Timur | Bekasi Jaya | Perumahan | 2000 | 0 |  | NON-KSO | Nethome |  | Nusantara Duasatu Telematika (N21) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Done approaching site | CH belum bisa di temui |  |  | cluster teluk angsan permai blm bisa bertemu dengan rw setempat karena rw setempat hanya bisa ditemu di hari minggu | [31 empty] | NET-H-000294 FTTH Teluk Angsan Permai
373 | Perumahan Duren Jaya | NET-H-000295 | FTTH Perumahan Duren Jaya | FTTH | QODN |  | Kota Bekasi | Bekasi Timur | Duren Jaya | Perumahan | 3300 | 0 |  | NON-KSO | Nethome |  | Nusantara Duasatu Telematika (N21) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | NY Start Permit | [35 empty] | NET-H-000295 FTTH Perumahan Duren Jaya
374 | Perum BJI | NET-H-000296 | FTTH Perum BJI | FTTH | QODN |  | Kota Bekasi | Bekasi Timur | Duren Jaya | Perumahan | 1700 | 0 |  | NON-KSO | Nethome |  | Nusantara Duasatu Telematika (N21) | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | NY Start Permit | [35 empty] | NET-H-000296 FTTH Perum BJI
375 | RW 029 Cluster kirana cikarang | NET-H-000297 | FTTH RW 029 Cluster kirana cikarang | FTTH | QODN |  | Kab. Bekasi | Cibitung | Wanajaya | Perumahan | 300 | 0 |  | KSO-INTERNAL | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000297 FTTH RW 029 Cluster kirana cikarang
376 | FTTH RW 06, 07 & 08 Kel. Sukajadi | KSO-H-000050 | FTTH RW 06, 07 & 08 Kel. Sukajadi | FTTH | QODN |  | Kota Tangerang | Karawaci | Sukajadi | Open Area | 465 | 0 |  | KSO | KSO Tertutup Klien PT Swadaya Digital Informatika | Mardi +62 852 1848 9907 |  | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Survey On Process | [43 empty] | KSO-H-000050 FTTH RW 06, 07 & 08 Kel. Sukajadi
377 | RT 004 Kampung Darma Jaya | NET-H-000299 | FTTH RT 004 Kampung Darma Jaya | FTTH | QODN |  | Kab. Bekasi | Tambun Selatan | Setiadarma | Open Area | 170 | 23 |  | KSO-INTERNAL | Nethome |  | INHOUSE | 3. Civil Work | 5. Waiting Implementation |  | No Issue | Waiting Implementation | [7 empty] | On Progress |  | Darto Marketing | Free 3 Bulan |  |  |  |  | 185 |  | 2025-01-13 | 2025-01-13 | 185 | M. Raul Habib | Done APD | Uploaded to Drive | NET-H-000299 FTTH RT 004 Kampung Darma Jaya |  | BTS TAMBUN BARU | 1 | 3 | 23 | 19 |  |  | 2531 |  | 372 | [8 empty] | NET-H-000299 FTTH RT 004 Kampung Darma Jaya |  | 2025-01-14 |  |  | On Progress
378 | RW 008 Bojong Kulur | NET-H-000300 | FTTH RW 08 KELURAHAN BOJONG KULUR | FTTH | QODN |  | Kab. Bogor | Gunung Putri | Bojong Kulur | Open Area | 1000 | 0 |  | KSO-INTERNAL | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Sitac On Process | [7 empty] | On Progress |  | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000300 FTTH RW 08 KELURAHAN BOJONG KULUR
379 | RW 006 Ciketing Asem, Mustikajaya | NET-H-000301 | FTTH RW 06 Ciketing Asem Kel. Mustikajaya | FTTH | QODN |  | Kota Bekasi | Mustika Jaya | Musika Jaya | Open Area | 1500 | 0 |  | KSO-INTERNAL | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Sitac On Process | [7 empty] | On Progress |  | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000301 FTTH RW 06 Ciketing Asem Kel. Mustikajaya
380 | RW 003 Ciketing Asem, Mustikajaya | NET-H-000302 | FTTH RW 03 Ciketing Asem Kel. Mustikajaya | FTTH | QODN |  | Kota Bekasi | Mustika Jaya | Musika Jaya | Open Area | 2000 | 0 |  | KSO-INTERNAL | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Sitac On Process | [7 empty] | On Progress |  | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000302 FTTH RW 03 Ciketing Asem Kel. Mustikajaya
381 | RW 28 Perumahan Griya Bukit Jaya, Gunung Putri - Bogor | NET-H-000303 | FTTH Perumahan Griya Bukit Jaya RW 28 | FTTH | QODN |  | Kab. Bogor | Gunung Putri | Tlajung Udik | Perumahan | 500 | 94 |  | KSO-INTERNAL | Nethome |  | INHOUSE | 2. Survey, Sitac & Design | 4. APD Done |  | No Issue | Sitac On Process | [7 empty] | On Progress |  | Darto Marketing | Free 3 Bulan |  |  |  |  | 754 |  | 2024-12-18 | 2024-12-18 | 754 | Aris Setiawan | Done APD | Uploaded to Drive | APD NET-H-000303 FTTH Perumahan Griya Bukit Jaya RW 28 | Waiting WO , present by marketing | BTS Gunung Putri | 6 | 15 | 94 | 75 |  |  | 7263 |  | 120 | 958 | [7 empty] | NET-H-000303 FTTH Perumahan Griya Bukit Jaya RW 28
382 | FTTH Taman Narogong Indah RW.09 | KSO-H-000051 | FTTH Taman Narogong Indah RW.09 | FTTH | QODN |  | Kota Bekasi | Rawalumbu | Pengasinan | Perumahan | 535 | 0 |  | KSO | GKI |  | GKI | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | NY Start Permit | [35 empty] | KSO-H-000051 FTTH Taman Narogong Indah RW.09
383 | FTTH Taman Narogong Indah RW.21 | KSO-H-000052 | FTTH Taman Narogong Indah RW.21 | FTTH | QODN |  | Kota Bekasi | Rawalumbu | Pengasinan | Perumahan | 600 | 0 |  | KSO | GKI |  | GKI | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | NY Start Permit | [35 empty] | KSO-H-000052 FTTH Taman Narogong Indah RW.21
384 | FTTH Taman Narogong Indah RW.22 | KSO-H-000053 | FTTH Taman Narogong Indah RW.22 | FTTH | QODN |  | Kota Bekasi | Rawalumbu | Pengasinan | Perumahan | 700 | 0 |  | KSO | GKI |  | GKI | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | NY Start Permit | [35 empty] | KSO-H-000053 FTTH Taman Narogong Indah RW.22
385 | FTTH RW. 08 Kel. Cilebut Timur | NET-H-000307 | FTTH RW. 08 Kel. Cilebut Timur | FTTH | QODN |  | Kab. Bogor | Sukaraja | Cilebut Timur | Open Area | 323 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 2. OG Survey |  |  | Survey On Process | [43 empty] | NET-H-000307 FTTH RW. 08 Kel. Cilebut Timur
386 | FTTH RW. 01 Kel. Kedung Jaya | NET-H-000308 | FTTH RW. 01 Kel. Kedung Jaya | FTTH | QODN |  | Kota Bogor | Tanah Sereal | Kedung Jaya | Open Area | 384 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 2. OG Survey |  |  | Survey On Process | [43 empty] | NET-H-000308 FTTH RW. 01 Kel. Kedung Jaya
387 | Kelurahan Serpong RW 04 - Cipeucang 1 | NET-H-000309 | FTTH RW 04 Kelurahan Serpong - Cipeucang 1 | FTTH | QODN |  | Tangerang Selatan | Serpong | Serpong | Perumahan | 700 | 84 | 84 | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 4. Electrical Work | 7. E2E Integration | Progress Penarikan Kabel Precon & ODN | No Issue | Installation On Progress | [7 empty] | On Progress |  | Ridho |  |  |  | Ridho |  | 666 |  | 2024-12-21 | 2024-12-21 | 666 | Muchamad Rivai | APD Done | Uploaded to Drive | APD NET-H-000309 FTTH RW 04 Kelurahan Serpong - Cipeucang 1 (666 HP) |  | BTS Doddy | 3 | 12 | 84 | 69 |  |  | 6398 |  | 820 | [8 empty] | NET-H-000309 FTTH RW 04 Kelurahan Serpong - Cipeucang 1 | 672 | 2024-12-20 | 2024-12-21 | 0010/SVYSPL-KJI-FMI/XII/2024 | On Progress | Belacom | 2025-01-06 | 2025-01-07 | 007/SPLICE-BELACOM/FMI/I/2025 | Done | 2025-01-13 | On Progress
388 | Kelurahan Kademangan RW 03 - Cipeucang 2 | NET-H-000310 | FTTH RW 03 Kelurahan Kademangan - Cipeucang 2 | FTTH | QODN |  | Tangerang Selatan | Setu | Kademangan | Open Area | 600 | 112 | 42 | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 3. Civil Work | 6. Pole & ODN Instalation | Progress Penarikan Kabel FO & Tiang | No Issue | Installation On Progress | [7 empty] | On Progress |  |  |  |  | 2024-12-25 | Ridho | Done | 913 |  | 2024-12-24 | 2024-12-24 | 913 | Aris Setiawan | Done APD | Uploaded to Drive | APD NET-H-000310 FTTH RW 03 Kelurahan Kademangan - Cipeucang 2 (913 HP) |  | BTS Doddy | 6 | 16 | 112 | 73 |  |  | 6763 |  | 1039 |  |  | 1078 | [5 empty] | NET-H-000310 FTTH RW 03 Kelurahan Kademangan - Cipeucang 2 | 336 | 2024-12-24 | 2024-12-24 | 0011/SVYSPL-KJI-FMI/XII/2024 | On Progress | Belacom | 2025-01-06 | 2025-01-07 | 008/SPLICE-BELACOM/FMI/I/2025 | On Progress
389 | Kelurahan Kademangan RW 03 - Cipeucang 3 | NET-H-000311 | FTTH RW 03 Kelurahan Kademangan - Cipeucang 3 | FTTH | QODN |  | Tangerang Selatan | Setu | Kademangan | Open Area | 400 | 52 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 3. Civil Work | 6. Pole & ODN Instalation | Prepare Material | No Issue | Installation On Progress | [7 empty] | On Progress | [5 empty] | Ridho |  | 412 |  | 2024-12-24 | 2024-12-24 | 412 | Muchamad Rivai | Done APD | Uploaded to Drive | APD NET-H-000311 FTTH RW 03 Kelurahan Kademangan - Cipeucang 3 (412 HP) |  | BTS Doddy | 2 | 8 | 52 | 58 |  |  | 4706 |  | 970 | [8 empty] | NET-H-000311 FTTH RW 03 Kelurahan Kademangan - Cipeucang 3 | 0 | 2024-12-24 | 2024-12-24 | 0012/SVYSPL-KJI-FMI/XII/2024 | On Progress | KJI | 2024-12-24 | 2024-12-24 | 0012/SVYSPL-KJI-FMI/XII/2024 | On Progress
390 | Perumahan Bumi Sawangan Indah 2 | KSO-H-000059 | FTTH Perumahan Bumi Sawangan Indah 2 | FTTH | QODN |  | Kota Depok | Sawangan | Pengasinan | Perumahan | 200 | 91 |  | KSO | Nethome |  |  | 2. Survey, Sitac & Design | 4. APD Done |  | No Issue | Sitac On Process | [7 empty] | On Progress |  | Darto Marketing | Free 3 Bulan |  |  |  |  | 735 |  | 2025-01-15 | 2025-01-15 | 729 | M. Raul Habib | Done APD | Uploaded to Drive | NET-H-000312 FTTH Bumi sawangan Indah 2 |  | BTS PLERED SAWANGAN | 4 | 12 | 91 | 66 |  | 2 | 6145 |  | 964 | 1084 | [7 empty] | KSO-H-000059 FTTH Perumahan Bumi Sawangan Indah 2
391 | RW 001 Cipayung Ciputat | NET-H-000313 | FTTH RW 001 Kel. Cipayung Ciputat | FTTH | QODN |  | Tangerang Selatan | Ciputat | Cipayung | Open Area | 400 | 0 |  | KSO-INTERNAL | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000313 FTTH RW 001 Kel. Cipayung Ciputat
392 | RT 002 Jatiluhur | NET-H-000314 | FTTH RT 002 RW 07 Kel. Jatiluhur | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatiluhur | Open Area | 300 | 0 |  | KSO-INTERNAL | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000314 FTTH RT 002 RW 07 Kel. Jatiluhur
393 | RW 08 Komplek Depsos Cikarang Barat | NET-H-000315 | FTTH RW 08 Komplek Depsos Kel. Telaga Asih | FTTH | QODN |  | Kab. Bekasi | Cikarang Barat | Telaga Asih | Perumahan | 1000 | 0 |  | KSO-INTERNAL | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000315 FTTH RW 08 Komplek Depsos Kel. Telaga Asih
394 | RW 03 Pengasinan | NET-H-000316 | FTTH RW 03 Kelurahan Pengasinan | FTTH | QODN |  | Kota Bekasi | Rawalumbu | Pengasinan | Open Area | 1000 | 0 |  | KSO-INTERNAL | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000316 FTTH RW 03 Kelurahan Pengasinan
395 | RW 07 Kampung Jatisari | NET-H-000317 | FTTH RW 07 Kampung Jatisari | FTTH | QODN |  | Kota Bekasi | Jatiasih | Jatisari | Open Area | 1200 | 0 |  | KSO-INTERNAL | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [9 empty] | M. Raul Habib | [22 empty] | NET-H-000317 FTTH RW 07 Kampung Jatisari
396 | Perumahan GCC - Cinity | KSO-H-000057 | FTTH Perumahan GCC - Cinity | FTTH | QODN |  | Kab. Bekasi | Cikarang Utara | Karangraharja | Perumahan | 4700 | 0 |  | KSO | Cinity |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 2. OG Survey |  |  | Sitac On Process | [24 empty] | NET-H-000318 | [18 empty] | KSO-H-000057 FTTH Perumahan GCC - Cinity
397 | Perumahan Cluster Sakura - Cinity | KSO-H-000058 | FTTH Perumahan Cluster Sakura - Cinity | FTTH | QODN |  | Kab. Bekasi | Cikarang Utara | Karangraharja | Perumahan | 2500 | 0 |  | KSO | Cinity |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 2. OG Survey |  |  | Sitac On Process | [24 empty] | NET-H-000319 | [18 empty] | KSO-H-000058 FTTH Perumahan Cluster Sakura - Cinity
398 | FTTH RW01 Ujung Menteng | NET-H-000422 | FTTH RW01 Ujung Menteng | FTTH | QODN |  | Jakarta Timur | Cakung | Ujung Menteng | Open Area | 800 | 78 |  | KSO-INTERNAL | KSO Internal |  | RPS (Rizki Prima Sakti) | 3. Civil Work | 6. Pole & ODN Instalation | Prepare Material | No Issue | Installation On Progress | [7 empty] | On Progress |  | Darto Marketing | [5 empty] | 659 |  | 2024-12-19 | 2024-12-19 | 659 | M. Raul Habib | Done APD | Uploaded to Drive | KSO-H-000054 KSO FTTH RW01 Ujung Menteng |  | BTS Ujung Menteng | 6 | 12 | 78 |  |  |  | 6533 |  | 1199 | 367 | [7 empty] | NET-H-000422 FTTH RW01 Ujung Menteng | 0 | 2024-12-27 | 2025-01-13 | - | On Progress
399 | RW26 Griya Bukit Jaya, Tlajung Udik , Kec. Gunung Putri - Bogor | NET-H-000320 | FTTH Perumahan Griya Bukit Jaya RW 26 | FTTH | QODN |  | Kab. Bogor | Gunung Putri | Tlajung Udik | Perumahan | 250 | 43 |  | KSO-INTERNAL | Nethome |  |  | 2. Survey, Sitac & Design | 4. APD Done |  |  | Sitac On Process | [7 empty] | On Progress |  | Darto Marketing | Free 3 Bulan |  |  |  |  | 346 |  | 2025-01-06 | 2025-01-06 | 346 | Muchamad Rivai | Done APD | Uploaded to Drive | APD NET-H-000320 FTTH Perumahan Griya Bukit Jaya RW 26 (346 HP) |  | BTS Gunung Putri | 2 | 6 | 43 | 53 |  |  | 3781 |  | 620 | [8 empty] | NET-H-000320 FTTH Perumahan Griya Bukit Jaya RW 26
400 | RW29 Griya Bukit Jaya, Tlajung Udik , Kec. Gunung Putri - Bogor | NET-H-000321 | FTTH Perumahan Griya Bukit Jaya RW 29 | FTTH | QODN |  | Kab. Bogor | Gunung Putri | Tlajung Udik | Perumahan | 250 | 34 |  | KSO-INTERNAL | Nethome |  |  | 2. Survey, Sitac & Design | 4. APD Done |  |  | Sitac On Process | [7 empty] | On Progress |  | Darto Marketing | Free 3 Bulan |  |  |  |  | 273 |  | 2025-01-06 | 2025-01-06 | 273 | Muchamad Rivai | Done APD | Uploaded to Drive | APD NET-H-000321 FTTH Perumahan Griya Bukit Jaya RW 29 (273 HP) |  | BTS Gunung Putri | 2 | 6 | 34 | 37 |  |  | 2834 |  | 680 | [8 empty] | NET-H-000321 FTTH Perumahan Griya Bukit Jaya RW 29
401 | RW 03 Desa Wanaherang, Kecamatan Gunung Putri - Bogor | NET-H-000322 | FTTH RW 03 Desa Wanaherang | FTTH | QODN |  | Kab. Bogor | Gunung Putri | Wanaherang | Open Area | 750 | 22 |  | KSO-INTERNAL | Nethome |  | INHOUSE | 3. Civil Work | 5. Waiting Implementation |  | No Issue | Waiting Implementation | [7 empty] | On Progress |  | Darto Marketing | Free 3 Bulan |  |  |  |  | 216 |  | 2025-01-07 | 2025-01-07 | 216 | Muchamad Rivai | Done APD | Uploaded to Drive | APD NET-H-000322 FTTH RW 03 Desa Wanaherang (216 HP) |  | BTS Cileungsi | 2 | 5 | 22 | 30 |  |  | 2406 |  | 855 | [8 empty] | NET-H-000322 FTTH RW 03 Desa Wanaherang |  | 2025-01-13 | 2025-01-13 | 0002/SVYSPL-RPS/FMI/I/2025 | On Progress
402 | RW 010 Mekarjaya Depok | NET-H-000323 | FTTH RW 010 Mekarjaya Depok | FTTH | QODN |  | Depok | Sukmajaya | Mekar Jaya | Open Area | 678 |  |  | KSO-INTERNAL | Nethome |  |  | 2. Survey, Sitac & Design | 2. OG Survey |  | No Issue | Sitac On Process | [7 empty] | On Progress |  | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000323 FTTH RW 010 Mekarjaya Depok
403 | RW 02 Villa Gading Harapan ,Babelan | KSO-H-000055 | FTTH RW 02 Villa Gading Harapan ,Babelan | FTTH | QODN |  | Kab. Bekasi | Babelan | Babelan | Open Area | 600 | 55 |  | KSO | KSO Tertutup Klien IHAI Network | Ahmad / +62 812-8347-8799 |  | 2. Survey, Sitac & Design | 4. APD Done | Overlay dengan plan perluasan KSO Pak Sarno |  | Sitac On Process | [7 empty] | On Progress |  |  |  |  | 2024-12-22 | Haikal | Done | 575 |  | 2025-01-16 |  | 575 | Aris Setiawan | Done APD | Uploaded to Drive | APD KSO-H-000055 FTTH RW 02 Villa Gading Harapan ,Babelan |  | BTS Babelan FO & WLL (BBLBKS) | 4 | 10 | 55 | 79 |  |  | 5040 |  | 1053 | [8 empty] | KSO-H-000055 FTTH RW 02 Villa Gading Harapan ,Babelan
404 | ARSA Residence Karawang | KSO-H-000056 | FTTH ARSA Residence Karawang | FTTH | QODN |  | Karawang | Karawang Timur | Karawang Wetan | Perumahan | 400 |  |  | KSO | KSO Tertutup Klien KDM.NET | Bapak deden +62 878-7910-5552 |  | 2. Survey, Sitac & Design | 2. OG Survey |  |  | Sitac On Process | [43 empty] | KSO-H-000056 FTTH ARSA Residence Karawang
405 | Kelurahan Serpong RT 05 RW 04 - Cipeucang 1 | NET-H-000324 | FTTH RT 05 RW 04 Kelurahan Serpong - Cipeucang 4 | FTTH | QODN |  | Tangerang Selatan | Serpong | Serpong | Perumahan | 200 | 11 | 11 | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 4. Electrical Work | 7. E2E Integration | Prepare Material | No Issue | Installation On Progress | [7 empty] | On Progress |  |  |  |  | 2024-12-28 | Ridho | Done | 97 |  | 2024-12-30 | 2024-12-30 | 87 | Aris Setiawan | Done APD | Uploaded to Drive | APD NET-H-000324 FTTH RT 05 RW 04 Kelurahan Serpong - Cipeucang 4 (87 HP) |  | BTS Doddy | 1 | 2 | 11 | 13 |  |  | 928 |  | 199 | [8 empty] | NET-H-000324 FTTH RT 05 RW 04 Kelurahan Serpong - Cipeucang 4 | 88 | 2024-12-30 | 2024-12-31 | 0014/SVYSPL-KJI-FMI/XII/2024 | On Progress | KJI | 2024-12-30 | 2024-12-31 | 0014/SVYSPL-KJI-FMI/XII/2024 | On Progress
406 | Open Arean Cibubur RW14 | NET-H-000325 | FTTH RW 14 Kelurahan Cibubur | FTTH | QODN |  | Jakarta Timur | Ciracas | Cibubur | Open Area | 300 |  |  | NON-KSO | Nethome |  | SBMU (Sembilan Belas Multi Usaha) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Cibubur Baru (CBJJKT) |  | Sitac On Process | [7 empty] | Reject | Tidak diperbolehkan ada jaringan Wifi baru |  |  | Sudah terlalu banyak provider, tiang dan kabel sudan semrawut | [31 empty] | NET-H-000325 FTTH RW 14 Kelurahan Cibubur
407 | Open Arean Cibubur RW13 | NET-H-000326 | FTTH RW 13 Kelurahan Cibubur | FTTH | QODN |  | Jakarta Timur | Ciracas | Cibubur | Open Area | 300 |  |  | NON-KSO | Nethome |  | SBMU (Sembilan Belas Multi Usaha) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Cibubur Baru (CBJJKT) |  | Sitac On Process | [7 empty] | Reject | Tidak diperbolehkan ada jaringan Wifi baru |  |  | Sudah terlalu banyak provider, tiang dan kabel sudan semrawut | [31 empty] | NET-H-000326 FTTH RW 13 Kelurahan Cibubur
408 | Open Arean Cibubur RW05 | NET-H-000327 | FTTH RW 05 Kelurahan Cibubur | FTTH | QODN |  | Jakarta Timur | Ciracas | Cibubur | Open Area | 700 |  |  | NON-KSO | Nethome |  | SBMU (Sembilan Belas Multi Usaha) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Cibubur Baru (CBJJKT) |  | Sitac On Process | [7 empty] | Reject | Tidak diperbolehkan ada jaringan Wifi baru |  |  | Sudah terlalu banyak provider, tiang dan kabel sudan semrawut | [31 empty] | NET-H-000327 FTTH RW 05 Kelurahan Cibubur
409 | Komplek Angkatan Darat Cibubur | NET-H-000328 | FTTH Komplek Angkatan Darat Cibubur | FTTH | QODN |  | Jakarta Timur | Ciracas | Cibubur | Perumahan | 1000 |  |  | NON-KSO | Nethome |  | SBMU (Sembilan Belas Multi Usaha) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Cibubur Baru (CBJJKT) |  | Sitac On Process | [7 empty] | Reject | Tidak diperbolehkan ada jaringan Wifi baru |  |  | Karena issue dari provider lain dan ada komplen dari Kodam kepada Ketua RW dan RT untuk menolak pembangunan jaringan baru di Wilayahnya. | [31 empty] | NET-H-000328 FTTH Komplek Angkatan Darat Cibubur
410 | Open Arean Cibubur RW09 | NET-H-000329 | FTTH RW 09 Kelurahan Cibubur | FTTH | QODN |  | Jakarta Timur | Ciracas | Cibubur | Open Area | 600 |  |  | NON-KSO | Nethome |  | SBMU (Sembilan Belas Multi Usaha) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Cibubur Baru (CBJJKT) |  | Sitac On Process | [7 empty] | Reject | Tidak diperbolehkan ada jaringan Wifi baru |  |  | Sudah terlalu banyak provider, tiang dan kabel sudan semrawut | [31 empty] | NET-H-000329 FTTH RW 09 Kelurahan Cibubur
411 | Open Area Mekarsari RW11 | NET-H-000330 | FTTH RW 11 Kelurahan Mekarsari | FTTH | QODN |  | Kota Depok | Cimanggis | MekarSari | Open Area | 800 |  |  | NON-KSO | Nethome |  | SBMU (Sembilan Belas Multi Usaha) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Cibubur Baru (CBJJKT) |  | Sitac On Process | [7 empty] | Reject | Tidak diperbolehkan ada jaringan Wifi baru |  |  | karena ada issue dari provider lain yang membuat para warga komplen dan sudah terlalu banyak kabel yang semrawut. | [31 empty] | NET-H-000330 FTTH RW 11 Kelurahan Mekarsari
412 | Open Area Harjamukti RW03 | NET-H-000331 | FTTH RW 03 Kelurahan Harjamukti | FTTH | QODN |  | Kota Depok | Cimanggis | Harjamukti | Open Area | 800 |  |  | NON-KSO | Nethome |  | SBMU (Sembilan Belas Multi Usaha) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Cibubur Baru (CBJJKT) |  | Sitac On Process | [7 empty] | Done Approaching site | CH masih belum bisa di temui |  |  | SPK done release | [31 empty] | NET-H-000331 FTTH RW 03 Kelurahan Harjamukti
413 | Open Area Ciriung Tengah | NET-H-000332 | FTTH Open Area Ciriung Tengah | FTTH | QODN |  | Kab. Bogor | Cibinong | Ciriung | Open Area | 1500 |  |  | NON-KSO | Nethome |  | INTEGRA LINTAS TEKNOLOGI ( INTEGRA ) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Mayor Oking (MOKBGR) |  | Sitac On Process | [7 empty] | NY Start Permit | [35 empty] | NET-H-000332 FTTH Open Area Ciriung Tengah
414 | Open Area Ciriung Barat | NET-H-000333 | FTTH Open Area Ciriung Barat | FTTH | QODN |  | Kab. Bogor | Cibinong | Ciriung | Open Area | 800 |  |  | NON-KSO | Nethome |  | INTEGRA LINTAS TEKNOLOGI ( INTEGRA ) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Mayor Oking (MOKBGR) |  | Sitac On Process | [7 empty] | NY Start Permit | [35 empty] | NET-H-000333 FTTH Open Area Ciriung Barat
415 | Open Area Ciriung Timur | NET-H-000334 | FTTH Open Area Ciriung Timur | FTTH | QODN |  | Kab. Bogor | Cibinong | Ciriung | Open Area | 500 |  |  | NON-KSO | Nethome |  | INTEGRA LINTAS TEKNOLOGI ( INTEGRA ) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Mayor Oking (MOKBGR) |  | Sitac On Process | [7 empty] | NY Start Permit | [35 empty] | NET-H-000334 FTTH Open Area Ciriung Timur
416 | Komplek Taman Permata Palem | NET-H-000335 | FTTH Komplek Taman Permata Palem | FTTH | QODN |  | Kab. Bogor | Cibinong | Cirimekar | Perumahan | 150 |  |  | NON-KSO | Nethome |  | INTEGRA LINTAS TEKNOLOGI ( INTEGRA ) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Mayor Oking (MOKBGR) |  | Sitac On Process | [7 empty] | NY Start Permit | [35 empty] | NET-H-000335 FTTH Komplek Taman Permata Palem
417 | Open Area Cirimekar | NET-H-000336 | FTTH Open Area Cirimekar | FTTH | QODN |  | Kab. Bogor | Cibinong | Cirimekar | Open Area | 1200 |  |  | NON-KSO | Nethome |  | INTEGRA LINTAS TEKNOLOGI ( INTEGRA ) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Mayor Oking (MOKBGR) |  | Sitac On Process | [7 empty] | Sosialisasi Permit | Tidak bole tanam tiang |  |  | ada 2 perumahan di boundary, need Re Funnel.dan hanya bisa ambil Homepass dijalan utama, dikarenakan akses gang yang sempit tidak memungkinkan untuk tanam tiang baru. | [31 empty] | NET-H-000336 FTTH Open Area Cirimekar
418 | Taman Kenari Jagorawi | NET-H-000337 | FTTH Taman Kenari Jagorawi | FTTH | QODN |  | Kab. Bogor | Citeureup | Puspasari | Perumahan | 500 |  |  | NON-KSO | Nethome |  | INTEGRA LINTAS TEKNOLOGI ( INTEGRA ) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Mayor Oking (MOKBGR) |  | Sitac On Process | [7 empty] | NY Start Permit | [35 empty] | NET-H-000337 FTTH Taman Kenari Jagorawi
419 | Komplek Graha Puspasari 1 | NET-H-000338 | FTTH Komplek Graha Puspasari 1 | FTTH | QODN |  | Kab. Bogor | Citeureup | Puspasari | Perumahan | 100 |  |  | NON-KSO | Nethome |  | INTEGRA LINTAS TEKNOLOGI ( INTEGRA ) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Mayor Oking (MOKBGR) |  | Sitac On Process | [7 empty] | Sosialisasi Permit | Tidak bole tanam tiang |  |  | pengurus sudah tidak mengizinkan penambahan jaringan dikarenakan sudah ada 4 provider yang terpasang dan kebanyakan warga juga sudah komplain, total ada 1 RW dan 4 RT. | [31 empty] | NET-H-000338 FTTH Komplek Graha Puspasari 1
420 | Komplek Graha Puspasari 2 | NET-H-000339 | FTTH Komplek Graha Puspasari 2 | FTTH | QODN |  | Kab. Bogor | Citeureup | Puspasari | Perumahan | 100 |  |  | NON-KSO | Nethome |  | INTEGRA LINTAS TEKNOLOGI ( INTEGRA ) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Mayor Oking (MOKBGR) |  | Sitac On Process | [7 empty] | Sosialisasi Permit | Menunggu jadwal sosialisasi |  |  | Sudah bertemu dengan kordinator pengurus komplek, dan beliau sangat welcome untuk menjelaskan ke ketua pengurus komplek terkait penambahan jaringan FMI di wilayah tsb. | [31 empty] | NET-H-000339 FTTH Komplek Graha Puspasari 2
421 | Open Area Puspasari | NET-H-000340 | FTTH Open Area Puspasari | FTTH | QODN |  | Kab. Bogor | Citeureup | Puspasari | Open Area | 1000 |  |  | NON-KSO | Nethome |  | INTEGRA LINTAS TEKNOLOGI ( INTEGRA ) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Mayor Oking (MOKBGR) |  | Sitac On Process | [7 empty] | Sosialisasi Permit | Tidak bole tanam tiang |  |  | Hanya bisa di ambil di akses jalan utama, dikarenakan banyak akses gang sempit yang tidak memungkinkan untuk penanaman tiang | [31 empty] | NET-H-000340 FTTH Open Area Puspasari
422 | RW 006 Bojong Kulur | NET-H-000341 | FTTH RW 006 Bojong Kulur | FTTH | QODN |  | Kab. Bogor | Gunung Putri | Bojong Kulur | Open Area | 600 |  |  | KSO-INTERNAL | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan |  |  |  |  | 210 |  |  |  |  | M. Raul Habib | [22 empty] | NET-H-000341 FTTH RW 006 Bojong Kulur
423 | RW 003 Pengasinan Rawalumbu | NET-H-000342 | FTTH RW 003 Kelurahan Pengasinan | FTTH | QODN |  | Kota Bekasi | Rawalumbu | Pengasinan | Open Area | 1000 |  |  | KSO-INTERNAL | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000342 FTTH RW 003 Kelurahan Pengasinan
424 | Kel. Kalijaga RW 05&06 | NET-H-000343 | FTTH Kel. Kalijaga RW 05&06 | FTTH | QODN |  | Kota Cirebon | Hajarmukti | Kalijaga | Open Area | 400 |  |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel POP Vihara Cirebon Fase 2 |  | Sitac On Process | [43 empty] | NET-H-000343 FTTH Kel. Kalijaga RW 05&06
425 | Grand Taman ANggrek Suci | NET-H-000344 | FTTH Grand Taman Anggrek Suci | FTTH | QODN |  | Kab. Cirebon | Mundu | Banjarwangunan | Perumahan | 500 |  |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel POP Vihara Cirebon Fase 2 |  | Sitac On Process | [43 empty] | NET-H-000344 FTTH Grand Taman Anggrek Suci
426 | Komplek Grand Metro Pamengkang | NET-H-000345 | FTTH Komplek Grand Metro Pamengkang | FTTH | QODN |  | Kab. Cirebon | Mundu | Pamengkang | Perumahan | 400 |  |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel POP Vihara Cirebon Fase 2 |  | Sitac On Process | [43 empty] | NET-H-000345 FTTH Komplek Grand Metro Pamengkang
427 | Perumahan Taman Hasna | NET-H-000346 | FTTH Perumahan Taman Hasna | FTTH | QODN |  | Kab. Cirebon | Mundu | Pamengkang | Perumahan | 600 |  |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel POP Vihara Cirebon Fase 2 |  | Sitac On Process | [43 empty] | NET-H-000346 FTTH Perumahan Taman Hasna
428 | Trusmiland Pamengkang | NET-H-000347 | FTTH Trusmiland Pamengkang | FTTH | QODN |  | Kab. Cirebon | Mundu | Pamengkang | Perumahan | 800 |  |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel POP Vihara Cirebon Fase 2 |  | Sitac On Process | [43 empty] | NET-H-000347 FTTH Trusmiland Pamengkang
429 | Open Area Pamengkang RW01&04 | NET-H-000348 | FTTH Open Area Pamengkang RW01&04 | FTTH | QODN |  | Kab. Cirebon | Mundu | Pamengkang | Open Area | 700 |  |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel POP Vihara Cirebon Fase 2 |  | Sitac On Process | [43 empty] | NET-H-000348 FTTH Open Area Pamengkang RW01&04
430 | Open Area Pamengkang RW05-07 | NET-H-000349 | FTTH Open Area Pamengkang RW05-07 | FTTH | QODN |  | Kab. Cirebon | Mundu | Pamengkang | Open Area | 800 |  |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel POP Vihara Cirebon Fase 2 |  | Sitac On Process | [43 empty] | NET-H-000349 FTTH Open Area Pamengkang RW05-07
431 | Komplek Green Pamengkang | NET-H-000350 | FTTH Komplek Green Pamengkang | FTTH | QODN |  | Kab. Cirebon | Mundu | Pamengkang | Perumahan | 200 |  |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel POP Vihara Cirebon Fase 2 |  | Sitac On Process | [43 empty] | NET-H-000350 FTTH Komplek Green Pamengkang
432 | Graha Keandra Pamengkang | NET-H-000351 | FTTH Graha Keandra Pamengkang | FTTH | QODN |  | Kab. Cirebon | Mundu | Pamengkang | Perumahan | 200 |  |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel POP Vihara Cirebon Fase 2 |  | Sitac On Process | [43 empty] | NET-H-000351 FTTH Graha Keandra Pamengkang
433 | Dforest Harmoni Pamengkang | NET-H-000352 | FTTH Dforest Harmoni Pamengkang | FTTH | QODN |  | Kab. Cirebon | Mundu | Pamengkang | Perumahan | 200 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel POP Vihara Cirebon Fase 2 |  | Sitac On Process | [43 empty] | NET-H-000352 FTTH Dforest Harmoni Pamengkang
434 | Open Area Setupatok RW 02-06 | NET-H-000353 | FTTH Open Area Setupatok RW 02-06 | FTTH | QODN |  | Kab. Cirebon | Mundu | Setupatok | Open Area | 1300 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 2. OG Survey | Funnel POP Vihara Cirebon Fase 2 |  | Sitac On Process | [43 empty] | NET-H-000353 FTTH Open Area Setupatok RW 02-06
435 | Open Area Argasunya RW05&06 | NET-H-000354 | FTTH Open Area Argasunya RW05&06 | FTTH | QODN |  | Kota Cirebon | Hajarmukti | Argasunya | Open Area | 600 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel POP Vihara Cirebon Fase 2 |  | Sitac On Process | [43 empty] | NET-H-000354 FTTH Open Area Argasunya RW05&06
436 | Open Area Argasunya RW 01-03 | NET-H-000355 | FTTH Open Area Argasunya RW 01-03 | FTTH | QODN |  | Kota Cirebon | Hajarmukti | Argasunya | Open Area | 700 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel POP Vihara Cirebon Fase 2 |  | Sitac On Process | [43 empty] | NET-H-000355 FTTH Open Area Argasunya RW 01-03
437 | Open Area Argasunya RW04 | NET-H-000356 | FTTH Open Area Argasunya RW04 | FTTH | QODN |  | Kota Cirebon | Hajarmukti | Argasunya | Open Area | 450 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel POP Vihara Cirebon Fase 2 |  | Sitac On Process | [43 empty] | NET-H-000356 FTTH Open Area Argasunya RW04
438 | Open Area Drajat RW01 | NET-H-000357 | FTTH Open Area Drajat RW01 | FTTH | QODN |  | Kota Cirebon | Kesambi | Drajat | Open Area | 300 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel POP Vihara Cirebon Fase 2 |  | Sitac On Process | [43 empty] | NET-H-000357 FTTH Open Area Drajat RW01
439 | Open Area Drajat RW 02 03 05 & 07 | NET-H-000358 | FTTH Open Area Drajat RW 02 03 05 & 07 | FTTH | QODN |  | Kota Cirebon | Kesambi | Drajat | Open Area | 500 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel POP Vihara Cirebon Fase 2 |  | Sitac On Process | [43 empty] | NET-H-000358 FTTH Open Area Drajat RW 02 03 05 & 07
440 | Open Area Drajat RW 04 & 06 | NET-H-000359 | FTTH Open Area Drajat RW 04 & 06 | FTTH | QODN |  | Kota Cirebon | Kesambi | Drajat | Open Area | 450 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel POP Vihara Cirebon Fase 2 |  | Sitac On Process | [43 empty] | NET-H-000359 FTTH Open Area Drajat RW 04 & 06
441 | Open Area Drajat RW 08 & 09 | NET-H-000360 | FTTH Open Area Drajat RW 08 & 09 | FTTH | QODN |  | Kota Cirebon | Kesambi | Drajat | Open Area | 500 | 0 |  | NON-KSO | Nethome |  | KJI (Khatulistiwa Jaringan Indonesia) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel POP Vihara Cirebon Fase 2 |  | Sitac On Process | [43 empty] | NET-H-000360 FTTH Open Area Drajat RW 08 & 09
442 | RW 01 Sepanjang jaya | NET-H-000361 | FTTH RW 01 Kel. Sepanjang jaya | FTTH | QODN |  | Kota Bekasi | Rawalumbu | Sepanjang Jaya | Open Area |  | 0 |  | KSO-INTERNAL | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000361 FTTH RW 01 Kel. Sepanjang jaya
443 | RW 03 Sepanjang jaya | NET-H-000362 | FTTH RW 03 Kel. Sepanjang jaya | FTTH | QODN |  | Kota Bekasi | Rawalumbu | Sepanjang Jaya | Open Area |  | 0 |  | KSO-INTERNAL | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000362 FTTH RW 03 Kel. Sepanjang jaya
444 | RW 05 Sepanjang jaya | NET-H-000363 | FTTH RW 05 Kel. Sepanjang jaya | FTTH | QODN |  | Kota Bekasi | Rawalumbu | Sepanjang Jaya | Open Area |  | 0 |  | KSO-INTERNAL | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000363 FTTH RW 05 Kel. Sepanjang jaya
445 | RW 06 Sepanjang jaya | NET-H-000364 | FTTH RW 06 Kel. Sepanjang jaya | FTTH | QODN |  | Kota Bekasi | Rawalumbu | Sepanjang Jaya | Open Area |  | 0 |  | KSO-INTERNAL | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000364 FTTH RW 06 Kel. Sepanjang jaya
446 | RW 07 Sepanjang jaya | NET-H-000365 | FTTH RW 07 Kel. Sepanjang jaya | FTTH | QODN |  | Kota Bekasi | Rawalumbu | Sepanjang Jaya | Open Area |  | 0 |  | KSO-INTERNAL | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000365 FTTH RW 07 Kel. Sepanjang jaya
447 | RW 08 Sepanjang jaya | NET-H-000366 | FTTH RW 08 Kel. Sepanjang jaya | FTTH | QODN |  | Kota Bekasi | Rawalumbu | Sepanjang Jaya | Open Area |  | 0 |  | KSO-INTERNAL | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000366 FTTH RW 08 Kel. Sepanjang jaya
448 | RW 09 Sepanjang jaya | NET-H-000423 | FTTH RW 09 Kel. Sepanjang jaya | FTTH | QODN |  | Kota Bekasi | Rawalumbu | Sepanjang Jaya | Open Area |  | 0 |  | KSO-INTERNAL | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000423 FTTH RW 09 Kel. Sepanjang jaya
449 | RW 004 Telkom Padurenan, Mustikajaya | NET-H-000424 | FTTH RW 004 Telkom Padurenan, Mustikajaya | FTTH | QODN |  | Kota Bekasi | Mustika Jaya | Padurenan | Open Area | 1000 | 0 |  | KSO-INTERNAL | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process |  | No Issue | Sitac On Process | [7 empty] | Sosialisasi Permit | On pogress by Marketing | Darto Marketing | Free 3 Bulan | [32 empty] | NET-H-000424 FTTH RW 004 Telkom Padurenan, Mustikajaya
450 | Apartemen Evenciio Margonda | NET-B-000031 | FTTB Apartemen Evenciio Margonda | FTTB | Reverse |  | Kota Depok | Beji | Pondok Cina | Apartment | 1245 | 89 |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 4. APD Done |  |  | Sitac On Process | [7 empty] | On Progress |  | Fahriah Marketing |  |  | 2025-01-07 | Dwi Tri | Done | 1245 |  | 2025-01-08 | 2025-01-08 | 1245 | Aris Setiawan | Done APD | Uploaded to Drive | FTTB Apartemen Evenciio Margonda |  | BTS Kencana Putri & BTS Graha Sentosa |  | 23 | 89 | [9 empty] | 220 |  |  |  |  | NET-B-000031 FTTB Apartemen Evenciio Margonda
451 | The Enviro Apartemen | NET-B-000032 | FTTB The Enviro Apartemen | FTTB | Reverse |  | Kabupaten Bekasi | Cikarang Utara | Simpangan | Apartment | 217 | 16 |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 4. APD Done |  |  | Sitac On Process | [7 empty] | On Progress |  | Fahriah Marketing | [5 empty] | 217 |  | 2025-01-09 | 2025-01-09 | 217 | Aris Setiawan | Done APD | Uploaded to Drive | FTTB The Enviro Apartemen |  | Wireless/Microwave |  | 4 | 16 | [14 empty] | NET-B-000032 FTTB The Enviro Apartemen
452 | Rumah Susun Polri Menteng | NET-B-000033 | FTTB Rumah Susun Polri Menteng | FTTB | Reverse |  | Jakarta Pusat | Menteng | Gondangdia | Apartment | 400 | 31 |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 4. APD Done |  |  | Sitac On Process | [7 empty] | On Progress |  | Fahriah Marketing |  |  | 2025-01-06 | Nutsvy Ratsby | Done | 400 |  | 2025-01-10 | 2025-01-10 | 400 | Aris Setiawan | Done APD | Uploaded to Drive | FTTB Rumah Susun Polri Menteng |  | BTS Wahid Hasyim |  | 8 | 31 | [9 empty] | 512 |  |  |  |  | NET-B-000033 FTTB Rumah Susun Polri Menteng
453 | Plaza Kenari Mas | KSO-B-000002 | FTTB Plaza Kenari Mas | FTTB | Reverse |  | Jakarta Pusat | Senen | Paseban | Apartment | 1493 | 188 |  | KSO | Magnet |  |  | 2. Survey, Sitac & Design | 4. APD Done |  |  | Sitac On Process | [7 empty] | On Progress |  | Magnet / Deibie Marketing |  |  | 2024-12-26 | Nutsvy Ratsby | Done | 1493 |  | 2025-01-13 | 2025-01-13 | 1493 | Aris Setiawan | Done APD | Uploaded to Drive | FTTB Plaza Kenari Mas |  | BTS Aprizal & BTS Golden | 9 | 25 | 188 | [14 empty] | KSO-B-000002 FTTB Plaza Kenari Mas
454 | Open Area Harjamukti RW10 | NET-H-000367 | FTTH Open Area Harjamukti RW10 | FTTH | QODN |  | Kota Cirebon | Hajarmukti | Hajarmukti | Open Area | 550 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000367 FTTH Open Area Harjamukti RW10
455 | Open Area Harjamukti RW02 | NET-H-000368 | FTTH Open Area Harjamukti RW02 | FTTH | QODN |  | Kota Cirebon | Hajarmukti | Hajarmukti | Open Area | 400 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000368 FTTH Open Area Harjamukti RW02
456 | Open Area Harjamukti RW01 | NET-H-000369 | FTTH Open Area Harjamukti RW01 | FTTH | QODN |  | Kota Cirebon | Hajarmukti | Hajarmukti | Open Area | 350 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000369 FTTH Open Area Harjamukti RW01
457 | Open Area Harjamukti RW04 | NET-H-000370 | FTTH Open Area Harjamukti RW04 | FTTH | QODN |  | Kota Cirebon | Hajarmukti | Hajarmukti | Open Area | 300 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000370 FTTH Open Area Harjamukti RW04
458 | Open Area Harjamukti RW05-06 | NET-H-000371 | FTTH Open Area Harjamukti RW05-06 | FTTH | QODN |  | Kota Cirebon | Hajarmukti | Hajarmukti | Open Area | 850 | 0 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000371 FTTH Open Area Harjamukti RW05-06
459 | Open Area Harjamukti RW07 | NET-H-000372 | FTTH Open Area Harjamukti RW07 | FTTH | QODN |  | Kota Cirebon | Hajarmukti | Hajarmukti | Open Area | 650 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000372 FTTH Open Area Harjamukti RW07
460 | Griya Sunyaragi Permai | NET-H-000373 | FTTH Griya Sunyaragi Permai | FTTH | QODN |  | Kota Cirebon | Kesambi | Karyamulya | Perumahan | 1100 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000373 FTTH Griya Sunyaragi Permai
461 | Taman Nuansa Majasem | NET-H-000374 | FTTH Taman Nuansa Majasem | FTTH | QODN |  | Kota Cirebon | Kesambi | Karyamulya | Perumahan | 550 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000374 FTTH Taman Nuansa Majasem
462 | Open Area Karyamulya RW08-10 | NET-H-000375 | FTTH Open Area Karyamulya RW08-10 | FTTH | QODN |  | Kota Cirebon | Kesambi | Karyamulya | Open Area | 3300 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000375 FTTH Open Area Karyamulya RW08-10
463 | Open Area Karyamulya RW01 | NET-H-000376 | FTTH Open Area Karyamulya RW01 | FTTH | QODN |  | Kota Cirebon | Kesambi | Karyamulya | Open Area | 400 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000376 FTTH Open Area Karyamulya RW01
464 | Open Area Karyamulya RW02 | NET-H-000377 | FTTH Open Area Karyamulya RW02 | FTTH | QODN |  | Kota Cirebon | Kesambi | Karyamulya | Open Area | 550 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000377 FTTH Open Area Karyamulya RW02
465 | Open Area Karyamulya RW13 | NET-H-000378 | FTTH Open Area Karyamulya RW13 | FTTH | QODN |  | Kota Cirebon | Kesambi | Karyamulya | Open Area | 950 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000378 FTTH Open Area Karyamulya RW13
466 | Open Area Karyamulya RW03-05 | NET-H-000379 | FTTH Open Area Karyamulya RW03-05 | FTTH | QODN |  | Kota Cirebon | Kesambi | Karyamulya | Open Area | 850 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000379 FTTH Open Area Karyamulya RW03-05
467 | Open Area Karyamulya RW06-07 | NET-H-000380 | FTTH Open Area Karyamulya RW06-07 | FTTH | QODN |  | Kota Cirebon | Kesambi | Karyamulya | Open Area | 500 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000380 FTTH Open Area Karyamulya RW06-07
468 | Open Area Karyamulya RW14 | NET-H-000381 | FTTH Open Area Karyamulya RW14 | FTTH | QODN |  | Kota Cirebon | Kesambi | Karyamulya | Open Area | 400 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000381 FTTH Open Area Karyamulya RW14
469 | Open Area Kesambi RW02 | NET-H-000382 | FTTH Open Area Kesambi RW02 | FTTH | QODN |  | Kota Cirebon | Kesambi | Kesambi | Open Area | 400 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000382 FTTH Open Area Kesambi RW02
470 | Open Area Kesambi RW07 | NET-H-000383 | FTTH Open Area Kesambi RW07 | FTTH | QODN |  | Kota Cirebon | Kesambi | Kesambi | Open Area | 300 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000383 FTTH Open Area Kesambi RW07
471 | Open Area Kesambi RW03-04 | NET-H-000384 | FTTH Open Area Kesambi RW03-04 | FTTH | QODN |  | Kota Cirebon | Kesambi | Kesambi | Open Area | 450 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000384 FTTH Open Area Kesambi RW03-04
472 | Open Area Kesambi RW05 | NET-H-000385 | FTTH Open Area Kesambi RW05 | FTTH | QODN |  | Kota Cirebon | Kesambi | Kesambi | Perumahan | 300 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000385 FTTH Open Area Kesambi RW05
473 | Open Area Pekiringan RW01-04 | NET-H-000386 | FTTH Open Area Pekiringan RW01-04 | FTTH | QODN |  | Kota Cirebon | Kesambi | Pekiringan | Open Area | 550 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000386 FTTH Open Area Pekiringan RW01-04
474 | Open Area Pekiringan RW10 | NET-H-000387 | FTTH Open Area Pekiringan RW10 | FTTH | QODN |  | Kota Cirebon | Kesambi | Pekiringan | Open Area | 250 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000387 FTTH Open Area Pekiringan RW10
475 | Open Area Pekiringan RW11 | NET-H-000388 | FTTH Open Area Pekiringan RW11 | FTTH | QODN |  | Kota Cirebon | Kesambi | Pekiringan | Open Area | 250 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000388 FTTH Open Area Pekiringan RW11
476 | Open Area Pekiringan RW06-09 | NET-H-000389 | FTTH Open Area Pekiringan RW06-09 | FTTH | QODN |  | Kota Cirebon | Kesambi | Pekiringan | Open Area | 450 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000389 FTTH Open Area Pekiringan RW06-09
477 | Komplek Sasana Budaya | NET-H-000390 | FTTH Komplek Sasana Budaya | FTTH | QODN |  | Kota Cirebon | Kesambi | Pekiringan | Perumahan | 250 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000390 FTTH Komplek Sasana Budaya
478 | Komplek Pembangunan | NET-H-000391 | FTTH Komplek Pembangunan | FTTH | QODN |  | Kota Cirebon | Kesambi | Pekiringan | Perumahan | 250 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000391 FTTH Komplek Pembangunan
479 | Open Area Pekiringan RW05 | NET-H-000392 | FTTH Open Area Pekiringan RW05 | FTTH | QODN |  | Kota Cirebon | Kesambi | Pekiringan | Open Area | 250 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000392 FTTH Open Area Pekiringan RW05
480 | Open Area Kejaksan RW05-07 | NET-H-000393 | FTTH Open Area Kejaksan RW05-07 | FTTH | QODN |  | Kota Cirebon | Kejaksan | Kejaksan | Open Area | 450 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000393 FTTH Open Area Kejaksan RW05-07
481 | Open Area Sukapura RW03-06 | NET-H-000394 | FTTH Open Area Sukapura RW03-06 | FTTH | QODN |  | Kota Cirebon | Kejaksan | Sukapura | Open Area | 450 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000394 FTTH Open Area Sukapura RW03-06
482 | Open Area Sukapura RW07-09 | NET-H-000395 | FTTH Open Area Sukapura RW07-09 | FTTH | QODN |  | Kota Cirebon | Kejaksan | Sukapura | Open Area | 550 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000395 FTTH Open Area Sukapura RW07-09
483 | Komplek Pilang Perdana | NET-H-000396 | FTTH Komplek Pilang Perdana | FTTH | QODN |  | Kota Cirebon | Kejaksan | Sukapura | Perumahan | 300 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000396 FTTH Komplek Pilang Perdana
484 | Komplek Sentrayasa | NET-H-000397 | FTTH Komplek Sentrayasa | FTTH | QODN |  | Kota Cirebon | Kejaksan | Sukapura | Perumahan | 300 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000397 FTTH Komplek Sentrayasa
485 | Open Area Sukapura RW10 | NET-H-000398 | FTTH Open Area Sukapura RW10 | FTTH | QODN |  | Kota Cirebon | Kejaksan | Sukapura | Open Area | 350 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000398 FTTH Open Area Sukapura RW10
486 | Komplek Pilang Mas Garden | NET-H-000399 | FTTH Komplek Pilang Mas Garden | FTTH | QODN |  | Kab. Cirebon | Kedawung | Kedungjaya | Perumahan | 200 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000399 FTTH Komplek Pilang Mas Garden
487 | Perumahan Pilang Sari | NET-H-000400 | FTTH Perumahan Pilang Sari | FTTH | QODN |  | Kab. Cirebon | Kedawung | Kedungjaya | Perumahan | 550 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000400 FTTH Perumahan Pilang Sari
488 | Open Area Kedungjaya RW03 | NET-H-000401 | FTTH Open Area Kedungjaya RW03 | FTTH | QODN |  | Kab. Cirebon | Kedawung | Kedungjaya | Perumahan | 300 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000401 FTTH Open Area Kedungjaya RW03
489 | Open Area Sutawinangun RW05&08 | NET-H-000402 | FTTH Open Area Sutawinangun RW05&08 | FTTH | QODN |  | Kab. Cirebon | Kedawung | Sutawinangun | Perumahan | 300 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000402 FTTH Open Area Sutawinangun RW05&08
490 | Open Area Sutawinangun RW01-04 & 06 | NET-H-000403 | FTTH Open Area Sutawinangun RW01-04 & 06 | FTTH | QODN |  | Kab. Cirebon | Kedawung | Sutawinangun | Open Area | 700 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000403 FTTH Open Area Sutawinangun RW01-04 & 06
Open Area Sutawinangun RW07 |  | NET-H-000404 | FTTH Open Area Sutawinangun RW07 | FTTH | QODN |  | Kab. Cirebon | Kedawung | Sutawinangun | Open Area | 350 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000404 FTTH Open Area Sutawinangun RW07
492 | Open Area Kertawinangun RW01-02 & 06 | NET-H-000405 | FTTH Open Area Kertawinangun RW01-02 & 06 | FTTH | QODN |  | Kab. Cirebon | Kedawung | Kertawinangun | Open Area | 550 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000405 FTTH Open Area Kertawinangun RW01-02 & 06
493 | Open Area Kertawinangun RW03-05 | NET-H-000406 | FTTH Open Area Kertawinangun RW03-05 | FTTH | QODN |  | Kab. Cirebon | Kedawung | Kertawinangun | Open Area | 650 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000406 FTTH Open Area Kertawinangun RW03-05
#REF! | Komplek Harjamulia Indah Estate | NET-H-000407 | FTTH Komplek Harjamulia Indah Estate | FTTH | QODN |  | Kab. Cirebon | Kedawung | Tuk | Perumahan | 200 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000407 FTTH Komplek Harjamulia Indah Estate
495 | Open Area Tuk RW07 | NET-H-000408 | FTTH Open Area Tuk RW07 | FTTH | QODN |  | Kab. Cirebon | Kedawung | Tuk | Open Area | 250 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000408 FTTH Open Area Tuk RW07
496 | Open Area Tuk RW06 | NET-H-000409 | FTTH Open Area Tuk RW06 | FTTH | QODN |  | Kab. Cirebon | Kedawung | Tuk | Open Area | 300 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000409 FTTH Open Area Tuk RW06
497 | Open Area Tuk RW01-03 & 10 | NET-H-000410 | FTTH Open Area Tuk RW01-03 & 10 | FTTH | QODN |  | Kab. Cirebon | Kedawung | Tuk | Open Area | 1000 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000410 FTTH Open Area Tuk RW01-03 & 10
498 | Komplek Griya Caraka | NET-H-000411 | FTTH Komplek Griya Caraka | FTTH | QODN |  | Kab. Cirebon | Kedawung | Kalikoa | Perumahan | 400 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000411 FTTH Komplek Griya Caraka
499 | Komplek Stadion Bima RW04-06 | NET-H-000412 | FTTH Komplek Stadion Bima RW04-06 | FTTH | QODN |  | Kab. Cirebon | Kedawung | Kalikoa | Perumahan | 500 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000412 FTTH Komplek Stadion Bima RW04-06
500 | Open Area Kalikoa RW01-03 | NET-H-000413 | FTTH Open Area Kalikoa RW01-03 | FTTH | QODN |  | Kab. Cirebon | Kedawung | Kalikoa | Open Area | 450 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000413 FTTH Open Area Kalikoa RW01-03
501 | Komplek PDK Yudhasari | NET-H-000414 | FTTH Komplek PDK Yudhasari | FTTH | QODN |  | Kota Cirebon | Kesambi | Sunyaragi | Perumahan | 250 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000414 FTTH Komplek PDK Yudhasari
502 | Open Area Sunyaragi RW03-08 | NET-H-000415 | FTTH Open Area Sunyaragi RW03-08 | FTTH | QODN |  | Kota Cirebon | Kesambi | Sunyaragi | Open Area | 800 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000415 FTTH Open Area Sunyaragi RW03-08
503 | Extendtion RT01 RW06 Kelurahan Sukadamai | NET-H-000416 | FTTH Extendtion RT01 RW06 Kelurahan Sukadamai | FTTH | QODN |  | Kota Bogor | Tanah Sereal | Sukadamai | Open Area | 150 | 14 |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 3. Civil Work | 5. Waiting Implementation |  |  | Waiting Implementation | [12 empty] | 2025-01-16 |  |  | 123 |  | 2025-01-17 | 2025-01-17 | 123 | M. Raul Habib | Done APD | Uploaded to Drive | NET-H-000416 FTTH Extendtion RT01 RW06 Kelurahan Sukadamai |  |  | 1 | 2 | 14 | 18 |  | 4 |  |  | 397 | [8 empty] | NET-H-000416 FTTH Extendtion RT01 RW06 Kelurahan Sukadamai
504 | Komplek Graha Nuansa Pilang | NET-H-000417 | FTTH Komplek Graha Nuansa Pilang | FTTH | QODN |  | Kab. Cirebon | Kedawung | Pilangsari | Perumahan | 300 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000417 FTTH Komplek Graha Nuansa Pilang
505 | Open Area Pilangsari RW01-03 | NET-H-000418 | FTTH Open Area Pilangsari RW01-03 | FTTH | QODN |  | Kab. Cirebon | Kedawung | Pilangsari | Open Area | 800 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000418 FTTH Open Area Pilangsari RW01-03
506 | Komplek Taman Kapuk Permai | NET-H-000419 | FTTH Komplek Taman Kapuk Permai | FTTH | QODN |  | Kab. Cirebon | Kedawung | Kedawung | Perumahan | 400 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000419 FTTH Komplek Taman Kapuk Permai
507 | Open Area Kedawung RW01 | NET-H-000420 | FTTH Open Area Kedawung RW01 | FTTH | QODN |  | Kab. Cirebon | Kedawung | Kedawung | Open Area | 500 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000420 FTTH Open Area Kedawung RW01
508 | Open Area Kedawung RW02&04 | NET-H-000421 | FTTH Open Area Kedawung RW02&04 | FTTH | QODN |  | Kab. Cirebon | Kedawung | Kedawung | Open Area | 800 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel Cirebon Fase 3 |  | Sitac On Process | [43 empty] | NET-H-000421 FTTH Open Area Kedawung RW02&04
509 | RT07 & 09 RW01 KELURAHAN KALIDERES | NET-H-000425 | FTTH RT07 & 09 RW01 KELURAHAN KALIDERES | FTTH | QODN |  | Jakarta Barat | Kalideres | Kalideres | Open Area | 391 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 3. OG APD |  |  | On Progress APD | [13 empty] | TORO |  | 191 | [27 empty] | NET-H-000425 FTTH RT07 & 09 RW01 KELURAHAN KALIDERES
510 | Perluasan RW 08 Pamengkang Zambrud | NET-H-000426 | FTTH Perluasan RW 08 Pamengkang Zambrud | FTTH | QODN |  | Kab. Cirebon | Mundu | Pamengkang | Perumahan | 46 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process |  |  | Sitac On Process | [43 empty] | NET-H-000426 FTTH Perluasan RW 08 Pamengkang Zambrud
511 | Perluasan RW 08 Perum mustika | NET-H-000427 | FTTH Perluasan RW 08 Perum mustika | FTTH | QODN |  | Kab. Cirebon | Mundu | Pamengkang | Perumahan | 47 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process |  |  | Sitac On Process | [43 empty] | NET-H-000427 FTTH Perluasan RW 08 Perum mustika
512 | Perluasan RT07&08 RW15 Kel. Kecapi (Kp. Balong) | NET-H-000428 | FTTH Perluasan RT07&08 RW15 Kel. Kecapi (Kp. Balong) | FTTH | QODN |  | Kota Cirebon | Harjamukti | Kecapi | Open Area | 150 | 10 |  | NON-KSO | Nethome |  | INHOUSE | 3. Civil Work | 6. Pole & ODN Instalation | Prepare Material | No Issue | Installation On Progress | [7 empty] | On Progress | [7 empty] | 124 |  |  | 2025-01-13 | 124 | Muchamad Rivai | Done APD | Uploaded to Drive | NET-H-000428 FTTH Perluasan RT07&08 RW15 Kel. Kecapi (Kp. Balong) | Penggunaan Pole Reroute BB/Feeder | New Langji Vihara 2 | 1 | 2 | 10 |  |  | 10 | 803 | [10 empty] | NET-H-000428 FTTH Perluasan RT07&08 RW15 Kel. Kecapi (Kp. Balong) | 0 | 2025-01-13 | 2025-01-13 | 0001/SPLICE-MSP/FMI/I/2025
513 | Perumahan Maharta | NET-H-000429 | FTTH Perumahan Maharta | FTTH | QODN |  | Tangerang Selatan | Pondok Area | Pondok Kacang Timur | Perumahan | 1000 |  |  | NON-KSO | Nethome |  | Oemerta Karya | 2. Survey, Sitac & Design | 2. OG Survey | Funnel BTS Pondok Kacang Timur |  | Sitac On Process | [43 empty] | NET-H-000429 FTTH Perumahan Maharta
514 | Perumahan Taman Prima | NET-H-000430 | FTTH Perumahan Taman Prima | FTTH | QODN |  | Tangerang Selatan | Pondok Area | Pondok Kacang Timur | Perumahan | 500 |  |  | NON-KSO | Nethome |  | Oemerta Karya | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Pondok Kacang Timur |  | Sitac On Process | [7 empty] | NY Start permit |  |  |  | SPK baru release | [31 empty] | NET-H-000430 FTTH Perumahan Taman Prima
515 | Villa Bintaro Regency | NET-H-000431 | FTTH Villa Bintaro Regency | FTTH | QODN |  | Tangerang Selatan | Pondok Area | Pondok Kacang Timur | Perumahan | 300 |  |  | NON-KSO | Nethome |  | Oemerta Karya | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Pondok Kacang Timur |  | Sitac On Process | [7 empty] | NY Start permit |  |  |  | SPK baru release | [31 empty] | NET-H-000431 FTTH Villa Bintaro Regency
516 | Komplek Griya Pipit | NET-H-000432 | FTTH Komplek Griya Pipit | FTTH | QODN |  | Tangerang Selatan | Pondok Area | Pondok Kacang Timur | Perumahan | 150 |  |  | NON-KSO | Nethome |  | Oemerta Karya | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Pondok Kacang Timur |  | Sitac On Process | [7 empty] | NY Start permit |  |  |  | SPK baru release | [31 empty] | NET-H-000432 FTTH Komplek Griya Pipit
517 | Open Area RW 01 Pondok Kacang Timur | NET-H-000433 | FTTH Open Area RW 01 Pondok Kacang Timur | FTTH | QODN |  | Tangerang Selatan | Pondok Area | Pondok Kacang Timur | Open Area | 400 |  |  | NON-KSO | Nethome |  | Oemerta Karya | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Pondok Kacang Timur |  | Sitac On Process | [7 empty] | NY Start permit |  |  |  | SPK baru release | [31 empty] | NET-H-000433 FTTH Open Area RW 01 Pondok Kacang Timur
518 | Open Area RW 04 Pondok Kacang Timur | NET-H-000434 | FTTH Open Area RW 04 Pondok Kacang Timur | FTTH | QODN |  | Tangerang Selatan | Pondok Area | Pondok Kacang Timur | Open Area | 500 |  |  | NON-KSO | Nethome |  | Oemerta Karya | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Pondok Kacang Timur |  | Sitac On Process | [7 empty] | NY Start permit |  |  |  | SPK baru release | [31 empty] | NET-H-000434 FTTH Open Area RW 04 Pondok Kacang Timur
519 | Open Area RW 05 Pondok Kacang Timur | NET-H-000435 | FTTH Open Area RW 05 Pondok Kacang Timur | FTTH | QODN |  | Tangerang Selatan | Pondok Area | Pondok Kacang Timur | Open Area | 500 |  |  | NON-KSO | Nethome |  | Oemerta Karya | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Pondok Kacang Timur |  | Sitac On Process | [7 empty] | NY Start permit |  |  |  | SPK baru release | [31 empty] | NET-H-000435 FTTH Open Area RW 05 Pondok Kacang Timur
520 | Open Area RW 07 Pondok Kacang Timur | NET-H-000436 | FTTH Open Area RW 07 Pondok Kacang Timur | FTTH | QODN |  | Tangerang Selatan | Pondok Area | Pondok Kacang Timur | Open Area | 700 |  |  | NON-KSO | Nethome |  | Oemerta Karya | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Pondok Kacang Timur |  | Sitac On Process | [7 empty] | NY Start permit |  |  |  | SPK baru release | [31 empty] | NET-H-000436 FTTH Open Area RW 07 Pondok Kacang Timur
521 | Open Area RW 03 Pondok Kacang Timur | NET-H-000437 | FTTH Open Area RW 03 Pondok Kacang Timur | FTTH | QODN |  | Tangerang Selatan | Pondok Area | Pondok Kacang Timur | Open Area | 200 |  |  | NON-KSO | Nethome |  | Oemerta Karya | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Pondok Kacang Timur |  | Sitac On Process | [7 empty] | NY Start permit |  |  |  | SPK baru release | [31 empty] | NET-H-000437 FTTH Open Area RW 03 Pondok Kacang Timur
522 | Open Area RW 02 & 05 Pondok Kacang Barat | NET-H-000438 | FTTH Open Area RW 02 & 05 Pondok Kacang Barat | FTTH | QODN |  | Tangerang Selatan | Pondok Area | Pondok Kacang Timur | Open Area | 1000 |  |  | NON-KSO | Nethome |  | Oemerta Karya | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Pondok Kacang Timur |  | Sitac On Process | [7 empty] | NY Start permit |  |  |  | SPK baru release | [31 empty] | NET-H-000438 FTTH Open Area RW 02 & 05 Pondok Kacang Barat
523 | Open Area RW 03 & 10 Pondok Kacang Barat | NET-H-000439 | FTTH Open Area RW 03 & 10 Pondok Kacang Barat | FTTH | QODN |  | Tangerang Selatan | Pondok Area | Pondok Kacang Timur | Open Area | 800 |  |  | NON-KSO | Nethome |  | Oemerta Karya | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Pondok Kacang Timur |  | Sitac On Process | [7 empty] | NY Start permit |  |  |  | SPK baru release | [31 empty] | NET-H-000439 FTTH Open Area RW 03 & 10 Pondok Kacang Barat
524 | Komplek Setneg Pondok Kacang Barat | NET-H-000440 | FTTH Komplek Setneg Pondok Kacang Barat | FTTH | QODN |  | Tangerang Selatan | Pondok Area | Pondok Kacang Timur | Perumahan | 300 |  |  | NON-KSO | Nethome |  | Oemerta Karya | 2. Survey, Sitac & Design | 2. OG Survey | Funnel BTS Pondok Kacang Timur |  | Sitac On Process | [43 empty] | NET-H-000440 FTTH Komplek Setneg Pondok Kacang Barat
525 | Open Area Waringinjaya | NET-H-000441 | FTTH Open Area Waringinjaya | FTTH | QODN |  | Kab. Bekasi | Kedungwaringin | Waringinjaya | Open Area | 1200 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS MINI 01 karawang - Cikarang |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000441 FTTH Open Area Waringinjaya
526 | Perumahan Duren Sawit Selatan | NET-H-000442 | FTTH Perumahan Duren Sawit Selatan | FTTH | QODN |  | Jakarta Timur | Duren Sawit | Duren Sawit | Perumahan | 4000 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS PONDOK BAMBU (PDBJKT) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000442 FTTH Perumahan Duren Sawit Selatan
527 | Pondok Kopi Utara | NET-H-000443 | FTTH Pondok Kopi Utara | FTTH | QODN |  | Jakarta Timur | Duren Sawit | Pondok kopi | Open Area | 2000 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS PRIMA (PRMJKT) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000443 FTTH Pondok Kopi Utara
528 | Komplek Pemadam Semper Barat RW01 | NET-H-000444 | FTTH Komplek Pemadam Semper Barat RW01 | FTTH | QODN |  | Jakarta Utara | Cilincing | Semper Barat | Perumahan | 1000 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 3. OG APD | FUnnel BTS SEMPER BARU (SPRBJKU) |  | On Progress APD | [12 empty] | 2025-01-15 | Haikal | Done | 1616 | [27 empty] | NET-H-000444 FTTH Komplek Pemadam Semper Barat RW01
529 | Open Area Semper Barat RW05 | NET-H-000445 | FTTH Open Area Semper Barat RW05 | FTTH | QODN |  | Jakarta Utara | Cilincing | Semper Barat | Open Area | 400 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | FUnnel BTS SEMPER BARU (SPRBJKU) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000445 FTTH Open Area Semper Barat RW05
530 | Open Area Tugu Utara RW02 | NET-H-000446 | FTTH Open Area Tugu Utara RW02 | FTTH | QODN |  | Jakarta Utara | Koja | Tugu Utara | Open Area | 700 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | FUnnel BTS SEMPER BARU (SPRBJKU) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000446 FTTH Open Area Tugu Utara RW02
531 | Open Area Tugu Utara RW16 | NET-H-000447 | FTTH Open Area Tugu Utara RW16 | FTTH | QODN |  | Jakarta Utara | Koja | Tugu Utara | Open Area | 350 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | FUnnel BTS SEMPER BARU (SPRBJKU) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000447 FTTH Open Area Tugu Utara RW16
532 | Komplek Yuka Tugu Utara RW08 | NET-H-000448 | FTTH Komplek Yuka Tugu Utara RW08 | FTTH | QODN |  | Jakarta Utara | Koja | Tugu Utara | Perumahan | 600 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | FUnnel BTS SEMPER BARU (SPRBJKU) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000448 FTTH Komplek Yuka Tugu Utara RW08
533 | Kelurahan Serpong RW 08 | NET-H-000449 | FTTH Kelurahan Serpong RW 08 | FTTH | QODN |  | Tangerang Selatan | Serpong | Serpong | Open Area | 300 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS DODDY (DDYTGR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000449 FTTH Kelurahan Serpong RW 08
534 | Kelurahan Serpong RW 01 | NET-H-000450 | FTTH Kelurahan Serpong RW 01 | FTTH | QODN |  | Tangerang Selatan | Serpong | Serpong | Open Area | 500 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS DODDY (DDYTGR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000450 FTTH Kelurahan Serpong RW 01
535 | Kelurahan Serpong RW 07 | NET-H-000451 | FTTH Kelurahan Serpong RW 07 | FTTH | QODN |  | Tangerang Selatan | Serpong | Serpong | Open Area | 300 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS DODDY (DDYTGR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000451 FTTH Kelurahan Serpong RW 07
536 | Perumahan Pondok Bahar Permai | NET-H-000452 | FTTH Perumahan Pondok Bahar Permai | FTTH | QODN |  | Kota Tangerang | Karang Tengah | Pondok Bahar | Perumahan | 1000 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Gondrong (GDRTGR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000452 FTTH Perumahan Pondok Bahar Permai
537 | Open Area RW 02 Pondok Bahar | NET-H-000453 | FTTH Open Area RW 02 Pondok Bahar | FTTH | QODN |  | Kota Tangerang | Karang Tengah | Pondok Bahar | Open Area | 600 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Gondrong (GDRTGR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000453 FTTH Open Area RW 02 Pondok Bahar
538 | Perumahan Bojong Depok baru | NET-H-000454 | FTTH Perumahan Bojong Depok baru | FTTH | QODN |  | Kab. Bogor | Cibinong | Sukahati | Perumahan | 1500 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Karadenan Cibinong (KDNBGR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000454 FTTH Perumahan Bojong Depok baru
539 | Perumahan Acropolis | NET-H-000455 | FTTH Perumahan Acropolis | FTTH | QODN |  | Kab. Bogor | Cibinong | Karadenan | Perumahan | 1000 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Karadenan Cibinong (KDNBGR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000455 FTTH Perumahan Acropolis
540 | Perum Puri Nirwana 3 | NET-H-000456 | FTTH Perum Puri Nirwana 3 | FTTH | QODN |  | Kab. Bogor | Cibinong | Karadenan | Perumahan | 900 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Karadenan Cibinong (KDNBGR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000456 FTTH Perum Puri Nirwana 3
541 | Open Area Tapos RW 01-15 | NET-H-000457 | FTTH Open Area Tapos RW 01-15 | FTTH | QODN |  | Kota Depok | Tapos | Tapos | Open Area | 500 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Tapos (TPSDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000457 FTTH Open Area Tapos RW 01-15
542 | Open Area Tapos RW 06-10 | NET-H-000458 | FTTH Open Area Tapos RW 06-10 | FTTH | QODN |  | Kota Depok | Tapos | Tapos | Open Area | 700 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Tapos (TPSDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000458 FTTH Open Area Tapos RW 06-10
543 | Open Area Tapos RW 13 | NET-H-000459 | FTTH Open Area Tapos RW 13 | FTTH | QODN |  | Kota Depok | Tapos | Tapos | Open Area | 100 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Tapos (TPSDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000459 FTTH Open Area Tapos RW 13
544 | Open Area Tapos RW 03 | NET-H-000460 | FTTH Open Area Tapos RW 03 | FTTH | QODN |  | Kota Depok | Tapos | Tapos | Open Area | 150 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Tapos (TPSDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000460 FTTH Open Area Tapos RW 03
545 | Open Area Cimpaeun RW 01 & 17 | NET-H-000461 | FTTH Open Area Cimpaeun RW 01 & 17 | FTTH | QODN |  | Kota Depok | Tapos | Cimpaeun | Open Area | 200 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Tapos (TPSDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000461 FTTH Open Area Cimpaeun RW 01 & 17
546 | Open Area Cimpaeun RW 13-15 | NET-H-000462 | FTTH Open Area Cimpaeun RW 13-15 | FTTH | QODN |  | Kota Depok | Tapos | Cimpaeun | Open Area | 500 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Tapos (TPSDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000462 FTTH Open Area Cimpaeun RW 13-15
547 | Open Area Kalibata RW04 | NET-H-000463 | FTTH Open Area Kalibata RW04 | FTTH | QODN |  | Jakarta Selatan | Pancoran | Kalibata | Open Area | 500 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Samali Baru (SMLBJKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000463 FTTH Open Area Kalibata RW04
548 | Open Area Kalibata RW06 | NET-H-000464 | FTTH Open Area Kalibata RW06 | FTTH | QODN |  | Jakarta Selatan | Pancoran | Kalibata | Open Area | 500 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Samali Baru (SMLBJKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000464 FTTH Open Area Kalibata RW06
549 | Open Area Kalibata RW03 | NET-H-000465 | FTTH Open Area Kalibata RW03 | FTTH | QODN |  | Jakarta Selatan | Pancoran | Kalibata | Open Area | 200 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Samali Baru (SMLBJKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000465 FTTH Open Area Kalibata RW03
550 | Open Area Kalibata RW07 | NET-H-000466 | FTTH Open Area Kalibata RW07 | FTTH | QODN |  | Jakarta Selatan | Pancoran | Kalibata | Open Area | 500 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Samali Baru (SMLBJKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000466 FTTH Open Area Kalibata RW07
551 | Open Area Kalibata RW02 | NET-H-000467 | FTTH Open Area Kalibata RW02 | FTTH | QODN |  | Jakarta Selatan | Pancoran | Kalibata | Open Area | 300 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Samali Baru (SMLBJKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000467 FTTH Open Area Kalibata RW02
552 | Open Area Pejaten Barat RW01 | NET-H-000468 | FTTH Open Area Pejaten Barat RW01 | FTTH | QODN |  | Jakarta Selatan | Pasar Minggu | Pejaten Barat | Open Area | 600 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Samali Baru (SMLBJKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000468 FTTH Open Area Pejaten Barat RW01
553 | Open Area Pejaten Barat RW03 | NET-H-000469 | FTTH Open Area Pejaten Barat RW03 | FTTH | QODN |  | Jakarta Selatan | Pasar Minggu | Pejaten Barat | Open Area | 700 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Samali Baru (SMLBJKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000469 FTTH Open Area Pejaten Barat RW03
554 | Open Area Pejaten Barat RW05 | NET-H-000470 | FTTH Open Area Pejaten Barat RW05 | FTTH | QODN |  | Jakarta Selatan | Pasar Minggu | Pejaten Barat | Open Area | 200 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Samali Baru (SMLBJKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000470 FTTH Open Area Pejaten Barat RW05
555 | Open Area Pejaten Barat RW04 | NET-H-000471 | FTTH Open Area Pejaten Barat RW04 | FTTH | QODN |  | Jakarta Selatan | Pasar Minggu | Pejaten Barat | Open Area | 500 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Samali Baru (SMLBJKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000471 FTTH Open Area Pejaten Barat RW04
556 | Open Area Kalibata RW09 | NET-H-000472 | FTTH Open Area Kalibata RW09 | FTTH | QODN |  | Jakarta Selatan | Pancoran | Kalibata | Open Area | 200 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Samali Baru (SMLBJKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000472 FTTH Open Area Kalibata RW09
557 | Komplek Timah RW12 | NET-H-000473 | FTTH Komplek Timah RW12 | FTTH | QODN |  | Kota Depok | Cimanggis | Tugu | Perumahan | 400 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Kencana Putri (KCPDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000473 FTTH Komplek Timah RW12
558 | Open Area Pasir Gunung Selatan RW02 | NET-H-000474 | FTTH Open Area Pasir Gunung Selatan RW02 | FTTH | QODN |  | Kota Depok | Cimanggis | Pasir Gunung Selatan | Open Area | 300 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Kencana Putri (KCPDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000474 FTTH Open Area Pasir Gunung Selatan RW02
559 | Open Area Pasir Gunung Selatan RW05 | NET-H-000475 | FTTH Open Area Pasir Gunung Selatan RW05 | FTTH | QODN |  | Kota Depok | Cimanggis | Pasir Gunung Selatan | Open Area | 200 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Kencana Putri (KCPDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000475 FTTH Open Area Pasir Gunung Selatan RW05
560 | Open Area Pasir Gunung Selatan RW07 | NET-H-000476 | FTTH Open Area Pasir Gunung Selatan RW07 | FTTH | QODN |  | Kota Depok | Cimanggis | Pasir Gunung Selatan | Open Area | 300 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Kencana Putri (KCPDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000476 FTTH Open Area Pasir Gunung Selatan RW07
561 | Open Area Srengseng Sawah RW 1&2 | NET-H-000477 | FTTH Open Area Srengseng Sawah RW 1&2 | FTTH | QODN |  | Jakarta Selatan | Jagakarsa | Srengseng Sawah | Open Area | 1000 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Kencana Putri (KCPDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000477 FTTH Open Area Srengseng Sawah RW 1&2
562 | Open Area Tugu RW09 | NET-H-000478 | FTTH Open Area Tugu RW09 | FTTH | QODN |  | Kota Depok | Cimanggis | Tugu | Open Area | 700 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Kencana Putri (KCPDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000478 FTTH Open Area Tugu RW09
563 | Open Area Tugu RW10 | NET-H-000479 | FTTH Open Area Tugu RW10 | FTTH | QODN |  | Kota Depok | Cimanggis | Tugu | Open Area | 1200 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Kencana Putri (KCPDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000479 FTTH Open Area Tugu RW10
564 | Open Area Cipedak RW01 RT09-11 | NET-H-000480 | FTTH Open Area Cipedak RW01 RT09-11 | FTTH | QODN |  | Jakarta Selatan | Jagakarsa | Cipedak | Open Area | 400 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Jagakarsa (JGKDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000480 FTTH Open Area Cipedak RW01 RT09-11
565 | Open Area Cipedak RW01 RT01-08 | NET-H-000481 | FTTH Open Area Cipedak RW01 RT01-08 | FTTH | QODN |  | Jakarta Selatan | Jagakarsa | Cipedak | Open Area | 1000 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Jagakarsa (JGKDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000481 FTTH Open Area Cipedak RW01 RT01-08
566 | Open Area Cipedak RW02 | NET-H-000482 | FTTH Open Area Cipedak RW02 | FTTH | QODN |  | Jakarta Selatan | Jagakarsa | Cipedak | Open Area | 600 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Jagakarsa (JGKDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000482 FTTH Open Area Cipedak RW02
567 | Open Area Cipedak RW06 | NET-H-000483 | FTTH Open Area Cipedak RW06 | FTTH | QODN |  | Jakarta Selatan | Jagakarsa | Cipedak | Open Area | 400 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Jagakarsa (JGKDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000483 FTTH Open Area Cipedak RW06
568 | Open Area Cipedak RW04 | NET-H-000484 | FTTH Open Area Cipedak RW04 | FTTH | QODN |  | Jakarta Selatan | Jagakarsa | Cipedak | Open Area | 1000 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Jagakarsa (JGKDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000484 FTTH Open Area Cipedak RW04
569 | Open Area Cipedak RW03 RT01-05 | NET-H-000485 | FTTH Open Area Cipedak RW03 RT01-05 | FTTH | QODN |  | Jakarta Selatan | Jagakarsa | Cipedak | Open Area | 300 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Jagakarsa (JGKDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000485 FTTH Open Area Cipedak RW03 RT01-05
570 | Open Area Cipedak RW03 RT06-07 | NET-H-000486 | FTTH Open Area Cipedak RW03 RT06-07 | FTTH | QODN |  | Jakarta Selatan | Jagakarsa | Cipedak | Open Area | 200 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Jagakarsa (JGKDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000486 FTTH Open Area Cipedak RW03 RT06-07
571 | Open Area Cipedak RW05 | NET-H-000487 | FTTH Open Area Cipedak RW05 | FTTH | QODN |  | Jakarta Selatan | Jagakarsa | Cipedak | Open Area | 500 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Jagakarsa (JGKDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000487 FTTH Open Area Cipedak RW05
572 | Open Area Sawangan Baru RW02-06 | NET-H-000488 | FTTH Open Area Sawangan Baru RW02-06 | FTTH | QODN |  | Kota Depok | Sawangan | Sawangan Baru | Open Area | 2000 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Abdul Wahab (ABWDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000488 FTTH Open Area Sawangan Baru RW02-06
573 | Open Area Sawangan Lama RW03&07 | NET-H-000489 | FTTH Open Area Sawangan Lama RW03&07 | FTTH | QODN |  | Kota Depok | Sawangan | Sawangan Lama | Open Area | 300 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Abdul Wahab (ABWDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000489 FTTH Open Area Sawangan Lama RW03&07
574 | Open Area Sawangan Lama RW06 | NET-H-000490 | FTTH Open Area Sawangan Lama RW06 | FTTH | QODN |  | Kota Depok | Sawangan | Sawangan Lama | Open Area | 400 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Abdul Wahab (ABWDPK) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000490 FTTH Open Area Sawangan Lama RW06
575 | Komplek Graha Duta Margahayu | NET-H-000491 | FTTH Komplek Graha Duta Margahayu | FTTH | QODN |  | Kota Bekasi | Bekasi Timur | Margahayu | Perumahan | 400 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Hoki Margahayu (MGHBKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000491 FTTH Komplek Graha Duta Margahayu
576 | Open Area Margahayu RW01-03 | NET-H-000492 | FTTH Open Area Margahayu RW01-03 | FTTH | QODN |  | Kota Bekasi | Bekasi Timur | Margahayu | Open Area | 500 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Hoki Margahayu (MGHBKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000492 FTTH Open Area Margahayu RW01-03
577 | Open Area Margahayu RW05-07 | NET-H-000493 | FTTH Open Area Margahayu RW05-07 | FTTH | QODN |  | Kota Bekasi | Bekasi Timur | Margahayu | Open Area | 500 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Hoki Margahayu (MGHBKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000493 FTTH Open Area Margahayu RW05-07
578 | Open Area Margahayu RW08 | Inline Dengan Req Sales | FTTH Open Area Margahayu RW08 | FTTH | QODN |  | Kota Bekasi | Bekasi Timur | Margahayu | Open Area | 300 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Hoki Margahayu (MGHBKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | Inline Dengan Req Sales FTTH Open Area Margahayu RW08
579 | Perumahan Cikarang Baru Sertajaya | NET-H-000495 | FTTH Perumahan Cikarang Baru Sertajaya | FTTH | QODN |  | Kab. Bekasi | Cikarang Timur | Sertajaya | Perumahan | 700 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Annur Cikarang (CKRJBR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000495 FTTH Perumahan Cikarang Baru Sertajaya
580 | Perumahan Cikarang Baru Jayamukti | NET-H-000496 | FTTH Perumahan Cikarang Baru Jayamukti | FTTH | QODN |  | Kab. Bekasi | Cikarang Pusat | Jayamukti | Perumahan | 700 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Annur Cikarang (CKRJBR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000496 FTTH Perumahan Cikarang Baru Jayamukti
581 | Open Area Jayamukti | NET-H-000497 | FTTH Open Area Jayamukti | FTTH | QODN |  | Kab. Bekasi | Cikarang Pusat | Jayamukti | Open Area | 600 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Annur Cikarang (CKRJBR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000497 FTTH Open Area Jayamukti
582 | Grand Kahuripan | NET-H-000498 | FTTH Grand Kahuripan | FTTH | QODN |  | Kab. Bogor | Klapanunggal | Klapanunggal | Perumahan | 3000 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Klapanunggal |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000498 FTTH Grand Kahuripan
583 | Permata Klapanunggal | NET-H-000499 | FTTH Permata Klapanunggal | FTTH | QODN |  | Kab. Bogor | Klapanunggal | Klapanunggal | Perumahan | 300 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Klapanunggal |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000499 FTTH Permata Klapanunggal
584 | Open Area Klapanunggal RW05 | NET-H-000500 | FTTH Open Area Klapanunggal RW05 | FTTH | QODN |  | Kab. Bogor | Klapanunggal | Klapanunggal | Open Area | 1000 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Klapanunggal |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000500 FTTH Open Area Klapanunggal RW05
585 | Open Area Klapanunggal RW 02&04 | NET-H-000501 | FTTH Open Area Klapanunggal RW 02&04 | FTTH | QODN |  | Kab. Bogor | Klapanunggal | Klapanunggal | Open Area | 1500 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Klapanunggal |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000501 FTTH Open Area Klapanunggal RW 02&04
586 | Perum Paspampres Situsari | NET-H-000502 | FTTH Perum Paspampres Situsari | FTTH | QODN |  | Kab. Bogor | Cileungsi | Setu Sari | Perumahan | 800 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Jonggol (JGLJBR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000502 FTTH Perum Paspampres Situsari
587 | WG Residence | NET-H-000503 | FTTH WG Residence | FTTH | QODN |  | Kab. Bogor | Cileungsi | Setu Sari | Perumahan | 100 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Jonggol (JGLJBR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000503 FTTH WG Residence
588 | Sunrise Garden Bukit Putera | NET-H-000504 | FTTH Sunrise Garden Bukit Putera | FTTH | QODN |  | Kab. Bogor | Cileungsi | Setu Sari | Perumahan | 700 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Jonggol (JGLJBR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000504 FTTH Sunrise Garden Bukit Putera
589 | TNI AD Situsari Permai | NET-H-000505 | FTTH TNI AD Situsari Permai | FTTH | QODN |  | Kab. Bogor | Cileungsi | Setu Sari | Perumahan | 100 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Jonggol (JGLJBR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000505 FTTH TNI AD Situsari Permai
590 | Komplek Mutiara | NET-H-000506 | FTTH Komplek Mutiara | FTTH | QODN |  | Kab. Bogor | Cileungsi | Setu Sari | Perumahan | 200 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Jonggol (JGLJBR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000506 FTTH Komplek Mutiara
591 | Permata Puri Harmoni 1 | NET-H-000507 | FTTH Permata Puri Harmoni 1 | FTTH | QODN |  | Kab. Bogor | Cileungsi | Setu Sari | Perumahan | 800 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Jonggol (JGLJBR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000507 FTTH Permata Puri Harmoni 1
592 | Griya Cipeucang | NET-H-000508 | FTTH Griya Cipeucang | FTTH | QODN |  | Kab. Bogor | Cileungsi | Cipeucang | Perumahan | 600 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Jonggol (JGLJBR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000508 FTTH Griya Cipeucang
593 | Open Area Bintara RW02 | NET-H-000509 | FTTH Open Area Bintara RW02 | FTTH | QODN |  | Kota Bekasi | Bekasi Barat | Bintara | Open Area | 1000 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Bintara (BTRBKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000509 FTTH Open Area Bintara RW02
594 | Open Area Pondok Kopi RW 04-07 | NET-H-000510 | FTTH Open Area Pondok Kopi RW 04-07 | FTTH | QODN |  | Jakarta Timur | Duren Sawit | Pondok Kopi | Open Area | 1300 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Bintara (BTRBKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000510 FTTH Open Area Pondok Kopi RW 04-07
595 | Open Area Bintara RW01 | NET-H-000511 | FTTH Open Area Bintara RW01 | FTTH | QODN |  | Kota Bekasi | Bekasi Barat | Bintara | Open Area | 400 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Bintara (BTRBKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000511 FTTH Open Area Bintara RW01
596 | Open Area Bintara Jaya RW 07,09&10 | NET-H-000512 | FTTH Open Area Bintara Jaya RW 07,09&10 | FTTH | QODN |  | Kota Bekasi | Bekasi Barat | Bintara | Open Area | 1000 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Bintara (BTRBKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000512 FTTH Open Area Bintara Jaya RW 07,09&10
597 | Komplek Pesanggrahan Permai RW07 | NET-H-000513 | FTTH Komplek Pesanggrahan Permai RW07 | FTTH | QODN |  | Jakarta Selatan | Pesanggrahan | Petukangan Selatan | Perumahan | 400 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Ciledug (CLDTGR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000513 FTTH Komplek Pesanggrahan Permai RW07
598 | Open Area Petukangan Selatan RW04 | NET-H-000514 | FTTH Open Area Petukangan Selatan RW04 | FTTH | QODN |  | Jakarta Selatan | Pesanggrahan | Petukangan Selatan | Open Area | 800 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Ciledug (CLDTGR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000514 FTTH Open Area Petukangan Selatan RW04
599 | Open Area Petukangan Selatan RW03 | NET-H-000515 | FTTH Open Area Petukangan Selatan RW03 | FTTH | QODN |  | Jakarta Selatan | Pesanggrahan | Petukangan Selatan | Open Area | 700 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Ciledug (CLDTGR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000515 FTTH Open Area Petukangan Selatan RW03
600 | Komplek Bumi Pesanggrahan RW08 | NET-H-000516 | FTTH Komplek Bumi Pesanggrahan RW08 | FTTH | QODN |  | Jakarta Selatan | Pesanggrahan | Petukangan Selatan | Perumahan | 500 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Ciledug (CLDTGR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000516 FTTH Komplek Bumi Pesanggrahan RW08
601 | Open Area Petukangan Selatan RW02&05 | NET-H-000517 | FTTH Open Area Petukangan Selatan RW02&05 | FTTH | QODN |  | Jakarta Selatan | Pesanggrahan | Petukangan Selatan | Open Area | 2300 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Ciledug (CLDTGR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000517 FTTH Open Area Petukangan Selatan RW02&05
602 | Open Area Petukangan Utara RW02 | NET-H-000518 | FTTH Open Area Petukangan Utara RW02 | FTTH | QODN |  | Jakarta Selatan | Pesanggrahan | Petukangan Utara | Open Area | 700 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Ciledug (CLDTGR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000518 FTTH Open Area Petukangan Utara RW02
603 | Open Area Petukangan Utara RW03 | NET-H-000519 | FTTH Open Area Petukangan Utara RW03 | FTTH | QODN |  | Jakarta Selatan | Pesanggrahan | Petukangan Utara | Open Area | 650 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Ciledug (CLDTGR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000519 FTTH Open Area Petukangan Utara RW03
604 | Open Area Petukangan Utara RW10 | NET-H-000520 | FTTH Open Area Petukangan Utara RW10 | FTTH | QODN |  | Jakarta Selatan | Pesanggrahan | Petukangan Utara | Open Area | 600 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Ciledug (CLDTGR) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000520 FTTH Open Area Petukangan Utara RW10
605 | Open Area Pondok Pinang RW02 | NET-H-000521 | FTTH Open Area Pondok Pinang RW02 | FTTH | QODN |  | Jakarta Selatan | Kebayoran Lama | Pondok Pinang | Open Area | 800 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Pondok Pinang (PDPJKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000521 FTTH Open Area Pondok Pinang RW02
606 | Open Area Pondok Pinang RW01 | NET-H-000522 | FTTH Open Area Pondok Pinang RW01 | FTTH | QODN |  | Jakarta Selatan | Kebayoran Lama | Pondok Pinang | Open Area | 1000 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Pondok Pinang (PDPJKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000522 FTTH Open Area Pondok Pinang RW01
607 | Open Area Pondok Pinang RW04&11 | NET-H-000523 | FTTH Open Area Pondok Pinang RW04&11 | FTTH | QODN |  | Jakarta Selatan | Kebayoran Lama | Pondok Pinang | Open Area | 1600 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Pondok Pinang (PDPJKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000523 FTTH Open Area Pondok Pinang RW04&11
608 | Open Area Pondok Pinang RW05 | NET-H-000524 | FTTH Open Area Pondok Pinang RW05 | FTTH | QODN |  | Jakarta Selatan | Kebayoran Lama | Pondok Pinang | Open Area | 500 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Pondok Pinang (PDPJKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000524 FTTH Open Area Pondok Pinang RW05
609 | Open Area Kebayoran Lama Selatan RW10 | NET-H-000525 | FTTH Open Area Kebayoran Lama Selatan RW10 | FTTH | QODN |  | Jakarta Selatan | Kebayoran Lama | Kebayoran Lama Selatan | Open Area | 700 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Pondok Pinang (PDPJKS) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000525 FTTH Open Area Kebayoran Lama Selatan RW10
610 | Open Area Kelapa Dua RW05-06 | NET-H-000526 | FTTH Open Area Kelapa Dua RW05-06 | FTTH | QODN |  | Kab. Tangerang | Kelapa Dua | Kelapa Dua | Open Area | 800 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Kelapa Dua |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000526 FTTH Open Area Kelapa Dua RW05-06
611 | Open Area Kelapa Dua RW07 | NET-H-000527 | FTTH Open Area Kelapa Dua RW07 | FTTH | QODN |  | Kab. Tangerang | Kelapa Dua | Kelapa Dua | Open Area | 500 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Kelapa Dua |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000527 FTTH Open Area Kelapa Dua RW07
612 | Open Area Kelapa Dua RW08 | NET-H-000528 | FTTH Open Area Kelapa Dua RW08 | FTTH | QODN |  | Kab. Tangerang | Kelapa Dua | Kelapa Dua | Open Area | 700 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Kelapa Dua |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000528 FTTH Open Area Kelapa Dua RW08
613 | Open Area Kelapa Dua RW09 | NET-H-000529 | FTTH Open Area Kelapa Dua RW09 | FTTH | QODN |  | Kab. Tangerang | Kelapa Dua | Kelapa Dua | Open Area | 400 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Kelapa Dua |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000529 FTTH Open Area Kelapa Dua RW09
614 | Open Area Kelapa Dua RW03&15 | NET-H-000530 | FTTH Open Area Kelapa Dua RW03&15 | FTTH | QODN |  | Kab. Tangerang | Kelapa Dua | Kelapa Dua | Open Area | 1000 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Kelapa Dua |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000530 FTTH Open Area Kelapa Dua RW03&15
615 | Open Area Manisjaya RW01 | NET-H-000531 | FTTH Open Area Manisjaya RW01 | FTTH | QODN |  | Kota Tangerang | Jatiuwung | Manis Jaya | Open Area | 200 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Plan Kampung Cikoneng |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000531 FTTH Open Area Manisjaya RW01
616 | Open Area Manisjaya RW02 | NET-H-000532 | FTTH Open Area Manisjaya RW02 | FTTH | QODN |  | Kota Tangerang | Jatiuwung | Manis Jaya | Open Area | 150 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Plan Kampung Cikoneng |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000532 FTTH Open Area Manisjaya RW02
617 | Open Area Manisjaya RW03 | NET-H-000533 | FTTH Open Area Manisjaya RW03 | FTTH | QODN |  | Kota Tangerang | Jatiuwung | Manis Jaya | Open Area | 300 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Plan Kampung Cikoneng |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000533 FTTH Open Area Manisjaya RW03
618 | Open Area Manisjaya RW04 | NET-H-000534 | FTTH Open Area Manisjaya RW04 | FTTH | QODN |  | Kota Tangerang | Jatiuwung | Manis Jaya | Open Area | 150 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Plan Kampung Cikoneng |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000534 FTTH Open Area Manisjaya RW04
619 | Open Area Manisjaya RW05 | NET-H-000535 | FTTH Open Area Manisjaya RW05 | FTTH | QODN |  | Kota Tangerang | Jatiuwung | Manis Jaya | Open Area | 300 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Plan Kampung Cikoneng |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000535 FTTH Open Area Manisjaya RW05
620 | Open Area Gandasari RW02 | NET-H-000536 | FTTH Open Area Gandasari RW02 | FTTH | QODN |  | Kota Tangerang | Jatiuwung | Gandasari | Open Area | 400 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Plan Kampung Cikoneng |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000536 FTTH Open Area Gandasari RW02
621 | Open Area Gandasari RW04 & 07 | NET-H-000537 | FTTH Open Area Gandasari RW04 & 07 | FTTH | QODN |  | Kota Tangerang | Jatiuwung | Gandasari | Open Area | 700 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Plan Kampung Cikoneng |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000537 FTTH Open Area Gandasari RW04 & 07
622 | Open Area Gandasari RW05 | NET-H-000538 | FTTH Open Area Gandasari RW05 | FTTH | QODN |  | Kota Tangerang | Jatiuwung | Gandasari | Open Area | 600 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Plan Kampung Cikoneng |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000538 FTTH Open Area Gandasari RW05
623 | Open Area Kadu RW01 | NET-H-000539 | FTTH Open Area Kadu RW01 | FTTH | QODN |  | Kab. Tangerang | Curug | Kadu | Open Area | 800 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Plan Kampung Cikoneng |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000539 FTTH Open Area Kadu RW01
624 | Open Area jatake RW07 | NET-H-000540 | FTTH Open Area jatake RW07 | FTTH | QODN |  | Kota Tangerang | Jatiuwung | Jatake | Open Area | 300 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Plan Kampung Cikoneng |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000540 FTTH Open Area jatake RW07
625 | Open Area Cakung Timur RW12 | NET-H-000541 | FTTH Open Area Cakung Timur RW12 | FTTH | QODN |  | Jakarta Timur | Cakung | Cakung Timur | Open Area | 700 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Cihuuy (CHYJKT) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000541 FTTH Open Area Cakung Timur RW12
626 | Open Area Cakung Timur RW05 | NET-H-000542 | FTTH Open Area Cakung Timur RW05 | FTTH | QODN |  | Jakarta Timur | Cakung | Cakung Timur | Open Area | 500 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Cihuuy (CHYJKT) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000542 FTTH Open Area Cakung Timur RW05
627 | Open Area Cakung Timur RW03 | NET-H-000543 | FTTH Open Area Cakung Timur RW03 | FTTH | QODN |  | Jakarta Timur | Cakung | Cakung Timur | Open Area | 300 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Cihuuy (CHYJKT) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000543 FTTH Open Area Cakung Timur RW03
628 | Open Area Cakung Timur RW09 | NET-H-000544 | FTTH Open Area Cakung Timur RW09 | FTTH | QODN |  | Jakarta Timur | Cakung | Cakung Timur | Open Area | 700 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Cihuuy (CHYJKT) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000544 FTTH Open Area Cakung Timur RW09
629 | Open Area Cakung Timur RW04 & 11 | NET-H-000545 | FTTH Open Area Cakung Timur RW04 & 11 | FTTH | QODN |  | Jakarta Timur | Cakung | Cakung Timur | Open Area | 800 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 1. Sitac Process | Funnel BTS Cihuuy (CHYJKT) |  | Sitac On Process | [7 empty] | Need Assign Team | [35 empty] | NET-H-000545 FTTH Open Area Cakung Timur RW04 & 11
630 | Open Area Jl Kemang Selatan II RT 02 RW 08 | NET-H-000546 | FTTH Open Area Jl Kemang Selatan II RT 02 RW 08 | FTTH | QODN |  | Jakarta Selatan | Mampang prapatan | Bangka | Open Area | 40 | 7 | 7 | NON-KSO | Nethome |  | INHOUSE | 4. Electrical Work | 7. E2E Integration | Progress Civil & Pemasangan ODN | No Issue | Installation On Progress | [15 empty] | 56 |  | 2025-01-15 | 2025-01-15 | 56 | Muchamad Rivai | Done APD | Uploaded to Drive | APD NET-H-000546 FTTH Open Area Jl Kemang Selatan II RT 02 RW 08 (56 HP) |  | BTS Kemang | 1 | 1 | 7 | 7 |  |  | 1033 | [10 empty] | NET-H-000546 FTTH Open Area Jl Kemang Selatan II RT 02 RW 08
631 | Cilenggang RW 01 | NET-H-000547 | FTTH Kelurahan Cilenggang RW 01 | FTTH | QODN |  | Tangerang Selatan | Serpong | Cilenggang | Open Area | 400 | 31 |  | NON-KSO | Nethome |  | INHOUSE | 3. Civil Work | 5. Waiting Implementation |  |  | Waiting Implementation | [15 empty] | 263 |  | 2025-01-17 | 2025-01-17 | 263 | M. Raul Habib | Done APD | Uploaded to Drive | NET-H-000547 FTTH Kelurahan Cilenggang RW 01 |  | BTS Doddy | 3 | 6 | 31 | 38 |  | 3 | 2784 |  | 1183 | [8 empty] | NET-H-000547 FTTH Kelurahan Cilenggang RW 01
632 | RW 01 Kelurahan Grogol Utara | NET-H-000548 | FTTH RW 01 Kelurahan Grogol Utara | FTTH | QODN |  | Jakarta Selatan | Kebayoran Lama | Grogol Utara | Open Area | 200 |  |  | NON-KSO | Nethome |  |  | 2. Survey, Sitac & Design | 3. OG APD |  |  | Sitac On Process
633 | Extendtion RT04 RW07 Kelurahan Sukadamai | NET-H-000549 | FTTH Extendtion RT04 RW07 Kelurahan Sukadamai | FTTH | QODN |  | Kota Bogor | Tanah Sereal | Sukadamai | Open Area | 107 |  |  | NON-KSO | Nethome |  | RPS (Rizki Prima Sakti) | 2. Survey, Sitac & Design | 2. OG Survey |  |  | Survey On Process
634 | Open Area Pegangsaan Dua Rw.03 | NET-H-000550 | FTTH Open Area Pegangsaan Dua Rw.03 | FTTH | QODN |  | Jakarta Utara | Kelapa Gading | Pegangsaan Dua | Open Area | 500 |  |  | NON-KSO | Nethome |  | Fibeart | 2. Survey, Sitac & Design | 1. Sitac Process |  |  | Sitac On Process
635 | Apartemen Casablanca East Resident 1 | NET-B-000034 | FTTB Apartemen Casablanca East Resident 1 | FTTB | Reverse |  | Jakarta Timur | Duren Sawit | Pd. Bambu | Apartment | [7 empty] | 2. Survey, Sitac & Design | 3. OG APD |  |  | Sitac On Process | [7 empty] | On Progress |  | Fahriah Marketing |  |  | 2025-01-22 | Aris Tegar | Done
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677 | [11 empty] | 0

## Hubbox (hidden)
Rangkaian ODN yang ter instal
No. | Cluster / Client Name | Project Name | Nomor Hubbox | ID Hubbox | Project Type | Propose Hub Box | Lat | Long | Rak / OTB / Port | Jumlah input aktif | Splitter Hubbox | Rangkaian 2 | Rangkaian 4 | Rangkaian 8 | Req WO Splice Date | WO Splice Date | WO Splice Number | Vendor Splice | Status | Done WO Splice | Done WO Splice Date | RFS Date | Remaks
1 | FTTH Cilenggang RW 04 | FTTH Cilenggang RW 04 | Hub Box 1 |  | NON-KSO | Inhouse
2 | FTTH Cilenggang RW 04 | FTTH Cilenggang RW 04 | Hub Box 2 |  | NON-KSO | Inhouse
3 | Prosky Pakulonan | Prosky Pakulonan | Hub Box 1 |  | NON-KSO | Inhouse
4 | FTTH Jl. Sinar Asih - Jatiasih RT01 RW08 | FTTH Jl. Sinar Asih - Jatiasih RT01 RW08 | Hub Box 1 |  | NON-KSO | Inhouse
5 | FTTH Jl. Sinar Asih - Jatiasih RT01 RW08 | FTTH Jl. Sinar Asih - Jatiasih RT01 RW08 | Hub Box 2 |  | NON-KSO | Inhouse
6 | jl lokomotif Kaliabang tengah RT 02 RW 15 | jl lokomotif Kaliabang tengah RT 02 RW 15 | Hub Box 1 |  | NON-KSO | Inhouse
7 | RT 24 dan RT 23 RW 03 BABELAN | RT 24 dan RT 23 RW 03 BABELAN | Hub Box 1 |  | NON-KSO | Inhouse
8 | FTTH RT 02 TAMAN RAHAYU | FTTH RT 02 TAMAN RAHAYU | Hub Box 1 |  | NON-KSO | Inhouse
9 | FTTH Jl. H. Taip | FTTH Jl. H. Taip | Hub Box 1 |  | NON-KSO | Inhouse
10 | FTTH Jl. H. Taip | FTTH Jl. H. Taip | Hub Box 2 |  | NON-KSO | Inhouse
11 | FTTH Jl.H. Abdul Gani-Cempaka Putih,Tangsel | FTTH Jl.H. Abdul Gani-Cempaka Putih,Tangsel | Hub Box 1 |  | NON-KSO | Inhouse
12 | FTTH Jl.Perintis | FTTH Jl.Perintis | Hub Box 1 |  | NON-KSO | Inhouse
13 | FTTH Jl. Lobak - Pondok Cabe Ilir | FTTH Jl. Lobak - Pondok Cabe Ilir | Hub Box 1 |  | NON-KSO | Inhouse
14 | FTTH Jl. Lobak - Pondok Cabe Ilir | FTTH Jl. Lobak - Pondok Cabe Ilir | Hub Box 2 |  | NON-KSO | Inhouse
15 | FTTH JL. BUKIT RAYA II - PISANGAN | FTTH JL. BUKIT RAYA II - PISANGAN | Hub Box 1 |  | NON-KSO | Inhouse
16 | FTTH Jl. Muri Salim | FTTH Jl. Muri Salim | Hub Box 1 |  | NON-KSO | Inhouse
17 | FTTH Jl. Muri Salim | FTTH Jl. Muri Salim | Hub Box 2 |  | NON-KSO | Inhouse
18 | FTTH Jl. Masjid Baitulsalam | FTTH Jl. Masjid Baitulsalam | Hub Box 1 |  | NON-KSO | Inhouse
19 | FTTH Jl. Masjid Baitulsalam | FTTH Jl. Masjid Baitulsalam | Hub Box 2 |  | NON-KSO | Inhouse
20 | FTTH Kelurahan Pondok Kacang Timur RW 02 | FTTH Kelurahan Pondok Kacang Timur RW 02 | Hub Box 1 |  | NON-KSO | Inhouse
21 | FTTH Kelurahan Pondok Kacang Timur RW 02 | FTTH Kelurahan Pondok Kacang Timur RW 02 | Hub Box 2 |  | NON-KSO | Inhouse
22 | PLAN QODN BTS Babelan jalur Client TCF-18708 Project Bapak Fandi | FTTH Jl Kebalenan - Jl Turi Kel. Babelan | Hub Box 1 |  | NON-KSO | Rinjani | -6.1711 | 107.0462 | BBLBKS/OL/02/0#11 | 2 | - | - | - | 2 Line | 2024-08-29 | 2024-08-29 | 1276/SPLICE-RINJANI/FMI/VIII/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-11
23 | PLAN QODN BTS Babelan jalur Client TCF-18708 Project Bapak Fandi | FTTH Jl Kebalenan - Jl Turi Kel. Babelan | Hub Box 2 |  | NON-KSO | Rinjani | -6.1714 | 107.0483 | BBLBKS/OL/02/0#12 | 2 | - | - | - | 2 Line | 2024-08-29 | 2024-08-29 | 1276/SPLICE-RINJANI/FMI/VIII/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-11
24 | FTTH QODN Jl.Arah Pabrik Relaxa Kel.Medan Satria | FTTH QODN Jl.Arah Pabrik Relaxa Kel.Medan Satria | Hub Box 1 |  | KSO | Pak Sarno | -6.1967 | 106.973 | UMNBKS/OL/02/5#3-4 | 2 | - | - | - | 2 Line | 2024-08-28 | 2024-08-29 | 1268/SPLICE-RINJANI/FMI/VIII/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-11
25 | Plan QODN Backbone Kaliabang - Jl.Ujung Harapan | FTTH QODN Backbone Kaliabang - Jl.Ujung Harapan | Hub Box 1 |  | NON-KSO | Rinjani | -6.189 | 106.9992 | KLBBKS/OL/02/5#2 | 1 | - | - | - | 1 Line | 2024-09-09 | 2024-09-10 | 1331/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-15
26 | Plan QODN Backbone Kaliabang - Jl.Ujung Harapan | FTTH QODN Backbone Kaliabang - Jl.Ujung Harapan | Hub Box 2 |  | NON-KSO | Rinjani | -6.1895 | 107.0072 | KLBBKS/OL/02/10#07 | 1 | - | - | - | 1 Line | 2024-09-09 | 2024-09-10 | 1331/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-15
27 | Plan QODN Backbone Kaliabang - Jl.Ujung Harapan | FTTH QODN Backbone Kaliabang - Jl.Ujung Harapan | Hub Box 3 |  | NON-KSO | Rinjani | -6.1896 | 107.0107 | KLBBKS/OL/01/10#08-09 | 2 | - | - | - | 2 Line | 2024-09-09 | 2024-09-10 | 1331/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-15
28 | Plan QODN Backbone Kaliabang - Jl.Ujung Harapan | FTTH QODN Backbone Kaliabang - Jl.Ujung Harapan | Hub Box 4 |  | NON-KSO | Rinjani | -6.1897 | 107.0127 | KLBBKS/OL/02/10#10 | 1 | - | - | - | 1 Line | 2024-09-09 | 2024-09-10 | 1331/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-15
29 | Plan QODN Backbone Kaliabang - Jl.Ujung Harapan | FTTH QODN Backbone Kaliabang - Jl.Ujung Harapan | Hub Box 5 |  | NON-KSO | Rinjani | -6.1897 | 107.014 | KLBBKS/OL/02/10#11-12 | 2 | - | - | - | 2 Line | 2024-09-09 | 2024-09-10 | 1331/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-15
30 | Plan QODN Backbone Kaliabang - Jl.Ujung Harapan | FTTH QODN Backbone Kaliabang - Jl.Ujung Harapan | Hub Box 6 |  | NON-KSO | Rinjani | -6.19 | 107.0163 | KLBBKS/OL/02/10#13 | 1 | - | - | - | 1 Line | 2024-09-09 | 2024-09-10 | 1331/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-15
31 | Plan QODN Backbone Kaliabang - Jl.Ujung Harapan | FTTH QODN Backbone Kaliabang - Jl.Ujung Harapan | Hub Box 7 |  | NON-KSO | Rinjani | -6.1901 | 107.0185 | KLBBKS/OL/02/10#14 | 1 | - | - | - | 1 Line | 2024-09-09 | 2024-09-10 | 1331/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-15
32 | Plan QODN Backbone Kaliabang - Jl.Ujung Harapan | FTTH QODN Backbone Kaliabang - Jl.Ujung Harapan | Hub Box 8 |  | NON-KSO | Rinjani | -6.1903 | 107.0197 | KLBBKS/OL/02/10#15 | 1 | - | - | - | 1 Line | 2024-09-09 | 2024-09-10 | 1331/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-15
33 | Propose Plan QODN jalur Backbone Kaliabang - Ujung Harapan Bahagia | FTTH QODN (Part 2) Jalur Backbone Kaliabang - Ujung Harapan Bahagia | Hub Box 1 |  | NON-KSO | Rinjani | -6.1713 | 107.0246 | BBLBKS/OL/02/0#13 | 1 | - | - | - | 1 Line | 2024-09-10 | 2024-09-10 | 1333/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-14
34 | Propose Plan QODN jalur Backbone Kaliabang - Ujung Harapan Bahagia | FTTH QODN (Part 2) Jalur Backbone Kaliabang - Ujung Harapan Bahagia | Hub Box 2 |  | NON-KSO | Rinjani | -6.1648 | 107.0242 | BBLBKS/OL/02/0#14 | 1 | - | - | - | 1 Line | 2024-09-10 | 2024-09-10 | 1333/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-14
35 | Propose QODN Jalur Backbone Kaliabang - Jl. Timaha Raya | FTTH QODN Jalur Backbone Kaliabang - Jl. Timaha Raya | Hub Box 1 |  | NON-KSO | Rinjani | -6.1602 | 107.0405 | BBLBKS/OL/01/4#0 | 1 | - | - | - | 1 Line | 2024-09-11 | 2024-09-11 | 1341/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-21
36 | Propose QODN Jalur Backbone Kaliabang - Jl. Timaha Raya | FTTH QODN Jalur Backbone Kaliabang - Jl. Timaha Raya | Hub Box 2 |  | NON-KSO | Rinjani | -6.16 | 107.038 | BBLBKS/OL/01/4#1 | 1 | - | - | - | 1 Line | 2024-09-11 | 2024-09-11 | 1341/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-21
37 | Propose QODN Jalur Backbone Kaliabang - Jl. Timaha Raya | FTTH QODN Jalur Backbone Kaliabang - Jl. Timaha Raya | Hub Box 3 |  | NON-KSO | Rinjani | -6.16 | 107.0369 | BBLBKS/OL/01/4#2 | 1 | - | - | - | 1 Line | 2024-09-11 | 2024-09-11 | 1341/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-21
38 | Propose QODN Jalur Backbone Kaliabang - Jl. Timaha Raya | FTTH QODN Jalur Backbone Kaliabang - Jl. Timaha Raya | Hub Box 4 |  | NON-KSO | Rinjani | -6.1604 | 107.0304 | BBLBKS/OL/01/4#3 | 1 | - | - | - | 1 Line | 2024-09-11 | 2024-09-11 | 1341/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-21
39 | Propose Plan QODN BACKBONE KALIABANG - JL.TAJJUDIN SEGMENT 1 | FTTH QODN BACKBONE KALIABANG - JL.TAJJUDIN SEGMENT 1 | Hub Box 1 |  | NON-KSO | Rinjani | -6.1923 | 107.0383 | KPIBKS/OL/01/5#11 | 1 | - | - | - | 1 Line | 2024-09-13 | 2024-09-13 | 1351/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-05
40 | Propose Plan QODN BACKBONE KALIABANG - JL.TAJJUDIN SEGMENT 1 | FTTH QODN BACKBONE KALIABANG - JL.TAJJUDIN SEGMENT 1 | Hub Box 2 |  | NON-KSO | Rinjani | -6.191 | 107.0387 | KPIBKS/OL/01/5#12 | 1 | - | - | - | 1 Line | 2024-09-13 | 2024-09-13 | 1351/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-05
41 | Propose Plan QODN BACKBONE KALIABANG - JL.TAJJUDIN SEGMENT 1 | FTTH QODN BACKBONE KALIABANG - JL.TAJJUDIN SEGMENT 1 | Hub Box 3 |  | NON-KSO | Rinjani | -6.1901 | 107.0389 | KPIBKS/OL/01/5#13 | 1 | - | - | - | 1 Line | 2024-09-13 | 2024-09-13 | 1351/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-05
42 | Propose Plan QODN BACKBONE KALIABANG - JL.TAJJUDIN SEGMENT 1 | FTTH QODN BACKBONE KALIABANG - JL.TAJJUDIN SEGMENT 1 | Hub Box 4 |  | NON-KSO | Rinjani | -6.1895 | 107.0389 | KPIBKS/OL/01/5#14 | 1 | - | - | - | 1 Line | 2024-09-13 | 2024-09-13 | 1351/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-05
43 | Propose Plan QODN BACKBONE KALIABANG - JL.TAJJUDIN SEGMENT 1 | FTTH QODN BACKBONE KALIABANG - JL.TAJJUDIN SEGMENT 1 | Hub Box 5 |  | NON-KSO | Rinjani | -6.1887 | 107.039 | KPIBKS/OL/01/5#15-16 | 2 | - | - | - | 2 Line | 2024-09-13 | 2024-09-13 | 1351/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-05
44 | Propose Plan QODN BACKBONE KALIABANG - JL.TAJJUDIN SEGMENT 1 | FTTH QODN BACKBONE KALIABANG - JL.TAJJUDIN SEGMENT 1 | Hub Box 6 |  | NON-KSO | Rinjani | -6.1879 | 107.0391 | KPIBKS/OL/01/5#17 | 1 | - | - | - | 1 Line | 2024-09-13 | 2024-09-13 | 1351/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-05
45 | Propose Plan QODN BACKBONE KALIABANG - JL.TAJJUDIN SEGMENT 1 | FTTH QODN BACKBONE KALIABANG - JL.TAJJUDIN SEGMENT 1 | Hub Box 7 |  | NON-KSO | Rinjani | -6.1838 | 107.0391 | KPIBKS/OL/01/5#18 | 1 | - | - | - | 1 Line | 2024-09-13 | 2024-09-13 | 1351/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-05
46 | BB Jl. KH Tajuddin Segment 2Jl. KH. A. Tajuddin - Jl. Ujung Harapan Bahagia | FTTH QODN BB Jl. KH. A. Tajuddin - Jl. Ujung Harapan Bahagia Segment 2 | Hub Box 1 |  | NON-KSO | Rinjani | -6.1849 | 107.0306 | KPIBKS/OL/01/4#09 | 1 | - | - | - | 1 Line | 2024-09-13 | 2024-09-13 | 1352/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-26
47 | BB Jl. KH Tajuddin Segment 2Jl. KH. A. Tajuddin - Jl. Ujung Harapan Bahagia | FTTH QODN BB Jl. KH. A. Tajuddin - Jl. Ujung Harapan Bahagia Segment 2 | Hub Box 2 |  | NON-KSO | Rinjani | -6.1863 | 107.0305 | KPIBKS/OL/01/4#10 | 1 | - | - | - | 1 Line | 2024-09-13 | 2024-09-13 | 1352/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-26
48 | BB Jl. KH Tajuddin Segment 2Jl. KH. A. Tajuddin - Jl. Ujung Harapan Bahagia | FTTH QODN BB Jl. KH. A. Tajuddin - Jl. Ujung Harapan Bahagia Segment 2 | Hub Box 3 |  | NON-KSO | Rinjani | -6.1884 | 107.0299 | KPIBKS/OL/01/4#11 | 1 | - | - | - | 1 Line | 2024-09-13 | 2024-09-13 | 1352/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-26
49 | BB Jl. KH Tajuddin Segment 2Jl. KH. A. Tajuddin - Jl. Ujung Harapan Bahagia | FTTH QODN BB Jl. KH. A. Tajuddin - Jl. Ujung Harapan Bahagia Segment 2 | Hub Box 4 |  | NON-KSO | Rinjani | -6.1895 | 107.0291 | KPIBKS/OL/01/4#12 | 1 | - | - | - | 1 Line | 2024-09-13 | 2024-09-13 | 1352/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-09-26
50 | Propose Plan Fat Q ODN Jalur Backbone Kaliabang - Jl. Tajjudin Seg 3 | FTTH QODN Jalur Backbone Kaliabang - Jl. Tajjudin Seg 3 | Hub Box 1 |  | NON-KSO | Rinjani | -6.1923 | 107.0196 | KPIBKS/OL/01/5#8 | 1 | - | - | - | 2 Line | 2024-09-13 | 2024-09-13 | 1353/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-12
51 | Propose Plan Fat Q ODN Jalur Backbone Kaliabang - Jl. Tajjudin Seg 3 | FTTH QODN Jalur Backbone Kaliabang - Jl. Tajjudin Seg 3 | Hub Box 2 |  | NON-KSO | Rinjani | -6.1925 | 107.0208 | KPIBKS/OL/01/5#9 | 1 | - | - | - | 2 Line | 2024-09-13 | 2024-09-13 | 1353/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-12
52 | Propose Plan Fat Q ODN Jalur Backbone Kaliabang - Jl. Tajjudin Seg 3 | FTTH QODN Jalur Backbone Kaliabang - Jl. Tajjudin Seg 3 | Hub Box 3 |  | NON-KSO | Rinjani | -6.1927 | 107.0211 | KPIBKS/OL/01/5#10 | 1 | - | - | - | 1 Line | 2024-09-13 | 2024-09-13 | 1353/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-12
52 | Propose Plan Fat Q ODN Jalur Backbone Kaliabang - Jl. Tajjudin Seg 3 | FTTH QODN Jalur Backbone Kaliabang - Jl. Tajjudin Seg 3 | Hub Box 4 |  | NON-KSO | Rinjani | -6.1933 | 107.0226 | KPIBKS/OL/01/5#11 | 1 | - | - | - | 1 Line | 2024-09-13 | 2024-09-13 | 1353/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-12
52 | Propose Plan Fat Q ODN Jalur Backbone Kaliabang - Jl. Tajjudin Seg 3 | FTTH QODN Jalur Backbone Kaliabang - Jl. Tajjudin Seg 3 | Hub Box 5 |  | NON-KSO | Rinjani | -6.1945 | 107.0265 | KPIBKS/OL/01/5#12 | 1 | - | - | - | 1 Line | 2024-09-13 | 2024-09-13 | 1353/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-12
52 | Propose Plan Fat Q ODN Jalur Backbone Kaliabang - Jl. Tajjudin Seg 3 | FTTH QODN Jalur Backbone Kaliabang - Jl. Tajjudin Seg 3 | Hub Box 6 |  | NON-KSO | Rinjani | -6.1962 | 107.0271 | KPIBKS/OL/01/5#13 | 1 | - | - | - | 1 Line | 2024-09-13 | 2024-09-13 | 1353/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-12
52 | Propose Plan Fat Q ODN Jalur Backbone Kaliabang - Jl. Tajjudin Seg 3 | FTTH QODN Jalur Backbone Kaliabang - Jl. Tajjudin Seg 3 | Hub Box 7 |  | NON-KSO | Rinjani | -6.1977 | 107.0289 | KPIBKS/OL/01/5#14 | 1 | - | - | - | 1 Line | 2024-09-13 | 2024-09-13 | 1353/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-12
52 | Propose Plan Fat Q ODN Jalur Backbone Kaliabang - Jl. Tajjudin Seg 3 | FTTH QODN Jalur Backbone Kaliabang - Jl. Tajjudin Seg 3 | Hub Box 8 |  | NON-KSO | Rinjani | -6.2012 | 107.0287 | KPIBKS/OL/01/5#15 | 1 | - | - | - | 1 Line | 2024-09-13 | 2024-09-13 | 1353/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-12
52 | Propose Plan Fat Q ODN Jalur Backbone Kaliabang - Jl. Tajjudin Seg 3 | FTTH QODN Jalur Backbone Kaliabang - Jl. Tajjudin Seg 3 | Hub Box 9 |  | NON-KSO | Rinjani | -6.2034 | 107.0295 | KPIBKS/OL/01/6#1-2 | 2 | - | - | - | 1 Line | 2024-09-13 | 2024-09-13 | 1353/SPLICE-RINJANI/FMI/IX/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-12
52 | Propose QODN Backbone Jatirasa - Via Vilani | FTTH QODN Backbone Jatirasa - Via Vilani | Hub Box 1 |  | NON-KSO | Rinjani | -6.2995 | 106.9706 | JTRBKS#1_3/0-1_H001 | 2 | - | - | - | 2 Line | 04-Okt-2024 | 04-Okt-2024 | 1438/SPLICE-RINJANI/FMI/X/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-11
52 | Propose QODN Backbone Jatirasa - Via Vilani | FTTH QODN Backbone Jatirasa - Via Vilani | Hub Box 2 |  | NON-KSO | Rinjani | -6.3003 | 106.9705 | JTRBKS#1_3/2-4_H002 | 3 | - | - | - | 3 Line | 04-Okt-2024 | 04-Okt-2024 | 1438/SPLICE-RINJANI/FMI/X/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-11
52 | Propose QODN Backbone Jatirasa - Via Vilani | FTTH QODN Backbone Jatirasa - Via Vilani | Hub Box 3 |  | NON-KSO | Rinjani | -6.3032 | 106.9702 | JTRBKS#1_3/5_H003 | 1 | 1 | - | 2 Line | - | 04-Okt-2024 | 04-Okt-2024 | 1438/SPLICE-RINJANI/FMI/X/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-11
52 | Propose QODN Backbone Jatirasa - Via Vilani | FTTH QODN Backbone Jatirasa - Via Vilani | Hub Box 4 |  | NON-KSO | Rinjani | -6.306 | 106.9711 | JTRBKS#1_3/6-7_H004 | 2 | - | - | - | 2 Line | 04-Okt-2024 | 04-Okt-2024 | 1438/SPLICE-RINJANI/FMI/X/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-11
52 | Propose QODN Backbone Jatirasa - Via Vilani | FTTH QODN Backbone Jatirasa - Via Vilani | Hub Box 5 |  | NON-KSO | Rinjani | -6.3089 | 106.9721 | JTRBKS#1_4/0-1_H005 | 2 | - | - | - | 2 Line | 04-Okt-2024 | 04-Okt-2024 | 1438/SPLICE-RINJANI/FMI/X/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-11
52 | Propose QODN Backbone Jatirasa - Via Vilani | FTTH QODN Backbone Jatirasa - Via Vilani | Hub Box 6 |  | NON-KSO | Rinjani | -6.3195 | 106.971 | JTRBKS#1_4/2-3_H006 | 2 | - | - | - | 2 Line | 04-Okt-2024 | 04-Okt-2024 | 1438/SPLICE-RINJANI/FMI/X/2024 | Rinjani | Input Core Ready | Done Splice | 2024-10-11
52
52
52
52
52
52
52
52
52
52
52